## Submittal Log Atlas
Project Name: | South Terminal Rehabilitation General Works Package Project Jeddah Airport
Contract No:
Client : | JEDCO
Consultant: | Dar Al Riyadh
Sub Contractor: | Atlas KSA | [7 empty] | TODAY is : |  | 2025-08-04 | [51 empty] | Use this field only for any comment.
System Package: | ICT | [7 empty] | CURRENT DOCUMENT STATUS | [7 empty] | REVISION 00 | [7 empty] | REVISION 01 | [7 empty] | REVISION 02 | [7 empty] | REVISION 03 | [7 empty] | REVISION 04 | [7 empty] | REVISION 05
SN | DOCUMENT TYPE | DOCUMENT RECOD | DISCIPLINE | CATEGORIES | DOCUMENT NAME | VENDOR | SYSTEM | FORECAST / ACTION BY | ATLAS SUBMISSION REFERENCE | CURRENT REV | SUB DATE | REPLY REF | REPLY DATE | STATUS CODE | REVIEW PERIOD | OVERDUE | ATLAS SUBMISSION REFERENCE | SUBMISSION DATE | DAR REFERENCE | DAR SUBMISSION DATE | REPLY REF | REPLY DATE | STATUS CODE | REVIEW PERIOD | ATLAS SUBMISSION REFERENCE | SUBMISSION DATE | DAR REERENCE NUMBER | DAR SUBMISSION DATE | REPLY REF | REPLY DATE | STATUS CODE | REVIEW PERIOD | ATLAS SUBMISSION REFERENCE | SUBMISSION DATE | DAR REERENCE NUMBER | DAR SUBMISSION DATE | REPLY REF | REPLY DATE | STATUS CODE | REVIEW PERIOD | ATLAS SUBMISSION REFERENCE | CURRENT REV | DAR REERENCE NUMBER | DAR SUBMISSION DATE | REPLY REF | REPLY DATE | STATUS CODE | REVIEW PERIOD | ATLAS SUBMISSION REFERENCE | ATLAS SUB DATE | DAR REERENCE NUMBER | DAR SUBMISSION DATE | REPLY REF | REPLY DATE | STATUS CODE | REVIEW PERIOD | ATLAS SUBMISSION REFERENCE | CURRENT REV | REPLY REF | REPLY DATE | STATUS CODE | REVIEW PERIOD
SN | DOCTYPE | DOCR | DISC | CATEGORY | DOC_NAME | VENDOR_NAME | SYSTEM | ACTION_BY | ATLAS_LATEST_SUBMISSION | ATLAS_LASTEST_REV | ATLAS_LATEST_SUB_DATE | DAR_LASTEST_SUBMISSION | DAR_REPLY_DATE | CURRENT_STATUS | REVIEW_C | DAR_OVERDUE | ST0 | STD0 | STD02 | STD03 | JVT0 | JVD0 | STATUS0 | REVIEW0 | ST1 | STD1 | STD12 | STD13 | JVT1 | JVD1 | STATUS1 | REVIEW1 | ST2 | ST22 | ST23 | STD2 | JVT2 | JVD2 | STATUS2 | REVIEW2 | ST3 | STD3 | STD33 | STD32 | JVT3 | JVD3 | STATUS3 | REVIEW3 | ST4 | STD4 | STD42 | STD43 | JVT4 | JVD4 | STATUS4 | REVIEW5 | ST5 | STD5 | JVT5 | JVD5 | STATUS5 | REVIEW52 | REMARKS
1 | PQ | --- | General | Project Submittal | Prequalification of Distributor (PQM) - Metra Cisco Partner | METRA | CNE |  | ATLS-004-PQM-ICT-00001-R01 | 1 | 2025-05-08 | ATV-1300000403-PQM-ICT-00005-R01 | 2025-05-12 | Code 1 | 4 | 4 | ATLS-004-PQM-ICT-00001-R00 | 2025-04-10 | ATV-1300000403-PQM-ICT-00005-R00 | 2025-04-13 | ATV-1300000403-PQM-ICT-00005-R00 | 2025-04-13 | Code 2 |  | ATLS-004-PQM-ICT-00001-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00005-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00005-R01 | 2025-05-12 | Code 1
2 | PQ | --- | General | Project Submittal | Prequalification of Distributor (PQM) - Anixter CommScope Partner | ANIXTER | SCN |  | ATLS-004-PQM-ICT-00002-R01 | 1 | 2025-05-08 | ATV-1300000403-PQM-ICT-00006-R01 | 2025-05-12 | Code 2 | 4 | 4 | ATLS-004-PQM-ICT-00002-R00 | 2025-04-10 | ATV-1300000403-PQM-ICT-00006-R00 | 2025-04-13 | ATV-1300000403-PQM-ICT-00006-R00 | 2025-04-13 | Code 2 |  | ATLS-004-PQM-ICT-00002-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00006-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00006-R01 | 2025-05-12 | Code 2
3 | PQ | --- | General | Project Submittal | Prequalification of Distributor (PQM) - SITA | SITA | BCE, IDS, BRS |  | ATLS-004-PQM-ICT-00003-R01 | 1 | 2025-04-28 | ATV-1300000403-PQM-ICT-00004-r01 | 2025-04-30 | Code 1 | 2 | 2 | ATLS-004-PQM-ICT-00003-R00 | 2025-04-10 | ATV-1300000403-PQM-ICT-00004-R00 | 2025-04-12 | ATV-1300000403-PQM-ICT-00004-R00 | 2025-04-13 | Code 2 |  | ATLS-004-PQM-ICT-00003-R01 | 2025-04-28 | ATV-1300000403-PQM-ICT-00004-R01 | 2025-04-28 | ATV-1300000403-PQM-ICT-00004-r01 | 2025-04-30 | Code 1
4 | PQ | --- | General | Project Submittal | Prequalification For IDEX Services Co. | IDEX | CPGS |  | ATLS-004-PQM-ICT-00004-R01 | 1 | 2025-05-01 | ATV-1300000403-PQM-ICT-00007-R00 | 2025-04-30 | UR (DAR) | 95 | 95 | ATLS-004-PQM-ICT-00004-R00 | 2025-04-17 | ATV-1300000403-PQM-ICT-00007-R00 | 2025-04-17 | ATV-1300000403-PQM-ICT-00007-R00 | 2025-04-30 | Code 3 |  | ATLS-004-PQM-ICT-00004-R01 | 2025-05-01 | ATV-1300000403-PQM-ICT-00007-R01 | 2025-07-22 |  |  | UR (DAR)
5 | PQ | --- | General | Project Submittal | Prequalification For Saudi Electronic Trading and Contracting Company Limited (SETRA) | SETRA | SACS |  | ATLS-004-PQM-ICT-00005-R02 | 2 | 2025-05-20 | ATV-1300000403-PQM-ICT-00008-R02 | 2025-05-26 | Code 1 | 6 | 6 | ATLS-004-PQM-ICT-00005-R00 | 2025-04-18 | ATV-1300000403-PQM-ICT-00008-R00 | 2025-04-20 | ATV-1300000403-PQM-ICT-00008-R00 | 2025-04-27 | Code 2 |  | ATLS-004-PQM-ICT-00005-R01 | 2025-05-07 | ATV-1300000403-PQM-ICT-00008-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00008-R01 | 2025-05-11 | Code 2 |  | ATLS-004-PQM-ICT-00005-R02 | 2025-05-19 | ATV-1300000403-PQM-ICT-00008-R02 | 2025-05-20 | ATV-1300000403-PQM-ICT-00008-R02 | 2025-05-26 | Code 1
6 | PQ | --- | General | Project Submittal | Prequalification of Subcontractor for ICT Works - Atlas Security |  |  |  | ATLS-004-PAS-ICT-00002-R00 | 0 | 2025-02-03 | ATV-1300000403-PAS-ICT-00002-R00 | 2025-04-06 | Code 1 | 62 | 62 | ATLS-004-PAS-ICT-00002-R00 | 2025-02-03 | ATV-1300000403-PAS-ICT-00002-R00 | 2025-03-27 | ATV-1300000403-PAS-ICT-00002-R00 | 2025-04-06 | Code 1
7 | MTS | --- | Communications | Project Submittal | Material Submittal for Structured Cabling Network - Backbone cabling | ANIXTER | SCN |  | ATLS-004-MTS-ICT-00020-R01 | 1 | 2025-06-11 | ATV-1300000403-MTS-ICT-00002-R01 | 2025-06-17 | Code 1 | 6 | 6 | ATLS-004-MTS-ICT-00020-R00 | 2025-04-18 | ATV-1300000403-MTS-ICT-00002-R00 | 2025-04-19 | ATV-1300000403-MTS-ICT-00002-R00 | 2025-04-22 | Code 2 |  | ATLS-004-MTS-ICT-00020-R01 | 2025-06-11 | ATV-1300000403-MTS-ICT-00002-R01 | 2025-06-11 | ATV-1300000403-MTS-ICT-00002-R01 | 2025-06-17 | Code 1
8 | MTS | --- | Communications | Project Submittal | Material Submittal for Stuctured Cabling Network - Horizontal cabling | ANIXTER | SCN |  | ATLS-004-MTS-ICT-00019-R01 | 1 | 2025-06-11 | ATV-1300000403-MTS-ICT-00001-R01 | 2025-06-17 | Code 2 | 6 | 6 | ATLS-004-MTS-ICT-00019-R00 | 2025-04-17 | ATV-1300000403-MTS-ICT-00001-R00 | 2025-04-19 | ATV-1300000403-MTS-ICT-00001-R00 | 2025-04-22 | Code 2 |  | ATLS-004-MTS-ICT-00019-R01 | 2025-06-11 | ATV-1300000403-MTS-ICT-00001-R01 | 2025-06-11 | ATV-1300000403-MTS-ICT-00001-R01 | 2025-06-17 | Code 2
9 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Airport Area Network - AAN | METRA | CNE |  | ATLS-004-MTS-ICT-00009-R02 | 2 | 2025-07-10 | ATV-1300000403-MTS-ICT-00017-R02 | 2025-07-23 | Code 1 | 13 | 13 | ATLS-004-MTS-ICT-00009-R00 | 2025-05-06 | ATV-1300000403-MTS-ICT-00017-R00 | 2025-05-06 | ATV-1300000403-MTS-ICT-00017-R00 | 2025-05-19 | Code 2 |  | ATLS-004-MTS-ICT-00009-R01 | 2025-06-23 | ATV-1300000403-MTS-ICT-00017-R01 | 2025-06-24 | ATV-1300000403-MTS-ICT-00017-R01 | 2025-06-30 | Code 3 |  | ATLS-004-MTS-ICT-00009-R02 | 2025-07-03 | ATV-1300000403-MTS-ICT-00017-R02 | 2025-07-10 | ATV-1300000403-MTS-ICT-00017-R02 | 2025-07-23 | Code 1
10 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - CCTV Dedicate Network | METRA | CNE |  |  | 2 | 2025-05-13 | ATV-1300000403-MTS-ICT-00005-R01 | 2025-05-14 | Code 1 | 1 | 1 | ATLS-004-MTS-ICT-00010-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00005-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00005-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00010-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00005-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00005-R01 | 2025-05-14 | Code 1
11 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - RSAF Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00018-R01 | 1 | 2025-05-19 | ATV-1300000403-MTS-ICT-00012-R01 | 2025-05-21 | Code 1 | 2 | 2 | ATLS-004-MTS-ICT-00018-R00 | 2025-04-25 | ATV-1300000403-MTS-ICT-00012-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00012-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00018-R01 | 2025-05-19 | ATV-1300000403-MTS-ICT-00012-R01 | 2025-05-20 | ATV-1300000403-MTS-ICT-00012-R01 | 2025-05-21 | Code 1
12 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - GID Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00013-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00008-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00013-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00008-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00008-R00 | 2025-04-30 | Code 2 |  | ATLS-004-MTS-ICT-00013-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00008-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00008-R01 | 2025-05-26 | Code 1
13 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - NIC Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00015-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00010-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00015-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00010-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00010-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00015-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00010-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00010-R01 | 2025-05-26 | Code 1
14 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - GDP Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00012-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00007-R01 | 2025-05-25 | Code 1 | 2 | 2 | ATLS-004-MTS-ICT-00012-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00007-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00007-R00 | 2025-04-30 | Code 2 |  | ATLS-004-MTS-ICT-00012-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00007-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00007-R01 | 2025-05-25 | Code 1
15 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Customs Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00011-R01 | 1 | 2025-05-27 | ATV-1300000403-MTS-LAN-00006-R01 | 2025-05-31 | Code 1 | 4 | 4 | ATLS-004-MTS-ICT-00011-R00 | 2025-04-24 | ATV-1300000403-MTS-LAN-00006-R00 | 2025-04-26 | ATV-1300000403-MTS-LAN-00006-R00 | 2025-05-01 | Code 2 |  | ATLS-004-MTS-ICT-00011-R01 | 2025-05-27 | ATV-1300000403-MTS-LAN-00006-R01 | 2025-05-29 | ATV-1300000403-MTS-LAN-00006-R01 | 2025-05-31 | Code 1
16 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Public Area Network | METRA | CNE |  | ATLS-004-MTS-ICT-00016-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-LAN-00013-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00016-R00 | 2025-04-28 | ATV-1300000403-MTS-LAN-00013-R00 | 2025-04-29 | ATV-1300000403-MTS-LAN-00013-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00016-R01 | 2025-05-23 | ATV-1300000403-MTS-LAN-00013-R01 | 2025-05-24 | ATV-1300000403-MTS-LAN-00013-R01 | 2025-05-26 | Code 1
17 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Intelligent Service Network | METRA | CNE |  | ATLS-004-MTS-ICT-00014-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00009-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00014-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00009-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00009-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00014-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00009-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00009-R01 | 2025-05-26 | Code 1
18 | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - RFID Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00017-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00011-R01 | 2025-05-25 | Code 1 | 2 | 2 | ATLS-004-MTS-ICT-00017-R00 | 2025-04-25 | ATV-1300000403-MTS-ICT-00011-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00011-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00017-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00011-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00011-R01 | 2025-05-25 | Code 1
19 | MTS | --- | Communications | Project Submittal | Material Submittal for Master Clock System | SAPLING | MCS |  | ATLS-004-MTS-ICT-00002-R01 | 1 | 2025-05-10 | ATV-1300000403-MTS-ICT-00003-R01 | 2025-05-13 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00002-R00 | 2025-04-23 | ATV-1300000403-MTS-ICT-00003-R00 | 2025-04-23 | ATV-1300000403-MTS-ICT-00003-R00 | 2025-04-29 | Code 2 |  | ATLS-004-MTS-ICT-00002-R01 | 2025-05-10 | ATV-1300000403-MTS-ICT-00003-R01 | 2025-05-10 | ATV-1300000403-MTS-ICT-00003-R01 | 2025-05-13 | Code 1
20 | MTS | --- | Communications | Project Submittal | Material Submittal for Internet Protocol Television System | TECHNACY | IPTV |  | ATLS-004-MTS-ICT-00004-R03 | 3 | 2025-07-24 | ATV-1300000403-MTS-ICT-00015-R03 | 2025-07-28 | Code 1 | 4 | 4 | ATLS-004-MTS-ICT-00004-R00 | 2025-04-30 | ATV-1300000403-MTS-ICT-00015-R00 | 2025-05-01 | ATV-1300000403-MTS-ICT-00015-R00 | 2025-05-19 | Code 2 |  | ATLS-004-MTS-ICT-00004-R01 | 2025-05-28 | ATV-1300000403-MTS-ICT-00015-R01 | 2025-06-04 | ATV-1300000403-MTS-ICT-00015-R01 | 2025-06-17 | Code 2 |  | ATLS-004-MTS-ICT-00004-R02 | 2025-07-07 | ATV-1300000403-MTS-ICT-00015-R02 | 2025-07-09 | ATV-1300000403-MTS-ICT-00015-R02 | 2025-07-16 | Code 2 |  | ATLS-004-MTS-ICT-00004-R03 | 2025-07-24 | ATV-1300000403-MTS-ICT-00015-R03 | 2025-07-24 | ATV-1300000403-MTS-ICT-00015-R03 | 2025-07-28 | Code 1
21 | MTS | --- | Communications | Project Submittal | Material Submittal for IP Based Intercom System | ANIXTER | VIS |  | ATLS-004-MTS-ICT-00026-R01 | 1 | 2025-07-05 | ATV-1300000403-MTS-ICT-00023-R01 | 2025-07-12 | Code 1 | 7 | 7 | ATLS-004-MTS-ICT-00026-R00 | 2025-05-30 | ATV-1300000403-MTS-ICT-00023-R00 | 2025-05-31 | ATV-1300000403-MTS-ICT-00023-R00 | 2025-06-03 | Code 2 |  | ATLS-004-MTS-ICT-00026-R01 | 2025-07-05 | ATV-1300000403-MTS-ICT-00023-R01 | 2025-07-05 | ATV-1300000403-MTS-ICT-00023-R01 | 2025-07-12 | Code 1
22 | MTS | --- | Communications | Project Submittal | Material Submittal for Public Address System | SONIC ELECTRONICS | PAS |  | ATLS-004-MTS-ICT-00007-R00 | 0 | 2025-05-05 | ATV-1300000403-MTS-ICT-00016-R00 | 2025-05-07 | Code 2 | 2 | 2 | ATLS-004-MTS-ICT-00007-R00 | 2025-05-05 | ATV-1300000403-MTS-ICT-00016-R00 | 2025-05-05 | ATV-1300000403-MTS-ICT-00016-R00 | 2025-05-07 | Code 2
23 | MTS | --- | Security and Safety | Project Submittal | Material Submittal for Security Access Control System | SETRA | SACS |  | ATLS-004-MTS-ICT-00003-R01 | 1 | 2025-06-12 | ATV-1300000403-MTS-ICT-00014-R01 | 2025-06-29 | Code 2 | 17 | 17 | ATLS-004-MTS-ICT-00003-R00 | 2025-04-29 | ATV-1300000403-MTS-ICT-00014-R00 | 2025-04-30 | ATV-1300000403-MTS-ICT-00014-R00 | 2025-05-15 | Code 2 |  | ATLS-004-MTS-ICT-00003-R01 | 2025-06-12 | ATV-1300000403-MTS-ICT-00014-R01 | 2025-06-14 | ATV-1300000403-MTS-ICT-00014-R01 | 2025-06-29 | Code 2
24 | MTS | --- | Security and Safety | Project Submittal | Material Submittal for Fire Alarm System | HONEYWELL | FAS |  | ATLS-004-MTS-ICT-00031-R00 | 0 | 2025-07-24 |  |  | UR (DAR) | 11 | 11 | ATLS-004-MTS-ICT-00031-R00 | 2025-07-24 | ATV-1300000403-MTS-ICT-00044-R00 | 2025-07-27 |  |  | UR (DAR)
25 | MTS | --- | Security and Safety | Project Submittal | Material Submittal for Closed Circuit Television System | ANIXTER | CCTV |  | ATLS-004-MTS-ICT-00001-R04 | 4 | 2025-06-19 | ATV-1300000403-MTS-ICT-00004-R04 | 2025-06-23 | Code 1 | 4 | 4 | ATLS-004-MTS-ICT-00001-R00 | 2025-04-23 | ATV-1300000403-MTS-ICT-00004-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00004-R00 | 2025-04-29 | Code 2 |  | ATLS-004-MTS-ICT-00001-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00004-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00004-R01 | 2025-05-15 | Code 2 |  | ATLS-004-MTS-ICT-00001-R02 | 2025-05-21 | ATV-1300000403-MTS-ICT-00004-R02 | 2025-05-21 | ATV-1300000403-MTS-ICT-00004-R02 | 2025-05-26 | Code 1 |  | ATLS-004-MTS-ICT-00001-R03 | 2025-06-04 | ATV-1300000403-MTS-ICT-00004-R03 | 2025-06-10 | ATV-1300000403-MTS-ICT-00004-R03 | 2025-06-17 | Code 2 |  | ATLS-004-MTS-ICT-00001-R04 | 2025-06-19 | ATV-1300000403-MTS-ICT-00004-R04 | 2025-06-22 | ATV-1300000403-MTS-ICT-00004-R04 | 2025-06-23 | Code 1
27 | MTS | --- | Special Airport Systems | Project Submittal | Material Submittal for Border Control Systems - SITA |  | BCE |  | ATLS-004-MTS-ICT-00035-R00 | 0 | 2025-07-08 | ATV-1300000403-MTS-ICT-00039-R00 | 2025-07-13 | Code 2 | 5 | 5 | ATLS-004-MTS-ICT-00035-R00 | 2025-07-08 | ATV-1300000403-MTS-ICT-00039-R00 | 2025-07-08 | ATV-1300000403-MTS-ICT-00039-R00 | 2025-07-13 | Code 2
28 | MTS | --- | Special Airport Systems | Project Submittal | Material Submittal for Information Display Systems | SITA | IDS |  | ATLS-004-MTS-ICT-00027-R00 | 0 | 2025-06-11 | ATV-1300000403-MTS-ICT-00027-R00 | 2025-06-23 | Code 2 | 12 | 12 | ATLS-004-MTS-ICT-00027-R00 | 2025-06-11 | ATV-1300000403-MTS-ICT-00027-R00 | 2025-06-12 | ATV-1300000403-MTS-ICT-00027-R00 | 2025-06-23 | Code 2
29 | MTS | --- | Special Airport Systems | Project Submittal | Material Submittal for Baggage Reonciliation System | SITA | BRS |  | ATLS-004-MTS-ICT-00022-R00 | 0 | 2025-05-15 | ATV-1300000403-MTS-ICT-00018-R00 | 2025-05-20 | Code 2 | 5 | 5 | ATLS-004-MTS-ICT-00022-R00 | 2025-05-15 | ATV-1300000403-MTS-ICT-00018-R00 | 2025-05-18 | ATV-1300000403-MTS-ICT-00018-R00 | 2025-05-20 | Code 2
30 | MST | --- | Communications | Project Submittal | Method Statement for the installation of Stuctured Cabling Network - Backbone cabling | ANIXTER | SCN | Shahul / Ibrar | ATLS-004-MST-ICT-00006-R00 | 0 | 2025-05-29 | ATV-1300000403-MST-ICT-00012-R00 | 2025-07-09 | Code 2 | 41 | 41 | ATLS-004-MST-ICT-00006-R00 | 2025-05-29 | ATV-1300000403-MST-ICT-00012-R00 | 2025-07-07 | ATV-1300000403-MST-ICT-00012-R00 | 2025-07-09 | Code 2
31 | MST | --- | Communications | Project Submittal | Method Statement for the installation of Stuctured Cabling Network - Horizontal cabling | ANIXTER | SCN | Shahul / Ibrar | ATLS-004-MST-ICT-00004-R00 | 0 | 2025-05-25 | ATV-1300000403-MST-ICT-00007-R00 | 2025-06-22 | Code 2 | 28 | 28 | ATLS-004-MST-ICT-00004-R00 | 2025-05-25 | ATV-1300000403-MST-ICT-00007-R00 | 2025-06-17 | ATV-1300000403-MST-ICT-00007-R00 | 2025-06-22 | Code 2
32 | MST | --- | Communications | Project Submittal | Method Statement for the installation of Active Network Equipment - AAN, CCTV Dedicate Network, RSAF Dedicated Network, GID, NIC,GDP, Customs. Pubic Area Network, Intelligent Service, VOIP, Corporate, Public | METRA | CNE | Jideh | ATLS-004-MST-ICT-00016-R00 | 0 | 2025-07-08 |  |  | UR (DAR) | 27 | 27 | ATLS-004-MST-ICT-00016-R00 | 2025-07-08 | ATV-1300000403-MST-ICT-00019-R00 | 2025-07-30 |  |  | UR (DAR)
33 | MST | --- | Communications | Project Submittal | Method Statement for the installation of Master Clock System | SAPLING | MCS | Cahit | ATLS-004-MST-ICT-00011-R01 | 1 | 2025-06-26 | ATV-1300000403-MST-ICT-00005-R01 | 2025-06-30 | Code 1 | 4 | 4 | ATLS-004-MST-ICT-00011-R00 | 2025-06-13 | ATV-1300000403-MST-ICT-00005-R00 | 2025-06-15 | ATV-1300000403-MST-ICT-00005-R00 | 2025-06-18 | Code 3 |  | ATLS-004-MST-ICT-00011-R01 | 2025-06-26 | ATV-1300000403-MST-ICT-00005-R01 | 2025-06-29 | ATV-1300000403-MST-ICT-00005-R01 | 2025-06-30 | Code 1
34 | MST | --- | Communications | Project Submittal | Method Statement for the installation of Internet Protocol Television System | TECHNACY | IPTV | Cahit | ATLS-004-MST-ICT-00008-R01 | 1 | 2025-07-04 | ATV-1300000403-MST-ICT-00002-R01 | 2025-07-09 | Code 1 | 5 | 5 | ATLS-004-MST-ICT-00008-R00 | 2025-05-31 | ATV-1300000403-MST-ICT-00002-R00 | 2025-06-03 | ATV-1300000403-MST-ICT-00002-R00 | 2025-06-12 | Code 2 |  | ATLS-004-MST-ICT-00008-R01 | 2025-07-04 | ATV-1300000403-MST-ICT-00002-R01 | 2025-07-07 | ATV-1300000403-MST-ICT-00002-R01 | 2025-07-09 | Code 1
35 | MST | --- | Communications | Project Submittal | Method Statement for the installation of IP Based Intercom System | GENETIC | VIS | Cahit | ATLS-004-MST-ICT-00014-R00 | 0 | 2025-06-17 | ATV-1300000403-MST-ICT-00013-R00 | 2025-07-13 | Code 2 | 26 | 26 | ATLS-004-MST-ICT-00014-R00 | 2025-06-17 | ATV-1300000403-MST-ICT-00013-R00 | 2025-07-09 | ATV-1300000403-MST-ICT-00013-R00 | 2025-07-13 | Code 2
36 | MST | --- | Communications | Project Submittal | Method Statement for the installation of Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS | Likhil | ATLS-004-MST-ICT-00010-R01 | 1 | 2025-07-07 | ATV-1300000403-MST-ICT-00003-R01 | 2025-07-31 | Code 1 | 24 | 24 | ATLS-004-MST-ICT-00010-R00 | 2025-06-03 | ATV-1300000403-MST-ICT-00003-R00 | 2025-06-04 | ATV-1300000403-MST-ICT-00003-R00 | 2025-06-12 | Code 2 |  | ATLS-004-MST-ICT-00010-R01 | 2025-07-07 | ATV-1300000403-MST-ICT-00003-R01 | 2025-07-30 | ATV-1300000403-MST-ICT-00003-R01 | 2025-07-31 | Code 1
37 | MST | --- | Security and Safety | Project Submittal | Method Statement for the installation of Security Access Control System | SETRA | SACS | Sahla | ATLS-004-MST-ICT-00007-R01 | 1 | 2025-07-31 | ATV-1300000403-MST-ICT-00009-R00 | 2025-06-22 | UR (DAR) | 4 | 4 | ATLS-004-MST-ICT-00007-R00 | 2025-05-25 | ATV-1300000403-MST-ICT-00009-R00 | 2025-06-21 | ATV-1300000403-MST-ICT-00009-R00 | 2025-06-22 | Code 2 |  | ATLS-004-MST-ICT-00007-R01 | 2025-07-31 | ATV-1300000403-MST-ICT-00009-R01 | 2025-08-02 |  |  | UR (DAR)
38 | MST | --- | Security and Safety | Project Submittal | Method Statement for the installation of Fire Alarm System | HONEYWELL | FAS | Riswan | ATLS-004-MST-ICT-00009-R00 | 0 | 2025-07-14 | ATV-1300000403-MST-ICT-00018-R00 | 2025-07-31 | Code 2 | 17 | 17 | ATLS-004-MST-ICT-00009-R00 | 2025-07-14 | ATV-1300000403-MST-ICT-00018-R00 | 2025-07-29 | ATV-1300000403-MST-ICT-00018-R00 | 2025-07-31 | Code 2
39 | MST | --- | Security and Safety | Project Submittal | Method Statement for the installation of Closed Circuit Television System | ANIXTER | CCTV | Cahit | ATLS-004-MST-ICT-00005-R00 | 0 | 2025-05-31 | ATV-1300000403-MST-ICT-00006-R00 | 2025-06-18 | Code 2 | 18 | 18 | ATLS-004-MST-ICT-00005-R00 | 2025-05-31 | ATV-1300000403-MST-ICT-00006-R00 | 2025-06-16 | ATV-1300000403-MST-ICT-00006-R00 | 2025-06-18 | Code 2
41 | MST | --- | Special Airport Systems | Project Submittal | Method Statement for the installation of Border Control Systems | SITA | BCE | Likhil | --- |  |  |  |  | --- | --- | ---
42 | MST | --- | Special Airport Systems | Project Submittal | Method Statement for the installation of Information Display Systems | SITA | IDS | Cahit | --- |  |  |  |  | --- | --- | ---
43 | MST | --- | Special Airport Systems | Project Submittal | Method Statement for the installation of Baggage Reonciliation System | SITA | BRS | Sahla | --- |  |  |  |  | --- | --- | ---
44 | ITP | --- | Communications | Project Submittal | ITP for the installation of Stuctured Cabling Network - Backbone cabling | ANIXTER | SCN |  | ATLS-004-ITP-ICT-00006-R01 | 1 | 2025-07-01 | ATV-1300000403-ITP-ICT-00007-R01 | 2025-06-25 | Code 1 | 34 | 34 | ATLS-004-ITP-ICT-00006-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00007-R00 | 2025-05-29 | ATV-1300000403-ITP-ICT-00007-R00 | 2025-06-25 | Code 2 |  | ATLS-004-ITP-ICT-00006-R01 | 2025-07-01 | ATV-1300000403-ITP-ICT-00007-R01 | 2025-07-01 | ATV-1300000403-ITP-ICT-00007-R01 | 2025-06-02 | Code 1
45 | ITP | --- | Communications | Project Submittal | ITP for the installation of Stuctured Cabling Network - Horizontal cabling | ANIXTER | SCN |  | ATLS-004-ITP-ICT-00002-R01 | 1 | 2025-07-01 | ATV-1300000403-ITP-ICT-00006-R01 | 2025-06-25 | Code 1 | 34 | 34 | ATLS-004-ITP-ICT-00002-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00006-R00 | 2025-05-29 | ATV-1300000403-ITP-ICT-00006-R00 | 2025-06-25 | Code 2 |  | ATLS-004-ITP-ICT-00002-R01 | 2025-07-01 | ATV-1300000403-ITP-ICT-00006-R01 | 2025-07-01 | ATV-1300000403-ITP-ICT-00006-R01 | 2025-06-02 | Code 1
46 | ITP | --- | Communications | Project Submittal | ITP for the installation of Active Network Equipment - Airport Area Network - AAN & Other Stakeholders LAN | METRA | CNE |  | ATLS-004-ITP-ICT-00014-R00 | 0 | 2025-07-12 | ATV-1300000403-ITP-ICT-00016-R00 | 2025-07-20 | Code 2 | 8 | 8 | ATLS-004-ITP-ICT-00014-R00 | 2025-07-12 | ATV-1300000403-ITP-ICT-00016-R00 | 2025-07-17 | ATV-1300000403-ITP-ICT-00016-R00 | 2025-07-20 | Code 2
47 | ITP | --- | Communications | Project Submittal | ITP for the installation of Master Clock System | SAPLING | MCS |  | ATLS-004-ITP-ICT-00007-R00 | 0 | 2025-05-21 | ATV-1300000403-ITP-ICT-00005-R00 | 2025-06-25 | Code 2 | 35 | 35 | ATLS-004-ITP-ICT-00007-R00 | 2025-05-21 | ATV-1300000403-ITP-ICT-00005-R00 | 2025-05-29 | ATV-1300000403-ITP-ICT-00005-R00 | 2025-06-25 | Code 2
48 | ITP | --- | Communications | Project Submittal | ITP for the installation of Internet Protocol Television System | TECHNACY | IPTV |  | ATLS-004-ITP-ICT-00008-R01 | 1 | 2025-06-12 | ATV-1300000403-ITP-ICT-00011-R01 | 2025-06-17 | Code 1 | 5 | 5 | ATLS-004-ITP-ICT-00008-R00 | 2025-05-21 | ATV-1300000403-ITP-ICT-00011-R00 | 2025-05-31 | ATV-1300000403-ITP-ICT-00011-R00 | 2025-06-01 | Code 2 |  | ATLS-004-ITP-ICT-00008-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00011-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00011-R01 | 2025-06-17 | Code 1
49 | ITP | --- | Communications | Project Submittal | ITP for the installation of IP Based Intercom System | GENETIC | VIS |  | ATLS-004-ITP-ICT-00012-R00 | 0 | 2025-06-19 | ATV-1300000403-ITP-ICT-00014-R00 | 2025-06-22 | Code 2 | 3 | 3 | ATLS-004-ITP-ICT-00012-R00 | 2025-06-19 | ATV-1300000403-ITP-ICT-00014-R00 | 2025-06-21 | ATV-1300000403-ITP-ICT-00014-R00 | 2025-06-22 | Code 2
50 | ITP | --- | Communications | Project Submittal | ITP for the installation of Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | ATLS-004-ITP-ICT-00012-R01 | 1 | 2025-06-12 | ATV-1300000403-ITP-ICT-00010-R01 | 2025-06-17 | Code 1 | 5 | 5 | ATLS-004-ITP-ICT-00012-R00 | 2025-05-30 | ATV-1300000403-ITP-ICT-00010-R00 | 2025-05-31 | ATV-1300000403-ITP-ICT-00010-R00 | 2025-06-01 | Code 2 |  | ATLS-004-ITP-ICT-00012-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00010-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00010-R01 | 2025-06-17 | Code 1
51 | ITP | --- | Security and Safety | Project Submittal | ITP for the installation of Access Control System | SETRA | SACS |  | ATLS-004-ITP-ICT-00009-R00 | 0 | 2025-05-23 | ATV-1300000403-ITP-ICT-00008-R00 | 2025-06-25 | Code 2 | 33 | 33 | ATLS-004-ITP-ICT-00009-R00 | 2025-05-23 | ATV-1300000403-ITP-ICT-00008-R00 | 2025-05-29 | ATV-1300000403-ITP-ICT-00008-R00 | 2025-06-25 | Code 2
52 | ITP | --- | Security and Safety | Project Submittal | ITP for the installation of Fire Alarm System | HONEYWELL | FAS |  | ATLS-004-ITP-ICT-00011-R01 | 1 | 2025-05-23 | ATV-1300000403-ITP-ICT-00002-R00 | 2025-05-27 | Code 1 | 4 | 4 | ATLS-004-ITP-ICT-00011-R00 | 2025-05-23 | ATV-1300000403-ITP-ICT-00002-R00 | 2025-04-26 | ATV-1300000403-ITP-ICT-00002-R00 | 2025-05-27 | Code 2 |  | ATLS-004-ITP-ICT-00011-R01 |  | ATV-1300000403-ITP-ICT-00001-R01 |  |  |  | Code 1
53 | ITP | --- | Security and Safety | Project Submittal | ITP for the installation of Closed Circuit Television System | ANIXTER | CCTV |  | ATLS-004-ITP-ICT-00005-R01 | 1 | 2025-06-12 | ATV-1300000403-ITP-ICT-00013-R01 | 2025-06-01 | Code 1 | 53 | 53 | ATLS-004-ITP-ICT-00005-R00 | 2025-05-21 | ATV-1300000403-ITP-ICT-00013-R00 | 2025-05-31 | ATV-1300000403-ITP-ICT-00013-R00 | 2025-06-01 | Code 2 |  | ATLS-004-ITP-ICT-00005-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00013-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00013-R01 | 17 un 25 | Code 1
55 | ITP | --- | Special Airport Systems | Project Submittal | ITP for the installation of Border Control Systems | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
56 | ITP | --- | Special Airport Systems | Project Submittal | ITP for the installation of Flight Information Display Systems | SITA | IDS |  | ATLS-004-ITP-ICT-00017-R00 | 0 | 2025-08-04 |  |  | UR (ATJV) | 0 | 0 | ATLS-004-ITP-ICT-00017-R00 | 2025-08-04 |  |  |  |  | UR (ATJV)
57 | ITP | --- | Special Airport Systems | Project Submittal | ITP for the installation of Baggage Reonciliation System | SITA | BRS |  | ATLS-004-ITP-ICT-00016-R00 | 0 | 2025-08-04 |  |  | UR (ATJV) | 0 | 0 | ATLS-004-ITP-ICT-00016-R00 | 2025-08-04 |  |  |  |  | UR (ATJV)
58 | MTS | --- | Communications | Project Submittal | Material Submittal for Data Communication Hardware - CCTV Server & Storage | DELL/METRA | DCH |  | ATLS-004-MTS-ICT-00030-R00 | 0 | 2025-06-26 | ATV-1300000403-MTS-ICT-00036-R00 | 2025-07-16 | Code 3 | 20 | 20 | ATLS-004-MTS-ICT-00030-R00 | 2025-06-26 | ATV-1300000403-MTS-ICT-00036-R00 | 2025-07-03 | ATV-1300000403-MTS-ICT-00036-R00 | 2025-07-16 | Code 3
59 | MTS | --- | Communications | Project Submittal | Material Submittal for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | SITA | COMMON USE SYSTEMS |  | ATLS-004-MTS-ICT-00023-R01 | 1 | 2025-07-03 | ATV-1300000403-MTS-ICT-00025-R01 | 2025-07-12 | Code 1 | 9 | 9 | ATLS-004-MTS-ICT-00023-R00 | 2025-05-31 | ATV-1300000403-MTS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-MTS-ICT-00025-R00 | 2025-06-12 | Code 3 |  | ATLS-004-MTS-ICT-00023-R01 | 2025-07-03 | ATV-1300000403-MTS-ICT-00025-R01 | 2025-07-05 | ATV-1300000403-MTS-ICT-00025-R01 | 2025-07-12 | Code 1
60 | MST | --- | Communications | Project Submittal | Method Statement for the installation of Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS | Likhil | ATLS-004-MST-ICT-00015-R00 | 0 | 2025-07-07 | ATV-1300000403-MST-ICT-00015-R00 | 2025-07-14 | Code 2 | 7 | 7 | ATLS-004-MST-ICT-00015-R00 | 2025-07-07 | ATV-1300000403-MST-ICT-00015-R00 | 2025-07-13 | ATV-1300000403-MST-ICT-00015-R00 | 2025-07-14 | Code 2
61 | SDD | --- | Communications | Project Submittal | System Design Document for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
62 | SDD | --- | Communications | Project Submittal | System Design Document for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
63 | SDD | --- | Communications | Project Submittal | System Design Document for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
64 | ICD | --- | Communications | Project Submittal | Interface Control Document for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
65 | ICD | --- | Communications | Project Submittal | Interface Control Document for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
66 | ICD | --- | Communications | Project Submittal | Interface Control Document for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
67 | TCD | --- | Communications | Project Submittal | Testing and Commissioning Document Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
68 | TCD | --- | Communications | Project Submittal | Testing and Commissioning Document Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
69 | TCD | --- | Communications | Project Submittal | Testing and Commissioning Document Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
70 | OMM | --- | Communications | Close Out Submittal | Operation & Maintenance Manual for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
71 | OMM | --- | Communications | Close Out Submittal | Operation & Maintenance Manual for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
72 | OMM | --- | Communications | Close Out Submittal | Operation & Maintenance Manual for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
73 | OTM | --- | Communications | Close Out Submittal | Operation Training Manual for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
74 | OTM | --- | Communications | Close Out Submittal | Operation Training Manual for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
75 | OTM | --- | Communications | Close Out Submittal | Operation Training Manual for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
76 | Warranty | --- | Communications | Close Out Submittal | Warranty for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
77 | Warranty | --- | Communications | Close Out Submittal | Warranty for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
78 | Warranty | --- | Communications | Close Out Submittal | Warranty for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
79 | ITP | --- | Communications | Project Submittal | ITP for the installation of Common Use Systems | HP | COMMON USE SYSTEMS |  | ATLS-004-ITP-ICT-00015-R00 | 0 | 2025-08-04 |  |  | UR (ATJV) | 0 | 0 | ATLS-004-ITP-ICT-00015-R00 | 2025-08-04 |  |  |  |  | UR (ATJV)
80 | PQ | --- | General | Project Submittal | Prequalification of Subcontractor for LEVION | ANIXTER | SPECIAL AIRPORT SYSTEM |  | ATLS-004-PQM-ICT-00008-R01 | 1 | 2025-05-23 | ATV-1300000403-PQM-ICT-00010-R00 | 2025-05-15 | UR (DAR) | 73 | 73 | ATLS-004-PQM-ICT-00008-R00 | 2025-05-01 | ATV-1300000403-PQM-ICT-00010-R00 | 2025-05-01 | ATV-1300000403-PQM-ICT-00010-R00 | 2025-05-15 | Code 3 |  | ATLS-004-PQM-ICT-00008-R01 | 2025-05-23 | ATV-1300000403-PQM-ICT-00010-R01 | 2025-07-22 |  |  | UR (DAR)
81 | MST | --- | Communications | Project Submittal | Method Statement for Installation of Cable Tray, Trunk and Basket Tray for Telecommunication System | SAFELINE | CRFE | Ibrar | ATLS-004-MST-ICT-00003-R01 | 1 | 2025-07-03 | ATV-1300000403-MST-ICT-00001-R01 | 2025-07-06 | Code 1 | 3 | 3 | ATLS-004-MST-ICT-00003-R00 | 2025-05-22 | ATV-1300000403-MST-ICT-00001-R00 | 2025-05-26 | ATV-1300000403-MST-ICT-00001-R00 | 2025-06-02 | Code 2 |  | ATLS-004-MST-ICT-00003-R01 | 2025-07-03 | ATV-1300000403-MST-ICT-00001-R01 | 2025-07-03 | ATV-1300000403-MST-ICT-00001-R01 | 2025-07-06 | Code 1
82 | MST | --- | Communications | Project Submittal | Method Statement for Installation of Raceways, Boxes and Accessories for Telecommunication System | SAFELINE | CRFE | Ibrar | ATLS-004-MST-ICT-00001-R00 | 0 | 2025-06-19 | ATV-1300000403-MST-ICT-00010-R00 | 2025-06-22 | Code 2 | 3 | 3 | ATLS-004-MST-ICT-00001-R00 | 2025-06-19 | ATV-1300000403-MST-ICT-00010-R00 | 2025-06-21 | ATV-1300000403-MST-ICT-00010-R00 | 2025-06-22 | Code 2
83 | MST | --- | Communications | Project Submittal | Method Statement for Installation of Rack Cbinets & PDU (AR) | LEGRAND | CRFE |  | ATLS-004-MST-ICT-00012-R01 | 1 | 2025-07-07 | ATV-1300000403-MST-ICT-00004-R01 | 2025-08-03 | Code 1 | 27 | 27 | ATLS-004-MST-ICT-00012-R00 | 2025-06-13 | ATV-1300000403-MST-ICT-00004-R00 | 2025-06-15 | ATV-1300000403-MST-ICT-00004-R00 | 2025-06-18 | Code 2 |  | ATLS-004-MST-ICT-00012-R01 | 2025-07-07 | ATV-1300000403-MST-ICT-00004-R01 | 2025-07-30 | ATV-1300000403-MST-ICT-00004-R01 | 2025-08-03 | Code 1
84 | MST | --- | Communications | Project Submittal | Method Statement for Installation of Floor Trunking and Junction Box For Telecommunication System | SAFELINE | CRFE | Ibrar | ATLS-004-MST-ICT-00002-R00 | 0 | 2025-05-26 | ATV-1300000403-MST-ICT-00008-R00 | 2025-06-22 | Code 2 | 27 | 27 | ATLS-004-MST-ICT-00002-R00 | 2025-05-26 | ATV-1300000403-MST-ICT-00008-R00 | 2025-06-19 | ATV-1300000403-MST-ICT-00008-R00 | 2025-06-22 | Code 2
85 | MTS | --- | Communications | Project Submittal | Material Submittal for Racks & PDU (AR) | ANIXTER | CRFE |  | ATLS-004-MTS-ICT-00008-R00 | 0 | 2025-06-12 | ATV-1300000403-MTS-ICT-00028-R00 | 2025-06-22 | Code 2 | 10 | 10 | ATLS-004-MTS-ICT-00008-R00 | 2025-06-12 | ATV-1300000403-MTS-ICT-00028-R00 | 2025-06-14 | ATV-1300000403-MTS-ICT-00028-R00 | 2025-06-22 | Code 2
86 | MTS | --- | Communications | Project Submittal | Material Submittal for UPS | ANIXTER | CRFE |  | ATLS-004-MTS-ICT-00024-R00 | 0 | 2025-05-30 | ATV-1300000403-MTS-ICT-00024-R00 | 2025-06-02 | Code 2 | 3 | 3 | ATLS-004-MTS-ICT-00024-R00 | 2025-05-30 | ATV-1300000403-MTS-ICT-00024-R00 | 2025-05-31 | ATV-1300000403-MTS-ICT-00024-R00 | 2025-06-02 | Code 2
87 | PQ | --- | General | Project Submittal | Prequalification of Subcontractor for LEGRAND | ANIXTER | LEGRAND |  | ATLS-004-PQM-ICT-00009-R00 | 0 | 2025-05-16 | ATV-1300000403-PQM-ICT-00011-R00 | 2025-05-26 | Code 2 | 10 | 10 | ATLS-004-PQM-ICT-00009-R00 | 2025-05-16 | ATV-1300000403-PQM-ICT-00011-R00 | 2025-05-18 | ATV-1300000403-PQM-ICT-00011-R00 | 2025-05-26 | Code 2
88 | ITP | --- | Communications | Project Submittal | ITP for Installation of Cable Tray, Trunk and Basket Tray for Telecommunication System | SAFELINE | CRFE |  | ATLS-004-ITP-ICT-00001-R01 | 1 | 2025-07-01 | ATV-1300000403-ITP-ICT-00003-R01 | 2025-07-02 | Code 1 | 1 | 1 | ATLS-004-ITP-ICT-00001-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00003-R00 | 2025-05-29 | ATV-1300000403-ITP-ICT-00003-R00 | 2025-06-25 | Code 2 |  | ATLS-004-ITP-ICT-00001-R01 | 2025-07-01 | ATV-1300000403-ITP-ICT-00003-R01 | 2025-07-01 | ATV-1300000403-ITP-ICT-00003-R01 | 2025-07-02 | Code 1
89 | ITP | --- | Communications | Project Submittal | ITP for Installation of Raceways, Boxes and Accessories for Telecommunication System | SAFELINE | CRFE |  | ATLS-004-ITP-ICT-00003-R01 | 1 | 2025-06-12 | ATV-1300000403-ITP-ICT-00012-R01 | 2025-06-17 | Code 1 | 5 | 5 | ATLS-004-ITP-ICT-00003-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-ITP-ICT-00012-R00 | 2025-06-01 | Code 2 |  | ATLS-004-ITP-ICT-00003-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00012-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00012-R01 | 2025-06-17 | Code 1
90 | ITP | --- | Communications | Project Submittal | ITP for Installation of Racks & PDU (AR) | LEGRAND | CRFE |  | ATLS-004-ITP-ICT-00010-R00 | 0 | 2025-05-23 | ATV-1300000403-ITP-ICT-00004-R00 | 2025-06-25 | Code 2 | 33 | 33 | ATLS-004-ITP-ICT-00010-R00 | 2025-05-23 | ATV-1300000403-ITP-ICT-00004-R00 | 2025-05-29 | ATV-1300000403-ITP-ICT-00004-R00 | 2025-06-25 | Code 2
91 | ITP | --- | Communications | Project Submittal | ITP for Installation of Floor Trunking and Junction Box For Telecommunication System | SAFELINE | CRFE |  | ATLS-004-ITP-ICT-00004-R01 | 1 | 2025-06-12 | ATV-1300000403-ITP-ICT-00009-R01 | 2025-06-17 | Code 1 | 5 | 5 | ATLS-004-ITP-ICT-00004-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00009-R00 | 2025-05-31 | ATV-1300000403-ITP-ICT-00009-R00 | 2025-06-01 | Code 2 |  | ATLS-004-ITP-ICT-00004-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00009-R01 | 2025-06-12 | ATV-1300000403-ITP-ICT-00009-R01 | 2025-06-17 | Code 1
92 | PQ | --- | General | Project Submittal | Prequalification of Manufacturer For Closed Circuit Television Storage (CCTV Storage) - HUAWEI KSA | HUAWEI | SPECIAL AIRPORT SYSTEM |  | ATLS-004-PQM-ICT-00006-R01 | 1 | 2025-05-01 | ATV-1300000403-PQM-ICT-00009-R00 | 2025-04-28 | UR (DAR) | 95 | 95 | ATLS-004-PQM-ICT-00006-R00 | 2025-04-24 | ATV-1300000403-PQM-ICT-00009-R00 | 2025-04-26 | ATV-1300000403-PQM-ICT-00009-R00 | 2025-04-28 | Code 3 |  | ATLS-004-PQM-ICT-00006-R01 | 2025-05-01 | ATV-1300000403-PQM-ICT-00009-R01 | 2025-07-22 |  |  | UR (DAR)
93 | PQ | --- | General | Project Submittal | Prequalifiction of Manufacturer for NAFCO | NAFFCO | Fire Alarm System, Public Address System, |  | ATLS-004-PQM-ICT-00010-R00 | 0 | 2025-05-28 | ATV-1300000403-PQM-ICT-00012-R00 | 2025-06-01 | Code 3 | 4 | 4 | ATLS-004-PQM-ICT-00010-R00 | 2025-05-28 | ATV-1300000403-PQM-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-PQM-ICT-00012-R00 | 2025-06-01 | Code 3
94 | PQ | --- | General | Project Submittal | Prequalifiction of Manufacturer for Safeline | Safeline | CRFE |  | ATLS-004-PQM-ICT-00011-R00 | 0 | 2025-06-04 | ATV-1300000403-PQM-ICT-00013-R00 | 2025-06-14 | Code 1 | 10 | 10 | ATLS-004-PQM-ICT-00011-R00 | 2025-06-04 | ATV-1300000403-PQM-ICT-00013-R00 | 2025-06-10 | ATV-1300000403-PQM-ICT-00013-R00 | 2025-06-14 | Code 1
95 | MTS | --- | Communications | Project Submittal | Material Submittal for Connectivity Hub for with Mic for recording | ANIXTER | FAS |  | ATLS-004-MTS-ICT-00025-R00 | 0 | 2025-06-02 | ATV-1300000403-MTS-ICT-00026-R00 | 2025-06-11 | Code 2 | 9 | 9 | ATLS-004-MTS-ICT-00025-R00 | 2025-06-02 | ATV-1300000403-MTS-ICT-00026-R00 | 2025-06-04 | ATV-1300000403-MTS-ICT-00026-R00 | 2025-06-11 | Code 2
96 | MST | --- | Communications | Project Submittal | Method Statement for Installation of UPS | LEGRAND | CRFE |  | ATLS-004-MST-ICT-00013-R00 | 0 | 2025-06-11 | ATV-1300000403-MST-ICT-00014-R00 | 2025-07-14 | Code 2 | 33 | 33 | ATLS-004-MST-ICT-00013-R00 | 2025-06-11 | ATV-1300000403-MST-ICT-00014-R00 | 2025-07-13 | ATV-1300000403-MST-ICT-00014-R00 | 2025-07-14 | Code 2
97 | ITP | --- | Communications | Project Submittal | ITP for Installation of UPS | LEGRAND | CRFE |  | ATLS-004-ITP-ICT-00013-R00 | 0 | 2025-06-19 | ATV-1300000403-ITP-ICT-00015-R00 | 2025-06-22 | Code 2 | 3 | 3 | ATLS-004-ITP-ICT-00013-R00 | 2025-06-19 | ATV-1300000403-ITP-ICT-00015-R00 | 2025-06-21 | ATV-1300000403-ITP-ICT-00015-R00 | 2025-06-22 | Code 2
98 | MTS | --- | Communications | Project Submittal | Material Submittal for Conduits & Accessories | SAFELINE |  |  | ATLS-004-MTS-ICT-00028-R00 | 0 | 2025-06-17 | ATV-1300000403-MTS-ICT-00030-R00 | 2025-06-23 | Code 2 | 6 | 6 | ATLS-004-MTS-ICT-00028-R00 | 2025-06-17 | ATV-1300000403-MTS-ICT-00030-R00 | 2025-06-18 | ATV-1300000403-MTS-ICT-00030-R00 | 2025-06-23 | Code 2
99 | MTS | --- | Communications | Project Submittal | Material Submittal Cable Tray Fittings and Accessories |  |  |  | ATLS-004-MTS-ICT-00029-R00 | 0 | 2025-06-18 | ATV-1300000403-MTS-ICT-00031-R00 | 2025-06-22 | Code 2 | 4 | 4 | ATLS-004-MTS-ICT-00029-R00 | 2025-06-18 | ATV-1300000403-MTS-ICT-00031-R00 | 2025-06-21 | ATV-1300000403-MTS-ICT-00031-R00 | 2025-06-22 | Code 2
100 | BL | --- | General | Project Submittal | Baseline Programme |  |  |  | --- |  |  |  |  | --- | --- | ---
101 | PQ | --- | General | Project Submittal | Prequalifiction of Integrated Steel Plant - Wire Basket & Screed Trunking |  |  |  | ATLS-004-PQM-ICT-00012-R01 | 1 | 2025-07-04 | ATV-1300000403-PQM-ICT-00014-R01 | 2025-07-06 | Code 1 | 2 | 2 | ATLS-004-PQM-ICT-00012-R00 | 2025-06-25 | ATV-1300000403-PQM-ICT-00014-R00 | 2025-06-26 | ATV-1300000403-PQM-ICT-00014-R00 | 2025-07-01 | Code 3 |  | ATLS-004-PQM-ICT-00012-R01 | 2025-07-04 | ATV-1300000403-PQM-ICT-00014-R01 | 2025-07-05 | ATV-1300000403-PQM-ICT-00014-R01 | 2025-07-06 | Code 1
102 | MTS | --- | Communications | Project Submittal | Material Submittal TETRA | ANIXTER |  |  | ATLS-004-MTS-ICT-00041-R00 | 0 | 2025-07-27 |  |  | UR (DAR) | 8 | 8 | ATLS-004-MTS-ICT-00041-R00 | 2025-07-27 | ATV-1300000403-MTS-ICT-00046-R00 | 2025-07-29 |  |  | UR (DAR)
103 | MTS | --- | Communications | Project Submittal | Material Submittal GSM |  |  |  | --- |  |  |  |  | --- | --- | ---
104 | MST | --- | Communications | Project Submittal | Method Statement for TETRA | ANIXTER |  |  | --- |  |  |  |  | --- | --- | ---
105 | MST | --- | Communications | Project Submittal | Method Statement for GSM |  |  |  | --- |  |  |  |  | --- | --- | ---
107 | MTS | --- | Communications | Project Submittal | Material Submittal Genetec License |  |  |  | ATLS-004-MTS-ICT-00032-R01 | 1 | 2025-07-22 | ATV-1300000403-MTS-ICT-00037-R01 | 2025-07-31 | Code 3 | 9 | 9 | ATLS-004-MTS-ICT-00032-R00 | 2025-07-07 | ATV-1300000403-MTS-ICT-00037-R00 | 2025-07-08 | ATV-1300000403-MTS-ICT-00037-R00 | 2025-07-13 | Code 2 |  | ATLS-004-MTS-ICT-00032-R01 | 2025-07-22 | ATV-1300000403-MTS-ICT-00037-R01 | 2025-07-23 | ATV-1300000403-MTS-ICT-00037-R01 | 2025-07-31 | Code 3
108 | MTS | --- | Communications | Project Submittal | Material Submittal for Border Control Systems - Vision Box | SITA |  |  | ATLS-004-MTS-ICT-00034-R00 | 0 | 2025-07-08 | ATV-1300000403-MTS-ICT-00038-R00 | 2025-07-13 | Code 2 | 5 | 5 | ATLS-004-MTS-ICT-00034-R00 | 2025-07-08 | ATV-1300000403-MTS-ICT-00038-R00 | 2025-07-08 | ATV-1300000403-MTS-ICT-00038-R00 | 2025-07-13 | Code 2
109 | MTS | --- | Communications | Project Submittal | Material Submittal for Disabled Toilet Alarm System | HONEYWELL |  |  | ATLS-004-MTS-ICT-00036-R00 | 0 | 2025-07-08 | ATV-1300000403-MTS-ICT-00040-R00 | 2025-07-21 | Code 2 | 13 | 13 | ATLS-004-MTS-ICT-00036-R00 | 2025-07-08 | ATV-1300000403-MTS-ICT-00040-R00 | 2025-07-09 | ATV-1300000403-MTS-ICT-00040-R00 | 2025-07-21 | Code 2
110 | MTS | --- | Communications | Project Submittal | Material Submittal for Closed Circuit Television System - Volume 1 | ANIXTER |  |  | ATLS-004-MTS-ICT-00037-R01 | 1 | 2025-07-31 | ATV-1300000403-MTS-ICT-00041-R00 | 2025-07-21 | UR (DAR) | 4 | 4 | ATLS-004-MTS-ICT-00037-R00 | 2025-07-09 | ATV-1300000403-MTS-ICT-00041-R00 | 2025-07-10 | ATV-1300000403-MTS-ICT-00041-R00 | 2025-07-21 | Code 2 |  | ATLS-004-MTS-ICT-00037-R01 | 2025-07-31 | ATV-1300000403-MTS-ICT-00041-R01 | 2025-08-02 |  |  | UR (DAR)
111 | MTS | --- | Communications | Project Submittal | Material Submittal for Conduits & Accessories (SESCO) | SESCO |  |  | ATLS-004-MTS-ICT-00038-R00 | 0 | 2025-07-09 | ATV-1300000403-MTS-ICT-00042-R00 | 2025-07-21 | Code 2 | 12 | 12 | ATLS-004-MTS-ICT-00038-R00 | 2025-07-09 | ATV-1300000403-MTS-ICT-00042-R00 | 2025-07-16 | ATV-1300000403-MTS-ICT-00042-R00 | 2025-07-21 | Code 2
112 | MST | --- | Communications | Project Submittal | Method Statement for Embedded Raceways (PVC Conduit System) |  |  |  | ATLS-004-MST-ICT-00017-R00 | 0 | 2025-07-14 | ATV-1300000403-MST-ICT-00016-R00 | 2025-07-17 | Code 2 | 3 | 3 | ATLS-004-MST-ICT-00017-R00 | 2025-07-14 | ATV-1300000403-MST-ICT-00016-R00 | 2025-07-16 | ATV-1300000403-MST-ICT-00016-R00 | 2025-07-17 | Code 2
113 | MTS | --- | Communications | Project Submittal | Material Submittal for Public Address System (Honeywell) | Honeywell |  |  | ATLS-004-MST-ICT-00039-R00 | 0 | 2025-07-28 |  |  | UR (DAR) | 7 | 7 | ATLS-004-MST-ICT-00039-R00 | 2025-07-28 | ATV-1300000403-MTS-ICT-00045-R00 | 2025-07-29 |  |  | UR (DAR)
114 | MTS | --- | Communications | Project Submittal | Material Submittal for Screed Trunking & Basket Tray (ISP) | ISP |  |  | ATLS-004-MST-ICT-00040-R00 | 0 | 2025-07-21 | ATV-1300000403-MTS-ICT-00043-R00 | 2025-07-27 | Code 2 | 6 | 6 | ATLS-004-MST-ICT-00040-R00 | 2025-07-21 | ATV-1300000403-MTS-ICT-00043-R00 | 2025-07-23 | ATV-1300000403-MTS-ICT-00043-R00 | 2025-07-27 | Code 2
115 | MTS | --- | Communications | Project Submittal | Material Submittal for Fire Alarm Cable |  |  |  | ATLS-004-MST-ICT-00042-R00 | 0 | 2025-08-04 |  |  | UR (ATJV) | 0 | 0 | ATLS-004-MST-ICT-00042-R00 | 2025-08-04 |  |  |  |  | UR (ATJV)

## Dashboard
Document - Register
South Terminal Rehabilitation General Works Package Project Jeddah Airport
|  |  | TOTAL | SUBMITTED |  | Code 1 | Code 2 | ADAVANCE REVIEW | RETURN TO ATLAS BY ATJV | OFFICIAL SUBMISSION UR (ATJV) | UNDER REVIEW WITH DAR | Code 3 | Code 4 | REV 0 TO SUBMIT
|  |  | 111 | 85 | 76.58% | 36 | 33 | 0 | 0 | 4 | 9 | 3 | 0 | 25
PQ | PROJECT DELIVERABLES | PREQUALIFICATION | 12 | 12 | 100% | 6 | 2 | 0 | 0 | 0 | 3 | 1 | 0 | 0
BL |  | BASELINE PROGRAMME | 1 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MTS |  | MATERIAL SUBMITTAL | 39 | 38 | 97.44% | 16 | 15 | 0 | 0 | 1 | 4 | 2 | 0 | 1
MST |  | INSTALLATION MOS | 22 | 17 | 77.27% | 5 | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 5
ITP |  | INSPECTION & TEST PLAN | 19 | 18 | 94.74% | 9 | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 1
SDD |  | SYSTEM DESIGN DOCUMENT | 3 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
ICD |  | INTERFACE CONTROL DOCUMENT | 3 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
TCD |  | TESTING AND COMMISSIONING DOCUMENT | 3 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OMM | Close Out | OPERATION & MAINTENANCE MANUAL | 3 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
OTM |  | OPERATION TRAINING MANUAL | 3 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Warranty |  | WARRANTY SUBMITAL | 3 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 76.58% |  | 42.35% | 38.82% | 0% | 0% | 4.706% | 10.59% | 3.529% | 0% | 22.52%