## ATLAS SD-LOG
| Project Name | South Terminal Rehabilitation General Works Package Project Jeddah Airport
Contract No
| Sub Contractor | ATLAS SECURITY
| Clinet | JEDCO
| Contractor | AT-JV | [13 empty] | 2025-08-05 | CURRENT STATUS OF THE DRAWING | [7 empty] | REV 00 SUBMISSION DETAILS |  |  |  |  | STATUS DETAILS |  |  | REV 01 SUBMISSION DETAILS |  |  |  |  | STATUS DETAILS |  |  | REV 02 SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | REV 03 SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | REV 04 SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | REV 05 SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | REV 06 SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | REV 07 SUBMISSION DETAILS |  |  | STATUS DETAILS
SN | System | Sub-System | Project Number | Main Contrator or Sub Contractor Initial | Buildning Name | Floor Level | Drawing Zone | Disipline | Sub-Disipline | Drawing Stage | Drawing Sequence | Drawing Number | N | FORECAST DATE | REVIEW TIME (DAYS) | REVIEW TIME OVERDUE DAYS | REVISION | SUBMISSION DTAE | TRANSMITTAL NUMBER | LATEST STATUS | ENGINEER COMMENT DATE | ENGINEER TRANSMITTAL NUMBER | CURRENT STATUS | REJECTED BY | ATLAS SUB REFERENCE | ATLAS DATE SUBMITTED | ATJV REFERENCE # | ATJV DATE SUBMITTED | REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | SUB REFERENCE | ATLAS DATE SUBMITTED | ATJV REFERENCE | ATJV SUBMISSION DATE | DAR REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | SUB REFERENCE | DATE SUBMITTED | REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | SUB REFERENCE | DATE SUBMITTED | REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | SUB REFERENCE | DATE SUBMITTED | REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | SUB REFERENCE | DATE SUBMITTED | REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | SUB REFERENCE | DATE SUBMITTED | REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | SUB REFERENCE | DATE SUBMITTED | REPLY REFERENCE | AT-JV COMMENT | DATE | CSC COMMENT | Category | Descripencies
SN | SYSTEM | SUB_SYSTEM | PROJECT_NO | Sub Con | BUILDING_NO | FLOOR_LEVEL | DRAWING_PARTS | DISIPLINE | Sub-Dec | DS | DRAWING_SEQ | DRAWING_NUMBER | DRAWING_DESCRIPTION | 21 | REV_TIME | REV_OD | 25 | ALTAS_LATEST_SUB_DATE | ATLAS_SUBMISSION | LATEST_STATUS | DAR_RESPONSE_DATE | DAR_REFERENCE_NUMBER | FINAL_STATUS | REJECT_BY | AREF_0 | ASUB_0 | ASUB_02 | ASUB_03 | JVREF_0 | JVC_0 | JVCD_0 | CMAC_0 | AREF_1 | ASUB_1 | JVREF_1 | JVREF_14 | JVREF_13 | JVC_1 | JVCD_1 | CMAC_1 | AREF_2 | ASUB_2 | JVREF_2 | JVC_2 | JVCD_2 | CMAC_2 | AREF_3 | ASUB_3 | JVREF_3 | JVC_3 | JVCD_3 | CMAC_3 | AREF_4 | ASUB_4 | JVREF_4 | JVC_4 | JVCD_4 | CMAC_4 | AREF_5 | ASUB_5 | JVREF_5 | JVC_5 | JVCD_5 | CMAC_5 | AREF_6 | ASUB_6 | JVREF_6 | JVC_6 | JVCD_6 | CMAC_6 | AREF_7 | ASUB_7 | JVREF_7 | JVC_7 | JVCD_7 | CMAC_7 | CATE | Descripencies
1 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-05-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-05 (AR) | 2025-05-12 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
2 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-06-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-06 (AR) | 2025-05-12 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
3 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-09-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-09 | 2025-05-12 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
4 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-10-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-10 | 2025-05-12 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
5 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-00-ICT-CNT-SD-00 | Terminal Basement Contaiment Overall Plan | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
6 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-01-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-01 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
7 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-02-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-02 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
8 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-03-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-03 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
9 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-04-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-04 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
10 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-05-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-05 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
11 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-06-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-06 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
12 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-07-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-07 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
13 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-08-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-08 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
14 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-09-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-09 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
15 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-10-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-10 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
16 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-11-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-11 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
17 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | CNT | SD | 00 | 1300403-ATS-B01-BF-12-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-12 | 2025-05-16 | 3 | --- | 00 | 2025-05-17 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
18 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-13-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-13 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00003-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 |  | ATLS-004-SD-ICT-00003-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
19 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-14-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-14 (AR) | 2025-05-12 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00003-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 |  | ATLS-004-SD-ICT-00003-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
20 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-15-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-15 (AR) | 2025-05-12 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00003-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 |  | ATLS-004-SD-ICT-00003-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
21 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-00-ICT-CNT-SD-00 | First Floor Contaiment Overall Plan (Departure Level) | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
22 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-01-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-01 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
23 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-02-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-02 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
24 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-03-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-03 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
25 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-04-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-04 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
26 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-05-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-05 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
27 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-06-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-06 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
28 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-07-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-07 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
29 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-08-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-08 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
30 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-09-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-09 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
31 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-10-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-10 | 2025-05-12 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
32 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-11-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-11 | 2025-05-12 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
33 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-12-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-12 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
34 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-13-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-13 | 2025-05-16 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
35 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-14-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-14 | 2025-05-12 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
36 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | CNT | SD | 00 | 1300403-ATS-B01-FF-15-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-15 | 2025-05-12 | 1 | --- | 00 | 2025-05-19 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 20 May 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
37 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-01-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-01 | 2025-05-16 | 6 | --- | 00 | 2025-05-20 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
38 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-02-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-02 | 2025-05-16 | 6 | --- | 00 | 2025-05-20 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
39 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-03-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-03 | 2025-05-16 | 6 | --- | 00 | 2025-05-20 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
40 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-04-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-04 | 2025-05-16 | 6 | --- | 00 | 2025-05-20 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
41 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-08-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-08 | 2025-05-16 | 6 | --- | 00 | 2025-05-20 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
42 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-12-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-12 | 2025-05-16 | 6 | --- | 00 | 2025-05-20 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
43 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-00-ICT-CNT-SD-00 | Ground Floor Contaiment Overall Plan (Arrival Level) | 2025-05-16 | 4 | --- | 00 | 2025-05-22 | ATLS-004-SD-ICT-00007-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00006-R00 | Code 2 |  | ATLS-004-SD-ICT-00007-R00 | 2025-05-22 | ATV-1300000403-SDS-ICT-00006-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00006-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
44 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-07-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-07 | 2025-05-16 | 4 | --- | 00 | 2025-05-22 | ATLS-004-SD-ICT-00007-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00006-R00 | Code 2 |  | ATLS-004-SD-ICT-00007-R00 | 2025-05-22 | ATV-1300000403-SDS-ICT-00006-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00006-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
45 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | CNT | SD | 00 | 1300403-ATS-B01-GF-11-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-11 | 2025-05-16 | 4 | --- | 00 | 2025-05-22 | ATLS-004-SD-ICT-00007-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00006-R00 | Code 2 |  | ATLS-004-SD-ICT-00007-R00 | 2025-05-22 | ATV-1300000403-SDS-ICT-00006-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00006-R00 | Code 2 | 26 may 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
46 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Overall Plan | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
47 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-01 |  | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
48 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-02 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
49 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-03 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
50 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-04 |  | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
51 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-05 |  | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
52 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-06 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
53 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-07 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
54 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-08 |  | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
55 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-09 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
56 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-10 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
57 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-11 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
58 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-12 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
59 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-13-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-13 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
60 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-14-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-14 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
61 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | CNT | SD | 00 | 1300403-ATS-B01-MZ-15-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-15 | 2025-05-22 | 2 | --- | 00 | 2025-05-27 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 29 May 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
62 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B02-GF-00-ICT-CNT-SD-00 | Ground Floor Contaiment Overall Plan | 2025-05-25 | 1 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00009-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 |  | ATLS-004-SD-ICT-00009-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
63 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B02-GF-01-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part 01 | 2025-05-25 | 1 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00009-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 |  | ATLS-004-SD-ICT-00009-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
64 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B02-GF-02-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part 02 | 2025-05-25 | 1 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00009-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 |  | ATLS-004-SD-ICT-00009-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
65 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B02-GF-03-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part 03 | 2025-05-25 | 1 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00009-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 |  | ATLS-004-SD-ICT-00009-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00041-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
66 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B04-LF-00-ICT-CNT-SD-00 | Lower Floor Overall Level Contaiment Plan | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
67 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B04-LF-01-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 01 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
68 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B04-LF-02-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 02 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
69 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B04-LF-03-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 03 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
70 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 04 | ICT | CNT | SD | 00 | 1300403-ATS-B04-LF-04-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 04 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
71 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B04-UF-00-ICT-CNT-SD-00 | Upper Floor Overall Level Contaiment Plan | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
72 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B04-UF-01-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 01 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
73 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B04-UF-02-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 02 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
74 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B04-UF-03-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 03 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
75 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 04 | ICT | CNT | SD | 00 | 1300403-ATS-B04-UF-04-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 04 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00019-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 |  | ATLS-004-SD-ICT-00019-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00057-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
76 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-00-ICT-MCK-SD-00 | Ground Floor Master Clock Overall System Plan (Arrival Level) | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
77 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-01-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-01 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
78 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-02-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-02 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
79 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-03-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-03 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
80 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-04-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-04 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
81 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-05-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-05 | 2025-05-22 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
82 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-06-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-06 | 2025-05-22 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
83 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-07-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-07 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
84 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-08-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-08 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
85 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-09-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-09 | 2025-05-22 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
86 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-10-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-10 | 2025-05-22 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
87 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-11-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-11 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
88 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-12-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-12 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
89 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-13-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-13 | 2025-06-02 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
90 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-14-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-14 | 2025-05-22 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
91 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | MCK | SD | 00 | 1300403-ATS-B01-GF-15-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-15 | 2025-05-22 | 4 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
92 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-00-ICT-MCK-SD-00 | First Floor Master Clock Overall System Plan (Departure Level) | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
93 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-01-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-01 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
94 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-02-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-02 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
95 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-03-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-03 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
96 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-04-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-04 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
97 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-05-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-05 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
98 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-06-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-06 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
99 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-07-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-07 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
100 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-08-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-08 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
101 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-09-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-09 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
102 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-10-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-10 | 2025-05-22 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
103 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-11-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-11 | 2025-05-22 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
104 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-12-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-12 | 2025-06-02 | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
105 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-13-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-13 |  | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
106 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-14-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-14 |  | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
107 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | MCK | SD | 00 | 1300403-ATS-B01-FF-15-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-15 |  | 6 | --- | 00 | 2025-05-28 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 03 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
108 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B07 | GF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B07-GF-00-ICT-VSS-SD-00 | Ground Floor Ip Cctv Systems Plan | 2025-05-30 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00016-R00 | Code 2 | 01 Jun 25 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 |  | ATLS-004-SD-ICT-00016-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00011-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 | 01 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
109 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B06 | GF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B06-GF-00-ICT-VSS-SD-00 | Ground Floor Ip Cctv System Plan | 2025-07-30 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00016-R00 | Code 2 | 01 Jun 25 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 |  | ATLS-004-SD-ICT-00016-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00011-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 | 01 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
110 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B05-LF-00-ICT-CNT-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Overall Contaiment Plan | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00023-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 |  | ATLS-004-SD-ICT-00023-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
111 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B05-LF-01-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-01 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00023-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 |  | ATLS-004-SD-ICT-00023-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
112 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B05-LF-02-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-02 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00023-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 |  | ATLS-004-SD-ICT-00023-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
113 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B05-LF-03-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-03 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00023-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 |  | ATLS-004-SD-ICT-00023-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
114 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 04 | ICT | CNT | SD | 00 | 1300403-ATS-B05-LF-04-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-04 | 2025-07-10 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00023-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 |  | ATLS-004-SD-ICT-00023-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00055-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
115 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-00-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock Overall System Plan | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
116 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-01-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-01 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
117 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-02-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-02 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
118 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-03-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-03 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
119 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-04-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-04 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
120 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-05-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-05 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
121 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-06-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-06 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
122 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-07-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-07 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
123 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-08-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-08 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
124 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-09-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-09 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
125 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-10-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-10 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
126 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-11-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-11 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
127 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | MCK | SD | 00 | 1300403-ATS-B01-BF-12-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-12 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 01 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
128 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-MCK-SD-00 | Mezzanine Floor Master Clock Overall System Plan | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
129 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-01 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
130 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-02 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
131 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-03 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
132 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-04 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
133 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-05 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
134 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-06 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
135 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-07 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
136 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-08 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
137 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-09 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
138 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-10 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
139 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-11 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
140 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-12 | 2025-06-02 | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
141 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-13-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-13 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
142 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-14-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-14 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
143 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | MCK | SD | 00 | 1300403-ATS-B01-MZ-15-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-15 |  | 3 | --- | 00 | 2025-05-29 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 1 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
144 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B05-LF-00-ICT-VSS-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan | 2025-05-30 | -142 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00025-R00 | Code 2 | 3/8/2025 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 |  | ATLS-004-SD-ICT-00025-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 | 3/8/2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
145 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B05-LF-01-ICT-VSS-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 01 | 2025-05-30 | -142 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00025-R00 | Code 2 | 3/8/2025 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 |  | ATLS-004-SD-ICT-00025-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 | 3/8/2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
146 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B05-LF-02-ICT-VSS-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 02 | 2025-05-30 | -142 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00025-R00 | Code 2 | 3/8/2025 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 |  | ATLS-004-SD-ICT-00025-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 | 3/8/2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
147 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B05-LF-03-ICT-VSS-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 03 | 2025-05-30 | -142 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00025-R00 | Code 2 | 3/8/2025 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 |  | ATLS-004-SD-ICT-00025-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 | 3/8/2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
148 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 04 | ICT | VSS | SD | 00 | 1300403-ATS-B05-LF-04-ICT-VSS-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 04 | 2025-05-30 | -142 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00025-R00 | Code 2 | 3/8/2025 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 |  | ATLS-004-SD-ICT-00025-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00079-R00 | Code 2 | 3/8/2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
149 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | MCK | SD | 00 | 1300403-ATS-B02-FF-00-ICT-MCK-SD-00 | First Floor Master Clock System Overall Plan | 2025-06-02 | 7 | --- | 00 | 2025-05-30 | ATLS-004-SD-ICT-00027-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
150 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | MCK | SD | 00 | 1300403-ATS-B02-FF-01-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part 01 | 2025-06-02 | 7 | --- | 00 | 2025-05-30 | ATLS-004-SD-ICT-00027-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
151 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | MCK | SD | 00 | 1300403-ATS-B02-FF-02-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part 02 | 2025-06-02 | 7 | --- | 00 | 2025-05-30 | ATLS-004-SD-ICT-00027-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
152 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | MCK | SD | 00 | 1300403-ATS-B02-FF-03-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part 03 | 2025-06-02 | 7 | --- | 00 | 2025-05-30 | ATLS-004-SD-ICT-00027-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00023-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
153 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B06 | m | 00 | ICT | MCK | SD | 00 | 1300403-ATS-B06-m -00-ICT-MCK-SD-00 | Ground Floor Ip Master Clock System Plan | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00030-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00024-R00 | Code 2 |  | ATLS-004-SD-ICT-00030-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00024-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
154 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | MCK | SD | 00 | 1300403-ATS-B02-GF-00-ICT-MCK-SD-00 | Ground Floor Master Clock System Overall Plan | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00026-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
155 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | MCK | SD | 00 | 1300403-ATS-B02-GF-01-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part 01 | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00026-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
156 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | MCK | SD | 00 | 1300403-ATS-B02-GF-02-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part 02 | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00026-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
157 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | MCK | SD | 00 | 1300403-ATS-B02-GF-03-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part 03 | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00026-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
158 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-00-ICT-IPT-SD-00 | Ground Floor Iptv System Overall Plan (Arrival Level) | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
159 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-01-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 01 | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
160 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-02-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 02 | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
161 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-03-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 03 | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
162 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-04-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 04 |  | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
163 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-05-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 05 | 2025-05-25 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
164 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-06-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 06 | 2025-05-25 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
165 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-07-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 07 | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
166 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-08-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 08 |  | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
167 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-09-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 09 | 2025-05-25 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
168 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-10-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 10 | 2025-05-25 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
169 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-11-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 11 | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
170 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-12-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 12 | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
171 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-13-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 13 | 2025-06-02 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
172 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-14-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 14 | 2025-05-25 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
173 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | IPT | SD | 00 | 1300403-ATS-B01-GF-15-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 15 | 2025-05-25 | 3 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00032-R00 | Code 2 | 5 Jun 25 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | Code 2 | 5 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
174 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-00-ICT-IPT-SD-00 | First Floor Iptv System Overall Plan (Departure Level) | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
175 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-01-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 01 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
176 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-02-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 02 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
177 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-03-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 03 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
178 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-04-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 04 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
179 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-05-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 05 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
180 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-06-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 06 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
181 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-07-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 07 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
182 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-08-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 08 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
183 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-09-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 09 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
184 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-10-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 10 | 2025-05-25 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
185 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-11-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 11 | 2025-05-25 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
186 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-12-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 12 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
187 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-13-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 13 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
188 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-14-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 14 | 2025-05-25 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
189 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | IPT | SD | 00 | 1300403-ATS-B01-FF-15-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 15 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00031-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
190 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Overall Plan | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
191 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 01 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
192 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 02 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
193 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 03 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
194 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 04 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
195 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 05 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
196 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 06 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
197 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 07 | 2025-06-02 | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
198 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 08 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
199 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 09 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
200 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 10 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
201 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 11 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
202 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 12 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
203 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-13-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 13 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
204 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-14-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 14 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
205 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | IPT | SD | 00 | 1300403-ATS-B01-MZ-15-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 15 |  | 2 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00034-R00 | Code 2 | 04 Jun 25 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | Code 2 | 04 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
206 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | IPT | SD | 00 | 1300403-ATS-B02-GF-00-ICT-IPT-SD-00 | Ground Floor Iptv System Overall Plan | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
207 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | IPT | SD | 00 | 1300403-ATS-B02-GF-01-ICT-IPT-SD-00 | Ground Floor Iptv System Plan Part 01 | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
208 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | IPT | SD | 00 | 1300403-ATS-B02-GF-02-ICT-IPT-SD-00 | Ground Floor Iptv System Plan Part 02 | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
209 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | IPT | SD | 00 | 1300403-ATS-B02-GF-03-ICT-IPT-SD-00 | Ground Floor Iptv System Plan Part 03 | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
210 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | IPT | SD | 00 | 1300403-ATS-B02-FF-00-ICT-IPT-SD-00 | First Floor Iptv System Overall Plan | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
211 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | IPT | SD | 00 | 1300403-ATS-B02-FF-01-ICT-IPT-SD-00 | First Floor Iptv System Plan Part 01 | 2025-06-02 | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
212 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | IPT | SD | 00 | 1300403-ATS-B02-FF-02-ICT-IPT-SD-00 | First Floor Iptv System Plan Part 02 |  | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
213 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | IPT | SD | 00 | 1300403-ATS-B02-FF-03-ICT-IPT-SD-00 | First Floor Iptv System Plan Part 03 |  | 4 | --- | 00 | 2025-06-02 | ATLS-004-SD-ICT-00033-R00 | Code 2 | 06 Jun 25 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | Code 2 | 06 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
214 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 01 | 1300403-ATS-00-00-00-ICT-TYP-SD-01 | ACCESS CONTROL AC1 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
215 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 02 | 1300403-ATS-00-00-00-ICT-TYP-SD-02 | ACCESS CONTROL AC2 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
216 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 03 | 1300403-ATS-00-00-00-ICT-TYP-SD-03 | ACCESS CONTROL AC3 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
217 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 04 | 1300403-ATS-00-00-00-ICT-TYP-SD-04 | ACCESS CONTROL AC4 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
218 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 05 | 1300403-ATS-00-00-00-ICT-TYP-SD-05 | ACCESS CONTROL AC5 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
219 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 06 | 1300403-ATS-00-00-00-ICT-TYP-SD-06 | ACCESS CONTROL AC6 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
220 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 07 | 1300403-ATS-00-00-00-ICT-TYP-SD-07 | ACCESS CONTROL AC7 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
221 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 08 | 1300403-ATS-00-00-00-ICT-TYP-SD-08 | ACCESS CONTROL AC8 SLIDING DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
222 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 09 | 1300403-ATS-00-00-00-ICT-TYP-SD-09 | ACCESS CONTROL AC9 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
223 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 10 | 1300403-ATS-00-00-00-ICT-TYP-SD-10 | ACCESS CONTROL AC10 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
224 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 11 | 1300403-ATS-00-00-00-ICT-TYP-SD-11 | ACCESS CONTROL AC11 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
225 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 12 | 1300403-ATS-00-00-00-ICT-TYP-SD-12 | ACCESS CONTROL AC12 SHUTTER INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
226 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 13 | 1300403-ATS-00-00-00-ICT-TYP-SD-13 | ACCESS CONTROL AC13 ELEVATOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00024-R01 | UR (DAR) | 12 Jun 25 | ATV-1300000403-SDS-ICT-00025-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 | ATV-1300000403-SDS-ICT-00025-R00 | Code 2 | 12 Jun 25 | Code 2 | ATLS-004-SD-ICT-00024-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00025-R01 | 2025-07-30 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
227 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B05-LF-00-ICT-ACS-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Access Control System Plan |  | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00014-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00016-R01 | Code 2 |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00016-R01 |  |  | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
228 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B05-LF-01-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-01 |  | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00014-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00016-R01 | Code 2 |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00016-R01 |  |  | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
229 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B05-LF-02-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-02 |  | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00014-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00016-R01 | Code 2 |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00016-R01 |  |  | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
230 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B05-LF-03-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-03 |  | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00014-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00016-R01 | Code 2 |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00016-R01 |  |  | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
231 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 04 | ICT | ACS | SD | 00 | 1300403-ATS-B05-LF-04-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-04 |  | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00014-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00016-R01 | Code 2 |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00016-R01 |  |  | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
232 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B04-LF-00-ICT-ACS-SD-00 | Lower Floor Overall Level Access Control System Plan | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
233 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B04-LF-01-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 01 | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
234 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B04-LF-02-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 02 | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
235 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B04-LF-03-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 03 | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
236 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 04 | ICT | ACS | SD | 00 | 1300403-ATS-B04-LF-04-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 04 | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
237 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B04-UF-00-ICT-ACS-SD-00 | Upper Floor Overall Level Access Control System Plan | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
238 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B04-UF-01-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 01 |  | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
239 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B04-UF-02-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 02 | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
240 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B04-UF-03-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 03 | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
241 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 04 | ICT | ACS | SD | 00 | 1300403-ATS-B04-UF-04-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 04 | 2025-05-26 | 8 | --- | 01 | 2025-06-03 | ATLS-004-SD-ICT-00028-R01 | Code 2 | 2025-06-11 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 02 Jun 25 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 | ATV-1300000403-SDS-ICT-00017-R01 | 2025-06-04 | ATV-1300000403-SDS-ICT-00017-R01 | Code 2 | 2025-06-11 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
242 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | CNT | SD | 00 | 1300403-ATS-B02-FF-00-ICT-CNT-SD-00 | First Floor Contaiment Overall Plan | 2025-05-25 | 8 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00010-R00 | Code 2 | 12 Jun 25 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00027-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 | 12 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
243 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B02-FF-01-ICT-CNT-SD-00 | First Floor Contaiment Plan Part 01 | 2025-05-25 | 8 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00010-R00 | Code 2 | 12 Jun 25 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00027-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 | 12 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
244 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B02-FF-02-ICT-CNT-SD-00 | First Floor Contaiment Plan Part 02 | 2025-05-25 | 8 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00010-R00 | Code 2 | 12 Jun 25 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00027-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 | 12 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
245 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | CNT | SD | 00 | 1300403-ATS-B02-FF-03-ICT-CNT-SD-00 | First Floor Contaiment Plan Part 03 | 2025-05-25 | 8 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00010-R00 | Code 2 | 12 Jun 25 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00027-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00027-R00 | Code 2 | 12 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
246 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-00-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment Overall System Plan | 2025-06-11 | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
247 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-01-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-01 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
248 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-02-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-02 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
249 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-03-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-03 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
250 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-04-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-04 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
251 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-05-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-05 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
252 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-06-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-06 | 2025-06-11 | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
253 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-07-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-07 | 2025-06-11 | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
254 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-08-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-08 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
255 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-09-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-09 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
256 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-10-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-10 | 2025-06-11 | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
257 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-11-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-11 | 2025-06-11 | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
258 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | COM | SD | 00 | 1300403-ATS-B01-BF-12-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-12 |  | 9 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00036-R00 | Code 2 | 13 Jun 25 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00029-R00 | Code 2 | 13 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
259 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-00-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment Overall System Plan (Departure Level) | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
260 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-01-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-01 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
261 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-02-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-02 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
262 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-03-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-03 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
263 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-04-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-04 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
264 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-05-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-05 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
265 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-06-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-06 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
266 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-07-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-07 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
267 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-08-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-08 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
268 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-09-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-09 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
269 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-10-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-10 | 2025-05-18 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
270 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-11-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-11 | 2025-05-18 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
271 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-12-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-12 | 2025-06-11 | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
272 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-13-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-13 |  | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
273 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-14-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-14 |  | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
274 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | COM | SD | 00 | 1300403-ATS-B01-FF-15-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-15 |  | 10 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00037-R00 | Code 2 | 14 Jun 25 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00028-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00028-R00 | Code 2 | 14 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
275 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-00-ICT-TEL-SD-00 | Terminal Basement IP Telephony Overall System Plan | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
276 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-02-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-02 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
277 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-03-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-03 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
278 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-04-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-04 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
279 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-05-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-05 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
280 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-06-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-06 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
281 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-07-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-07 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
282 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-08-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-08 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
283 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-10-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-10 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
284 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-11-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-11 | 2025-06-16 | 11 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00008-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00031-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00031-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
285 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony Overall System Plan | 2025-06-16 | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
286 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-01 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
287 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-02 | 2025-06-16 | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
288 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-03 | 2025-06-16 | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
289 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-04 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
290 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-05 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
291 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-06 | 2025-06-16 | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
292 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-07 | 2025-06-16 | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
293 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-08 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
294 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-09 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
295 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-10 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
296 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-11 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
297 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | TEL | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-12 |  | 12 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00018-R00 | Code 2 | 16 Jun 25 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 |  | ATLS-004-SD-ICT-00018-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00026-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00026-R00 | Code 2 | 16 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
298 | ICT | IPTV SYSTEM | 1300403 | ATS | B06 | 00 | 00 | ICT | IPT | SD | 00 | 1300403-ATS-B06-00-00-ICT-IPT-SD-00 | Ground Floor Iptv System Plan | 2025-06-02 | 8 | --- | 00 | 2025-06-04 | ATLS-004-SD-ICT-00035-R00 | Code 2 | 12 jun 25 | ATV-1300000403-SDS-ICT-00030-R00 | Code 2 |  | ATLS-004-SD-ICT-00035-R00 | 2025-06-04 | ATV-1300000403-SDS-ICT-00030-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00030-R00 | Code 2 | 12 jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
299 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B03-BF-00-ICT-ACS-SD-00 | Basement Access Control System Plan | 2025-05-26 | 1 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00029-R00 | Code 2 | 10 Jun 25 | ATV-1300000403-SDS-ICT-00032-R00 | Code 2 |  | ATLS-004-SD-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00032-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00032-R00 | Code 2 | 10 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
300 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B03 | GF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B03-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Plan | 2025-05-26 | 1 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00029-R00 | Code 2 | 10 Jun 25 | ATV-1300000403-SDS-ICT-00032-R00 | Code 2 |  | ATLS-004-SD-ICT-00029-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00032-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00032-R00 | Code 2 | 10 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
301 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-00-ICT-DAT-SD-00 | Terminal Basement Data Network Overall System Plan | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
302 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-02-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-02 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
303 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-03-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-03 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
304 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-04-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-04 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
305 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-05-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-05 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
306 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-06-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-06 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
307 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-07-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-07 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
308 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-08-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-08 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
309 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-10-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-10 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
310 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-11-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-11 | 2025-05-18 | 8 | --- | 00 | 2025-06-09 | ATLS-004-SD-ICT-00017-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 |  | ATLS-004-SD-ICT-00017-R00 | 2025-06-09 | ATV-1300000403-SDS-ICT-00033-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00033-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
311 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B07 | GF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B07-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan |  | 2 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00045-R00 | Code 2 | 25 Jun 25 | ATV-1300000403-SDS-ICT-00047-R00 | Code 2 |  | ATLS-004-SD-ICT-00045-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00047-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00047-R00 | Code 2 | 25 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
312 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B06 | GF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B06-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan |  | 2 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00044-R00 | Code 2 | 25 Jun 25 | ATV-1300000403-SDS-ICT-00046-R00 | Code 2 |  | ATLS-004-SD-ICT-00044-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00046-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00046-R00 | Code 2 | 25 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
313 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B04-LF-00-ICT-COM-SD-00 | Lower Level Floor Overall Communication Equipment Plan | 2025-06-11 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
314 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B04-LF-01-ICT-COM-SD-00 | Lower Level Floor Communication Equipment Plan Part 01 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
315 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B04-LF-02-ICT-COM-SD-00 | Lower Level Floor Communication Equipment Plan Part 02 | 2025-06-11 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
316 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B04-LF-03-ICT-COM-SD-00 | Lower Level Floor Communication Equipment Plan Part 03 | 2025-06-11 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
317 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 04 | ICT | COM | SD | 00 | 1300403-ATS-B04-LF-04-ICT-COM-SD-00 | Lower Level Floor Communication Equipment Plan Part 04 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
318 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B04-UF-00-ICT-COM-SD-00 | Upper Level Floor Overall Communication Equipment Plan | 2025-06-11 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
319 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B04-UF-01-ICT-COM-SD-00 | Upper Level Floor Communication Equipment Plan Part 01 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
320 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B04-UF-02-ICT-COM-SD-00 | Upper Level Floor Communication Equipment Plan Part 02 | 2025-06-11 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
321 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B04-UF-03-ICT-COM-SD-00 | Upper Level Floor Communication Equipment Plan Part 03 | 2025-06-11 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
322 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 04 | ICT | COM | SD | 00 | 1300403-ATS-B04-UF-04-ICT-COM-SD-00 | Upper Level Floor Communication Equipment Plan Part 04 | 2025-06-11 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00042-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00042-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
323 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Overall Equipment Plan | 2025-06-11 | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
324 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-01 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
325 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-02 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
326 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-03 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
327 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-04 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
328 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-05 | 2025-06-11 | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
329 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-06 | 2025-06-11 | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
330 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-07 | 2025-06-11 | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
331 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-08 | 2025-06-11 | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
332 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-09 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
333 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-10 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
334 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-11 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
335 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | COM | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-12 |  | 5 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00038-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 |  | ATLS-004-SD-ICT-00038-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00034-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
336 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephony Overall System Plan (Arrival Level) | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
337 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-01-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-01 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
338 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-02-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-02 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
339 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-03-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-03 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
340 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-04-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-04 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
341 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-05-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-05 | 2025-05-24 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
342 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-06-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-06 | 2025-05-24 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
343 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-07-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-07 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
344 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-08-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-08 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
345 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-09-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-09 | 2025-05-24 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
346 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-10-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-10 | 2025-05-24 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
347 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-11-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-11 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
348 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-12-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-12 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
349 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-13-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-13 | 2025-06-16 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
350 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-14-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-14 | 2025-05-24 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
351 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | TEL | SD | 00 | 1300403-ATS-B01-GF-15-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-15 | 2025-05-24 | 9 | --- | 00 | 2025-06-10 | ATLS-004-SD-ICT-00046-R00 | Code 2 | 19 Jun 25 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 |  | ATLS-004-SD-ICT-00046-R00 | 2025-06-10 | ATV-1300000403-SDS-ICT-00036-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00036-R00 | Code 2 | 19 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
352 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B05-LF-00-ICT-COM-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Communication Equipment System Plan | 2025-06-11 | 2 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00043-R00 | Code 2 | 25 Jun 25 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 |  | ATLS-004-SD-ICT-00043-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 | 25 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
353 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B05-LF-01-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-01 |  | 2 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00043-R00 | Code 2 | 25 Jun 25 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 |  | ATLS-004-SD-ICT-00043-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 | 25 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
354 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B05-LF-02-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-02 | 2025-06-11 | 2 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00043-R00 | Code 2 | 25 Jun 25 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 |  | ATLS-004-SD-ICT-00043-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 | 25 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
355 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B05-LF-03-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-03 |  | 2 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00043-R00 | Code 2 | 25 Jun 25 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 |  | ATLS-004-SD-ICT-00043-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 | 25 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
356 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 04 | ICT | COM | SD | 00 | 1300403-ATS-B05-LF-04-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-04 | 2025-06-11 | 2 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00043-R00 | Code 2 | 25 Jun 25 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 |  | ATLS-004-SD-ICT-00043-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00049-R00 | Code 2 | 25 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
357 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B02-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Overall Plan | 2025-06-11 | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
358 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B02-GF-01-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan Part 01 | 2025-06-11 | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
359 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B02-GF-02-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan Part 02 |  | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
360 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B02-GF-03-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan Part 03 | 2025-06-11 | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
361 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B02-FF-00-ICT-COM-SD-00 | First Floor Communication Equipment Overall Plan | 2025-06-11 | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
362 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B02-FF-01-ICT-COM-SD-00 | First Floor Communication Equipment Plan Part 01 | 2025-06-11 | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
363 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B02-FF-02-ICT-COM-SD-00 | First Floor Communication Equipment Plan Part 02 | 2025-06-11 | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
364 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B02-FF-03-ICT-COM-SD-00 | First Floor Communication Equipment Plan Part 03 |  | 4 | --- | 00 | 2025-06-11 | ATLS-004-SD-ICT-00040-R00 | Code 2 | 15 Jun 25 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 |  | ATLS-004-SD-ICT-00040-R00 | 2025-06-11 | ATV-1300000403-SDS-ICT-00035-R00 | 2025-06-12 | ATV-1300000403-SDS-ICT-00035-R00 | Code 2 | 15 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
365 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | CNT | SD | 0 | 1300403-ATS-B03-BF-00-ICT-CNT-SD-0 | Basement Floor Contaiment Overall Plan | 2025-07-10 | 5 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00050-R00 | Code 2 | 29 Jun 25 | ATV-1300000403-SDS-ICT-00056-R00 | Code 2 |  | ATLS-004-SD-ICT-00050-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00056-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00056-R00 | Code 2 | 29 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
366 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B03 | BF | 01 | ICT | CNT | SD | 00 | 1300403-ATS-B03-BF-01-ICT-CNT-SD-00 | Basement Floor Contaiment Part-01 | 2025-07-10 | 5 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00050-R00 | Code 2 | 29 Jun 25 | ATV-1300000403-SDS-ICT-00056-R00 | Code 2 |  | ATLS-004-SD-ICT-00050-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00056-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00056-R00 | Code 2 | 29 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
367 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B03 | BF | 02 | ICT | CNT | SD | 00 | 1300403-ATS-B03-BF-02-ICT-CNT-SD-00 | Basement Floor Contaiment Part-02 | 2025-07-10 | 5 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00050-R00 | Code 2 | 29 Jun 25 | ATV-1300000403-SDS-ICT-00056-R00 | Code 2 |  | ATLS-004-SD-ICT-00050-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00056-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00056-R00 | Code 2 | 29 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 1 | Cannot find the Redundancy Route
368 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-00-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication Overall System Plan | 2025-06-06 | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
369 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-01-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-01 | 2025-06-06 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00091-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00091-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
370 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-02-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-02 | 2025-06-06 | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
371 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-03-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-03 | 2025-06-06 | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
372 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-04-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-04 |  | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
373 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-05-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-05 |  | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
374 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-06-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-06 | 2025-06-06 | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
375 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-07-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-07 | 2025-06-06 | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
376 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-08-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-08 |  | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
377 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-09-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-09 | 2025-06-06 | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
378 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-10-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-10 | 2025-06-06 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00091-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00091-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
379 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-11-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-11 | 2025-06-06 | 3 | --- | 00 | 2025-06-30 | ATLS-004-SD-ICT-00051-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 |  | ATLS-004-SD-ICT-00051-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00067-R00 | 2025-06-29 | ATV-1300000403-SDS-ICT-00067-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
380 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | WAP | SD | 00 | 1300403-ATS-B01-BF-12-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-12 | 2025-06-06 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00091-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00091-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
381 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-00-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication Overall System Plan (Arrival Level) | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
382 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-01-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-01 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
383 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-02-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-02 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
384 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-03-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-03 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
385 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-04-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-04 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
386 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-05-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-05 |  | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
387 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-06-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-06 | 2025-05-22 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
388 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-07-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-07 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
389 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-08-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-08 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
390 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-09-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-09 | 2025-05-22 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
391 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-10-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-10 | 2025-05-22 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
392 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-11-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-11 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
393 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-12-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-12 |  | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
394 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-13-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-13 | 2025-06-06 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
395 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-14-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-14 | 2025-05-22 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
396 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | WAP | SD | 00 | 1300403-ATS-B01-GF-15-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-15 | 2025-05-22 | 6 | --- | 00 | 2025-06-26 | ATLS-004-SD-ICT-00052-R00 | Code 2 | 02 Jul 25 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 |  | ATLS-004-SD-ICT-00052-R00 | 2025-06-26 | ATV-1300000403-SDS-ICT-00066-R00 | 2025-06-28 | ATV-1300000403-SDS-ICT-00066-R00 | Code 2 | 02 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
397 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-00-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment Overall System Plan(Arrival Level) | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
398 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-01-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-01 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
399 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-02-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-02 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
400 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-03-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-03 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
401 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-04-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-04 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
402 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-05-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-05 | 2025-05-18 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
403 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-06-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-06 | 2025-05-18 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
404 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-07-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-07 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
405 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-08-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-08 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
406 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-09-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-09 | 2025-05-18 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
407 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-10-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-10 | 2025-05-18 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
408 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-11-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-11 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
409 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-12-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-12 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
410 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-13-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-13 | 2025-06-11 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
411 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-14-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-14 |  | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
412 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | COM | SD | 00 | 1300403-ATS-B01-GF-15-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-15 | 2025-05-18 | 4 | --- | 00 | 2025-06-13 | ATLS-004-SD-ICT-00039-R00 | Code 2 | 17 Jun 25 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 |  | ATLS-004-SD-ICT-00039-R00 | 2025-06-13 | ATV-1300000403-SDS-ICT-00037-R00 | 2025-06-14 | ATV-1300000403-SDS-ICT-00037-R00 | Code 2 | 17 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
413 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-00-ICT-SIG-SD-00 | Ground Floor Digital Signage Overall Layout Plan | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
414 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-01-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-01 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
415 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-02-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-02 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
416 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-03-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-03 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
417 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-04-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-04 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
418 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-05-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-05 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
419 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-06-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-06 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
420 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-07-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-07 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
421 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-08-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-08 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
422 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-09-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-09 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
423 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-10-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-10 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
424 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-11-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-11 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
425 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-12-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-12 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
426 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-13-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-13 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
427 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-14-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-14 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
428 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | SIG | SD | 00 | 1300403-ATS-B01-GF-15-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-15 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00047-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 |  | ATLS-004-SD-ICT-00047-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00039-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00039-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
429 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-00-ICT-SIG-SD-00 | First Floor Digital Signage Overall Layout Plan | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
430 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-01-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-01 |  | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
431 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-02-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-01 |  | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
432 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-03-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-01 |  | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
433 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-04-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-04 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
434 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-05-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-05 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
435 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-06-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-06 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
436 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-07-ICT-SIG-SD-00 | Firstfloor Digital Signage Layout Plan Part-07 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
437 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-08-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-08 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
438 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-09-ICT-SIG-SD-00 | Firstfloor Digital Signage Layout Plan Part-09 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
439 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-10-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-10 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
440 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-11-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-11 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
441 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-12-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-12 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
442 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-13-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-13 | 2025-06-11 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
443 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-14-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-14 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
444 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | SIG | SD | 00 | 1300403-ATS-B01-FF-15-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-15 | 2025-05-22 | 7 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00048-R00 | Code 2 | 22 Jun 25 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 |  | ATLS-004-SD-ICT-00048-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00038-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00038-R00 | Code 2 | 22 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
445 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | SIG | SD | 00 | 1300403-ATS-B02-GF-00-ICT-SIG-SD-00 | Ground Floor Digital Signage Overall Layout Plan | 2025-05-24 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
446 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | SIG | SD | 00 | 1300403-ATS-B02-GF-01-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-01 | 2025-05-22 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
447 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | SIG | SD | 00 | 1300403-ATS-B02-GF-02-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-02 | 2025-05-22 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
448 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | SIG | SD | 00 | 1300403-ATS-B02-GF-03-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-03 | 2025-05-22 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
449 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | SIG | SD | 00 | 1300403-ATS-B02-FF-00-ICT-SIG-SD-00 | First Floor Digital Signage Overall Layout Plan | 2025-05-24 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
450 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | SIG | SD | 00 | 1300403-ATS-B02-FF-01-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-01 | 2025-05-24 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
451 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | SIG | SD | 00 | 1300403-ATS-B02-FF-02-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-02 | 2025-05-24 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
452 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | SIG | SD | 00 | 1300403-ATS-B02-FF-03-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-03 | 2025-05-22 | 8 | --- | 00 | 2025-06-15 | ATLS-004-SD-ICT-00049-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 |  | ATLS-004-SD-ICT-00049-R00 | 2025-06-15 | ATV-1300000403-SDS-ICT-00040-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00040-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
453 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B03 | GF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B03-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan | 2025-06-11 | 50 | #VALUE! | 00 | 2025-06-16 | ATLS-004-SD-ICT-00041-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00041-R00 | 2025-06-16 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
454 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-00-ICT-TEL-SD-00 | First Floor Ip Telephony Overall System Plan (Departure Level) | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
455 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-01-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-01 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
456 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-02-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-02 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
457 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-03-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-03 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
458 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-04-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-04 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
459 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-05-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-05 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
460 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-08-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-08 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
461 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-09-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-09 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
462 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-11-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-11 | 2025-05-24 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
463 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-12-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-12 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
464 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-13-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-13 | 2025-06-16 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
465 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-14-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-14 | 2025-05-24 | 4 | --- | 00 | 2025-06-19 | ATLS-004-SD-ICT-00053-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 |  | ATLS-004-SD-ICT-00053-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00042-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
466 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-00-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm Overall System Plan (Arrival Level) | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
467 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-07-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-07 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
468 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-08-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-08 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
469 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-10-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-10 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
470 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-11-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-11 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
471 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-12-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-12 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
472 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-13-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-13 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
473 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-14-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-14 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
474 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | DTA | SD | 00 | 1300403-ATS-B01-GF-15-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part-15 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00054-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00054-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
475 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-00-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm Overall System Plan (Arrival Level) | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
476 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-06-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-06 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
477 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-07-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-07 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
478 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-09-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-09 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
479 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-10-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-10 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
480 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-11-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-11 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
481 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-12-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-12 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
482 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-14-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-14 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
483 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | DTA | SD | 00 | 1300403-ATS-B01-FF-15-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part-15 | 2025-08-06 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00055-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00055-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
484 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | DTA | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-DTA-SD-00 | Mezzanine Floor Disabled Toilet Alarm Overall System Plan | 2025-08-06 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00056-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00056-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
485 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | DTA | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-DTA-SD-00 | Mezzanine Floor Disabled Toilet Alarm System Plan Part-06 | 2025-08-06 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00056-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00056-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
486 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | DTA | SD | 00 | 1300403-ATS-B02-GF-00-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Overall Plan | 2025-08-06 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00114-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00114-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
487 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | DTA | SD | 00 | 1300403-ATS-B02-GF-01-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm System Plan Part 01 | 2025-08-06 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00114-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00114-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
488 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | DTA | SD | 00 | 1300403-ATS-B02-FF-00-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Overall Plan | 2025-08-06 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00114-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00114-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
489 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | DTA | SD | 00 | 1300403-ATS-B02-FF-01-ICT-DTA-SD-00 | First Floor Disabled Toilet Alarm System Plan Part 01 | 2025-08-06 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00114-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00114-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
490 | ICT | DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B06 | GF | 00 | ICT | DTA | SD | 00 | 1300403-ATS-B06-GF-00-ICT-DTA-SD-00 | Ground Floor Disabled Toilet Alarm Overall System Plan | 2025-08-06 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00115-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00115-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 6 | Waiting for supplier confirmation for cable route
491 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | ECS | SD | 00 | 1300403-ATS-B01-GF-00-ICT-ECS-SD-00 | Ground Floor Emergency Communication System Overall System Plan (Arrival Level) |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
492 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | ECS | SD | 00 | 1300403-ATS-B01-GF-03-ICT-ECS-SD-00 | Ground Floor Emergency Communication System Plan Part-03 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
493 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | ECS | SD | 00 | 1300403-ATS-B01-GF-09-ICT-ECS-SD-00 | Ground Floor Emergency Communication System Plan Part-09 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
494 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | ECS | SD | 00 | 1300403-ATS-B01-GF-13-ICT-ECS-SD-00 | Ground Floor Emergency Communication System Plan Part-13 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
495 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | ECS | SD | 00 | 1300403-ATS-B01-GF-14-ICT-ECS-SD-00 | Ground Floor Emergency Communication System Plan Part-14 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
496 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | ECS | SD | 00 | 1300403-ATS-B01-GF-15-ICT-ECS-SD-00 | Ground Floor Emergency Communication System Plan Part-15 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
497 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | ECS | SD | 00 | 1300403-ATS-B01-FF-00-ICT-ECS-SD-00 | First Floor Emergency Communication System Overall Plan (Arrival Level) |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
498 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | ECS | SD | 00 | 1300403-ATS-B01-FF-06-ICT-ECS-SD-00 | First Floor Emergency Communication System Plan Part-06 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
499 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | ECS | SD | 00 | 1300403-ATS-B01-FF-07-ICT-ECS-SD-00 | First Floor Emergency Communication System Plan Part-07 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
500 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | ECS | SD | 00 | 1300403-ATS-B01-FF-14-ICT-ECS-SD-00 | First Floor Emergency Communication System Plan Part-14 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
501 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | ECS | SD | 00 | 1300403-ATS-B01-FF-15-ICT-ECS-SD-00 | First Floor Emergency Communication System Plan Part-15 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
502 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | ECS | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-ECS-SD-00 | Mezzanine Floor Emergency Communication System Overall Plan |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
503 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | ECS | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-ECS-SD-00 | Mezzanine Floor Emergency Communication Syste Plan Part-06 |  | 6 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | Code 2 | 29 Jun 2025 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 |  | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00053-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00053-R00 | Code 2 | 29 Jun 2025 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
504 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B07 | 00 | 00 | ICT | ENL | SD | 00 | 1300403-ATS-B07-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-08-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
505 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B07 | GF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B07-GF-00-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan | 2025-07-14 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00088-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00088-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
506 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B07 | GF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B07-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network Plan | 2025-05-30 | 43 | #VALUE! | 00 | 2025-06-23 | ATLS-004-SD-ICT-00067-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00067-R00 | 2025-06-23 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
507 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B07 | GF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B07-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan | 2025-06-11 | 3 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00068-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00050-R00 | Code 2 |  | ATLS-004-SD-ICT-00068-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00050-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00050-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
508 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B07 | GF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B07-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Plan | 2025-05-26 | 7 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00060-R00 | Code 2 | 01 Jul 25 | ATV-1300000403-SDS-ICT-00065-R00 | Code 2 |  | ATLS-004-SD-ICT-00060-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00065-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00065-R00 | Code 2 | 01 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
509 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B07 | 00 | 00 | ICT | SLD | SD | 00 | 1300403-ATS-B07-00-00-ICT-SLD-SD-00 | Low Current Systems Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
510 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B07 | 00 | 00 | ICT | SLD | SD | 01 | 1300403-ATS-B07-00-00-ICT-SLD-SD-01 | Ip Cctv & Access Control Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
511 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B06 | 00 | 00 | ICT | ENL | SD | 00 | 1300403-ATS-B06-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-08-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
512 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B06 | GF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B06-GF-00-ICT-FAS-SD-00 | Ground And Roof Top Floor Fire Alarm System Plan | 2025-07-14 | #VALUE! | #VALUE! | 00 | 2025-07-04 | ATLS-004-SD-ICT-00101-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00101-R00 | 2025-07-04 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
513 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B06 | GF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B06-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network System Plan | 2025-07-28 | 4 | --- | 00 | 2025-07-23 | ATLS-004-SD-ICT-00072-R00 | Code 2 | 27 Jul 25 | ATV-1300000403-SDS-ICT-00074-R00 | Code 2 |  | ATLS-004-SD-ICT-00072-R00 | 2025-07-23 | ATV-1300000403-SDS-ICT-00074-R00 | 2025-07-24 | ATV-1300000403-SDS-ICT-00074-R00 | Code 2 | 27 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
514 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B06 | GF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B06-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan | 2025-06-25 | 7 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00073-R00 | Code 2 | 01 Jul 25 | ATV-1300000403-SDS-ICT-00064-R00 | Code 2 |  | ATLS-004-SD-ICT-00073-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00064-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00064-R00 | Code 2 | 01 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
515 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B06 | GF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B06-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Plan | 2025-05-26 | 7 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00060-R00 | Code 2 | 01 Jul 25 | ATV-1300000403-SDS-ICT-00065-R00 | Code 2 |  | ATLS-004-SD-ICT-00060-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00065-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00065-R00 | Code 2 | 01 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
516 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B06 | 00 | 00 | ICT | SLD | SD | 00 | 1300403-ATS-B06-00-00-ICT-SLD-SD-00 | Low Current Systems Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
517 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B06 | 00 | 00 | ICT | SLD | SD | 01 | 1300403-ATS-B06-00-00-ICT-SLD-SD-01 | Ip Cctv , Access Control & Ip Master Clock Single-Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
518 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B05 | 00 | 00 | ICT | ENL | SD | 00 | 1300403-ATS-B05-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
519 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B05-LF-00-ICT-FAS-SD-00 | Lower Floor Fire Overall Plan At Level -1.5 And Level -5.0M Fire Alarm System Plan | 2025-07-14 | #VALUE! | #VALUE! | 00 | 2025-07-23 | ATLS-004-SD-ICT-00110-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00110-R00 | 2025-07-23 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
520 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B05-LF-01-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-01 | 2025-07-14 | #VALUE! | #VALUE! | 00 | 2025-07-23 | ATLS-004-SD-ICT-00110-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00110-R00 | 2025-07-23 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
521 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B05-LF-02-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-02 | 2025-07-14 | #VALUE! | #VALUE! | 00 | 2025-07-23 | ATLS-004-SD-ICT-00110-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00110-R00 | 2025-07-23 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
522 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B05-LF-03-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-03 | 2025-07-14 | #VALUE! | #VALUE! | 00 | 2025-07-23 | ATLS-004-SD-ICT-00110-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00110-R00 | 2025-07-23 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
523 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 04 | ICT | FAS | SD | 00 | 1300403-ATS-B05-LF-04-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-04 | 2025-07-14 | #VALUE! | #VALUE! | 00 | 2025-07-23 | ATLS-004-SD-ICT-00110-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00110-R00 | 2025-07-23 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
524 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B05-LF-00-ICT-DAT-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Data Network System Plan | 2025-05-30 | 1 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00059-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 |  | ATLS-004-SD-ICT-00059-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
525 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B05-LF-01-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 01 | 2025-05-30 | 1 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00059-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 |  | ATLS-004-SD-ICT-00059-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
526 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B05-LF-02-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 02 | 2025-05-30 | 1 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00059-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 |  | ATLS-004-SD-ICT-00059-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
527 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B05-LF-03-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 03 | 2025-05-30 | 1 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00059-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 |  | ATLS-004-SD-ICT-00059-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
528 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 04 | ICT | DAT | SD | 00 | 1300403-ATS-B05-LF-04-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 04 | 2025-05-30 | 1 | --- | 00 | 2025-06-23 | ATLS-004-SD-ICT-00059-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 |  | ATLS-004-SD-ICT-00059-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00048-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
529 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 00 | ICT | SLD | SD | 00 | 1300403-ATS-B05-00-00-ICT-SLD-SD-00 | Fire Alarm System Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
530 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 00 | ICT | SLD | SD | 01 | 1300403-ATS-B05-00-00-ICT-SLD-SD-01 | Ict Data Network & Bms Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
531 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 00 | ICT | SLD | SD | 02 | 1300403-ATS-B05-00-00-ICT-SLD-SD-02 | Ict Rooms Detailed Layout | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
532 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 00 | ICT | SLD | SD | 03 | 1300403-ATS-B05-00-00-ICT-SLD-SD-03 | Access Control & Ip Cctv System Single-Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
533 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 00 | ICT | SLD | SD | 04 | 1300403-ATS-B05-00-00-ICT-SLD-SD-04 | Ict Backbone Network Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
534 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 00 | ICT | SLD | SD | 05 | 1300403-ATS-B05-00-00-ICT-SLD-SD-05 | Car Parking Management System (Cpms) Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
535 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B04 | 00 | 00 | ICT | ENL | SD | 00 | 1300403-ATS-B04-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-08-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
536 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B04-LF-00-ICT-FAS-SD-00 | Lower Floor Overall Level Fire Alarm System Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
537 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B04-LF-01-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 01 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
538 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B04-LF-02-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 02 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
539 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B04-LF-03-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 03 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
540 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 04 | ICT | FAS | SD | 00 | 1300403-ATS-B04-LF-04-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 04 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
541 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B04-UF-00-ICT-FAS-SD-00 | Upper Floor Overall Level Fire Alarm System Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
542 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B04-UF-01-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 01 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
543 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B04-UF-02-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 02 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
544 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B04-UF-03-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 03 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
545 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 04 | ICT | FAS | SD | 00 | 1300403-ATS-B04-UF-04-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 04 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
546 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B04-LF-00-ICT-DAT-SD-00 | Lower Floor Overall Level Data Network System Plan | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 |  | ATLS-004-SD-ICT-00058-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00051-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
547 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B04-LF-01-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 01 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 |  | ATLS-004-SD-ICT-00058-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00051-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
548 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B04-LF-02-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 02 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 |  | ATLS-004-SD-ICT-00058-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00051-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
549 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B04-LF-03-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 03 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 |  | ATLS-004-SD-ICT-00058-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00051-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
550 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 04 | ICT | DAT | SD | 00 | 1300403-ATS-B04-LF-04-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 04 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 |  | ATLS-004-SD-ICT-00058-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00051-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00051-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00051-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
551 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B04-UF-00-ICT-DAT-SD-00 | Upper Floor Overall Level Data Network System Plan | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 |  | ATLS-004-SD-ICT-00066-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00052-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00052-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00052-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
552 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B04-UF-01-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 01 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 |  | ATLS-004-SD-ICT-00066-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00052-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00052-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00052-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
553 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B04-UF-02-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 02 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 |  | ATLS-004-SD-ICT-00066-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00052-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00052-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00052-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
554 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B04-UF-03-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 03 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 |  | ATLS-004-SD-ICT-00066-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00052-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00052-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00052-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
555 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 04 | ICT | DAT | SD | 00 | 1300403-ATS-B04-UF-04-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 04 | 2025-05-30 | 7 | --- | 01 | 2025-06-26 | ATLS-004-SD-ICT-00058-R01 | Code 2 | 2025-07-03 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 |  | ATLS-004-SD-ICT-00066-R00 | 2025-06-23 | ATV-1300000403-SDS-ICT-00052-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00052-R00 | Code 3 | 26 Jun 25 | Code 3 | ATLS-004-SD-ICT-00058-R01 | 2025-06-26 | ATV-1300000403-SDS-ICT-00052-R01 | 2025-06-27 | ATV-1300000403-SDS-ICT-00052-R01 | Code 2 | 2025-07-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
556 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B04-LF-00-ICT-VSS-SD-00 | Lower Floor Overall Level Ip Cctv System Plan | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00078-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00078-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
557 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B04-LF-01-ICT-VSS-SD-00 | Lower Floor Ip Cctv System Plan Part 01 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00078-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00078-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
558 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B04-LF-02-ICT-VSS-SD-00 | Lower Floor Ip Cctv System Plan Part 02 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00078-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00078-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
559 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B04-LF-03-ICT-VSS-SD-00 | Lower Floor Ip Cctv System Plan Part 03 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00078-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00078-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
560 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 04 | ICT | VSS | SD | 00 | 1300403-ATS-B04-LF-04-ICT-VSS-SD-00 | Lower Floor Ip Cctv System Plan Part 04 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00078-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00078-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
561 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B04-UF-00-ICT-VSS-SD-00 | Upper Floor Overall Level Ip Cctv System Plan | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00079-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00079-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
562 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B04-UF-01-ICT-VSS-SD-00 | Upper Floor Ip Cctv System Plan Part 01 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00079-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00079-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
563 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B04-UF-02-ICT-VSS-SD-00 | Upper Floor Ip Cctv System Plan Part 02 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00079-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00079-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
564 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B04-UF-03-ICT-VSS-SD-00 | Upper Floor Ip Cctv System Plan Part 03 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00079-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00079-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
565 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 04 | ICT | VSS | SD | 00 | 1300403-ATS-B04-UF-04-ICT-VSS-SD-00 | Upper Floor Ip Cctv System Plan Part 04 | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-06-25 | ATLS-004-SD-ICT-00079-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00079-R00 | 2025-06-25 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
566 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 00 | ICT | SLD | SD | 00 | 1300403-ATS-B04-00-00-ICT-SLD-SD-00 | Fire Alarm System Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
567 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 00 | ICT | SLD | SD | 01 | 1300403-ATS-B04-00-00-ICT-SLD-SD-01 | Ict Backbone Network Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
568 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 00 | ICT | SLD | SD | 02 | 1300403-ATS-B04-00-00-ICT-SLD-SD-02 | Ict Rooms Detailed Layout | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
569 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 00 | ICT | SLD | SD | 03 | 1300403-ATS-B04-00-00-ICT-SLD-SD-03 | Access Control & Ip Cctv System Single-Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
570 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 00 | ICT | SLD | SD | 04 | 1300403-ATS-B04-00-00-ICT-SLD-SD-04 | Ict Data Network Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
571 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 00 | ICT | SLD | SD | 05 | 1300403-ATS-B04-00-00-ICT-SLD-SD-05 | Car Parking Management System (Cpms ) Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
572 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B03 | 00 | 00 | ICT | ENL | SD | 00 | 1300403-ATS-B03-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plan | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
573 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B03-BF-00-ICT-FAS-SD-00 | Basement Fire Alarm System Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
574 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B03 | GF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B03-GF-00-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
575 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B03 | FF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B03-FF-00-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
576 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B03-BF-00-ICT-PAS-SD-00 | Basement Sound Managment System Plan | 2025-08-03 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00087-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00087-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
577 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B03 | GF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B03-GF-00-ICT-PAS-SD-00 | Ground Floor Sound Management System Plan | 2025-08-03 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00087-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00087-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
578 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B03 | FF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B03-FF-00-ICT-PAS-SD-00 | First Floor Sound Management System Plan | 2025-08-03 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00087-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00087-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
579 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B03-BF-00-ICT-DAT-SD-00 | Basement Data Network Plan | 2025-07-08 | 5 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00071-R00 | Code 2 | 29 Jun 25 | ATV-1300000403-SDS-ICT-00059-R00 | Code 2 |  | ATLS-004-SD-ICT-00071-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00059-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00059-R00 | Code 2 | 29 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
580 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B03 | GF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B03-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network Plan | 2025-07-28 | -19 | --- | 01 | 2025-07-28 | ATLS-004-SD-ICT-00076-R01 | AR (ATJV) | 9 Jul 25 | ATV-1300000403-SDS-ICT-00068-R01 | AR (ATJV) |  | ATLS-004-SD-ICT-00076-R00 | 2025-07-01 | ATV-1300000403-SDS-ICT-00068-R00 | 2025-07-02 | ATV-1300000403-SDS-ICT-00068-R00 | Code 3 | 9 Jul 25 | Code 3 | ATLS-004-SD-ICT-00076-R01 | 2025-07-28 | ATV-1300000403-SDS-ICT-00068-R01 |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
581 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B03 | FF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B03-FF-00-ICT-DAT-SD-00 | First Floor Data Network Plan | 2025-07-08 | -19 | --- | 01 | 2025-07-28 | ATLS-004-SD-ICT-00086-R01 | AR (ATJV) | 9 Jul 25 | ATV-1300000403-SDS-ICT-00069-R01 | AR (ATJV) |  | ATLS-004-SD-ICT-00086-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00069-R00 | 2025-07-02 | ATV-1300000403-SDS-ICT-00069-R00 | Code 3 | 9 Jul 25 | Code 3 | ATLS-004-SD-ICT-00086-R01 | 2025-07-28 | ATV-1300000403-SDS-ICT-00069-R01 |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
582 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B03-BF-00-ICT-VSS-SD-00 | Basement Ip Cctv System Plan | 2025-06-25 | 8 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00103-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00103-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00080-R00 | 2025-07-28 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
583 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B03 | GF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B03-GF-00-ICT-VSS-SD-00 | Ground Floor Ip Cctv System Plan | 2025-06-25 | 8 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00103-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00103-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00080-R00 | 2025-07-28 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
584 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B03 | FF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B03-FF-00-ICT-VSS-SD-00 | First Floor Ip Cctv System Plan | 2025-06-25 | 8 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00103-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00103-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00080-R00 | 2025-07-28 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
585 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 00 | ICT | SLD | SD | 00 | 1300403-ATS-B03-00-00-ICT-SLD-SD-00 | Fire Alarm System Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
586 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 00 | ICT | SLD | SD | 01 | 1300403-ATS-B03-00-00-ICT-SLD-SD-01 | Sound Management System Single-Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
587 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 00 | ICT | SLD | SD | 02 | 1300403-ATS-B03-00-00-ICT-SLD-SD-02 | Ict Network & Bms Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
588 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 00 | ICT | SLD | SD | 03 | 1300403-ATS-B03-00-00-ICT-SLD-SD-03 | Access Control System Single-Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
589 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 00 | ICT | SLD | SD | 04 | 1300403-ATS-B03-00-00-ICT-SLD-SD-04 | Ict Rooms Detailed Layouts | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
590 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 00 | ICT | SLD | SD | 05 | 1300403-ATS-B03-00-00-ICT-SLD-SD-05 | Disabled Alarm Toilet Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
591 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 00 | ICT | SLD | SD | 06 | 1300403-ATS-B03-00-00-ICT-SLD-SD-06 | Ip Cctv Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
592 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B03-BF-00-ICT-TEL-SD-00 | Basement Floor Ip Telephone System Plan | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-07-11 | ATLS-004-SD-ICT-00105-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00105-R00 | 2025-07-11 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
593 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B03 | GF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B03-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan | 2025-06-25 | #VALUE! | #VALUE! | 00 | 2025-07-11 | ATLS-004-SD-ICT-00105-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00105-R00 | 2025-07-11 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
594 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B03 | BF | 00 | ICT | COM | SD | 00 | 1300403-ATS-B03-BF-00-ICT-COM-SD-00 | Basement Floor Communication Equipment Plan | 2025-06-23 | 2 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00069-R00 | Code 2 | 26 Jun 25 | ATV-1300000403-SDS-ICT-00054-R00 | Code 2 |  | ATLS-004-SD-ICT-00069-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00054-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00054-R00 | Code 2 | 26 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
595 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B02 | 00 | 00 | ICT | ENL | SD | 00 | 1300403-ATS-B02-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans (1 Of 2) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
596 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B02 | 00 | 00 | ICT | ENL | SD | 01 | 1300403-ATS-B02-00-00-ICT-ENL-SD-01 | Ict Technical Rooms Enlarged Plans (2 Of 2) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
597 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B02-GF-00-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Overall Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
598 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B02-GF-01-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan Part 01 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
599 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B02-GF-02-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan Part 02 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
600 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B02-GF-03-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan Part 03 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
601 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B02-FF-00-ICT-FAS-SD-00 | First Floor Fire Alarm System Overall Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
602 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B02-FF-01-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part 01 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
603 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B02-FF-02-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part 02 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
604 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B02-FF-03-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part 03 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
605 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | RF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B02-RF-00-ICT-FAS-SD-00 | Roof Fire Alarm System Overall Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
606 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | RF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B02-RF-01-ICT-FAS-SD-00 | Roof Fire Alarm System Plan Part 01 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
607 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | RF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B02-RF-02-ICT-FAS-SD-00 | Roof Fire Alarm System Plan Part 02 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
608 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B02-GF-00-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Overall Plan | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
609 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | PAS | SD | 00 | 1300403-ATS-B02-GF-01-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Plan Part 01 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
610 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | PAS | SD | 00 | 1300403-ATS-B02-GF-02-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Plan Part 02 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
611 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | PAS | SD | 00 | 1300403-ATS-B02-GF-03-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Plan Part 03 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
612 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B02-FF-00-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Overall Plan | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
613 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | PAS | SD | 00 | 1300403-ATS-B02-FF-01-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part 01 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
614 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | PAS | SD | 00 | 1300403-ATS-B02-FF-02-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part 02 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
615 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | PAS | SD | 00 | 1300403-ATS-B02-FF-03-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part 03 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
616 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B02-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Overall Plan | 2025-06-25 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00085-R01 | UR (DAR) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00070-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00085-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00070-R00 | 2025-07-02 | ATV-1300000403-SDS-ICT-00070-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00085-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00070-R01 | 2025-07-29 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
617 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | TEL | SD | 00 | 1300403-ATS-B02-GF-01-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan Part 01 | 2025-06-25 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00085-R01 | UR (DAR) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00070-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00085-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00070-R00 | 2025-07-02 | ATV-1300000403-SDS-ICT-00070-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00085-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00070-R01 | 2025-07-29 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
618 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | TEL | SD | 00 | 1300403-ATS-B02-GF-02-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan Part 02 | 2025-06-25 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00085-R01 | UR (DAR) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00070-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00085-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00070-R00 | 2025-07-02 | ATV-1300000403-SDS-ICT-00070-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00085-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00070-R01 | 2025-07-29 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
619 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | TEL | SD | 00 | 1300403-ATS-B02-GF-03-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan Part 03 | 2025-06-25 | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00085-R01 | UR (DAR) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00070-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00085-R00 | 2025-06-30 | ATV-1300000403-SDS-ICT-00070-R00 | 2025-07-02 | ATV-1300000403-SDS-ICT-00070-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00085-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00070-R01 | 2025-07-29 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
620 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B02-FF-00-ICT-TEL-SD-00 | First Floor Ip Telephone System Overall Plan | 2025-07-29 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00112-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00112-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00082-R00 | 2025-07-30 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
621 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | TEL | SD | 00 | 1300403-ATS-B02-FF-01-ICT-TEL-SD-00 | First Floor Ip Telephone System Plan Part 01 | 2025-07-29 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00112-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00112-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00082-R00 | 2025-07-30 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
622 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | TEL | SD | 00 | 1300403-ATS-B02-FF-02-ICT-TEL-SD-00 | First Floor Ip Telephone System Plan Part 02 | 2025-07-29 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00112-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00112-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00082-R00 | 2025-07-30 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
623 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | TEL | SD | 00 | 1300403-ATS-B02-FF-03-ICT-TEL-SD-00 | First Floor Ip Telephone System Plan Part 03 | 2025-07-29 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00112-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00112-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00082-R00 | 2025-07-30 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
624 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 00 | 1300403-ATS-B02-00-00-ICT-SLD-SD-00 | Fire Alarm System Single-Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
625 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 01 | 1300403-ATS-B02-00-00-ICT-SLD-SD-01 | Public Address & Voice Evacuation Systems Single-Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
626 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 02 | 1300403-ATS-B02-00-00-ICT-SLD-SD-02 | Ict Backbone Network Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
627 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 03 | 1300403-ATS-B02-00-00-ICT-SLD-SD-03 | Ict Rooms Detailed Layouts (1 Of 2) | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
628 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 04 | 1300403-ATS-B02-00-00-ICT-SLD-SD-04 | Ict Rooms Detailed Layouts (2 Of 2) | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
629 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 05 | 1300403-ATS-B02-00-00-ICT-SLD-SD-05 | Ict Data Network Single Line Diagrams | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
630 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 06 | 1300403-ATS-B02-00-00-ICT-SLD-SD-06 | Ip Master Clock Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
631 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 07 | 1300403-ATS-B02-00-00-ICT-SLD-SD-07 | Disabled Toilet Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
632 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 08 | 1300403-ATS-B02-00-00-ICT-SLD-SD-08 | Ip Cctv Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
633 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 09 | 1300403-ATS-B02-00-00-ICT-SLD-SD-09 | Fids & Cids Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
634 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 10 | 1300403-ATS-B02-00-00-ICT-SLD-SD-10 | Access Control Single Line Diagram | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
635 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 00 | ICT | SLD | SD | 11 | 1300403-ATS-B02-00-00-ICT-SLD-SD-11 | Electronic Visual Information Display (Evids) And Cid Single Line Diagrams | 2025-09-08 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
636 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B02-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Overall Plan | 2025-05-26 | 6 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00061-R00 | Code 2 | 01 Jul 25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 |  | ATLS-004-SD-ICT-00061-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 | 01 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
637 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B02-GF-01-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part 01 | 2025-05-26 | 6 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00061-R00 | Code 2 | 01 Jul 25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 |  | ATLS-004-SD-ICT-00061-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 | 01 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
638 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B02-GF-02-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part 02 | 2025-05-26 | 6 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00061-R00 | Code 2 | 01 Jul 25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 |  | ATLS-004-SD-ICT-00061-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 | 01 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
639 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B02-GF-03-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part 03 | 2025-05-26 | 6 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00061-R00 | Code 2 | 01 Jul 25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 |  | ATLS-004-SD-ICT-00061-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00062-R00 | Code 2 | 01 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
640 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B02-FF-00-ICT-ACS-SD-00 | First Floor Access Control System Overall Plan | 2025-05-26 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00062-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00062-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
641 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B02-FF-01-ICT-ACS-SD-00 | First Floor Access Control System Plan Part 01 | 2025-05-26 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00062-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00062-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
642 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B02-FF-02-ICT-ACS-SD-00 | First Floor Access Control System Plan Part 02 | 2025-05-26 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00062-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00062-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
643 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B02-FF-03-ICT-ACS-SD-00 | First Floor Access Control System Plan Part 03 | 2025-05-26 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00062-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00062-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
644 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B02-GF-00-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Overall Plan | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
645 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B02-GF-01-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part 01 | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
646 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B02-GF-02-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part 02 | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
647 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B02-GF-03-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part 03 | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
648 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B02-FF-00-ICT-VSS-SD-00 | First Floor Video Survelliance System Overall Plan | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
649 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B02-FF-01-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part 01 | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
650 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B02-FF-02-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part 02 | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
651 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B02-FF-03-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part 03 | 2025-08-13 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
652 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | WAP | SD | 00 | 1300403-ATS-B02-GF-00-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Overall Plan | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00084-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00084-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
653 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | WAP | SD | 00 | 1300403-ATS-B02-GF-01-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part 01 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00084-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00084-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
654 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | WAP | SD | 00 | 1300403-ATS-B02-GF-02-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part 02 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00084-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00084-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
655 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | WAP | SD | 00 | 1300403-ATS-B02-GF-03-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part 03 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00084-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00084-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
656 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | WAP | SD | 00 | 1300403-ATS-B02-FF-00-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Overall Plan | 2025-06-30 | 3 | --- | 00 | 2025-07-26 | ATLS-004-SD-ICT-00083-R00 | Code 2 | 29 Jul 25 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 |  | ATLS-004-SD-ICT-00083-R00 | 2025-07-26 | ATV-1300000403-SDS-ICT-00078-R00 | 2025-07-27 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 | 29 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
657 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | WAP | SD | 00 | 1300403-ATS-B02-FF-01-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part 01 | 2025-06-30 | 3 | --- | 00 | 2025-07-26 | ATLS-004-SD-ICT-00083-R00 | Code 2 | 29 Jul 25 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 |  | ATLS-004-SD-ICT-00083-R00 | 2025-07-26 | ATV-1300000403-SDS-ICT-00078-R00 | 2025-07-27 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 | 29 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
658 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | WAP | SD | 00 | 1300403-ATS-B02-FF-02-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part 02 | 2025-06-30 | 3 | --- | 00 | 2025-07-26 | ATLS-004-SD-ICT-00083-R00 | Code 2 | 29 Jul 25 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 |  | ATLS-004-SD-ICT-00083-R00 | 2025-07-26 | ATV-1300000403-SDS-ICT-00078-R00 | 2025-07-27 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 | 29 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
659 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | WAP | SD | 00 | 1300403-ATS-B02-FF-03-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part 03 | 2025-06-30 | 3 | --- | 00 | 2025-07-26 | ATLS-004-SD-ICT-00083-R00 | Code 2 | 29 Jul 25 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 |  | ATLS-004-SD-ICT-00083-R00 | 2025-07-26 | ATV-1300000403-SDS-ICT-00078-R00 | 2025-07-27 | ATV-1300000403-SDS-ICT-00078-R00 | Code 2 | 29 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
660 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B02-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network System Overall Plan | 2025-08-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
661 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B02-GF-01-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part 01 | 2025-08-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
662 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B02-GF-02-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part 02 | 2025-08-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
663 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B02-GF-03-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part 03 | 2025-08-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
664 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B02-FF-00-ICT-DAT-SD-00 | First Floor Data Network System Overall Plan | 2025-07-08 | #VALUE! | #VALUE! | 00 | 2025-07-11 | ATLS-004-SD-ICT-00106-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00106-R00 | 2025-07-11 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
665 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B02-FF-01-ICT-DAT-SD-00 | First Floor Data Network System Plan Part 01 | 2025-07-08 | #VALUE! | #VALUE! | 00 | 2025-07-11 | ATLS-004-SD-ICT-00106-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00106-R00 | 2025-07-11 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
666 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B02-FF-02-ICT-DAT-SD-00 | First Floor Data Network System Plan Part 02 | 2025-07-08 | #VALUE! | #VALUE! | 00 | 2025-07-11 | ATLS-004-SD-ICT-00106-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00106-R00 | 2025-07-11 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
667 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B02-FF-03-ICT-DAT-SD-00 | First Floor Data Network System Plan Part 03 | 2025-07-08 | #VALUE! | #VALUE! | 00 | 2025-07-11 | ATLS-004-SD-ICT-00106-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00106-R00 | 2025-07-11 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
668 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 00 | 1300403-ATS-B01-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans (1 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
669 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 01 | 1300403-ATS-B01-00-00-ICT-ENL-SD-01 | Ict Technical Rooms Enlarged Plans (2 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
670 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 02 | 1300403-ATS-B01-00-00-ICT-ENL-SD-02 | Ict Technical Rooms Enlarged Plans (3 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
671 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 03 | 1300403-ATS-B01-00-00-ICT-ENL-SD-03 | Ict Technical Rooms Enlarged Plans (4 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
672 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 04 | 1300403-ATS-B01-00-00-ICT-ENL-SD-04 | Ict Technical Rooms Enlarged Plans (5 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
673 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 05 | 1300403-ATS-B01-00-00-ICT-ENL-SD-05 | Ict Technical Rooms Enlarged Plans (6 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
674 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 06 | 1300403-ATS-B01-00-00-ICT-ENL-SD-06 | Ict Technical Rooms Enlarged Plans (7 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
675 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 07 | 1300403-ATS-B01-00-00-ICT-ENL-SD-07 | Ict Technical Rooms Enlarged Plans (8 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
676 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 08 | 1300403-ATS-B01-00-00-ICT-ENL-SD-08 | Ict Technical Rooms Enlarged Plans (9 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
677 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 09 | 1300403-ATS-B01-00-00-ICT-ENL-SD-09 | Ict Technical Rooms Enlarged Plans (10 Of 10) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
678 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 10 | 1300403-ATS-B01-00-00-ICT-ENL-SD-10 | Ict Rooms Detailed Layouts (1 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
679 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 11 | 1300403-ATS-B01-00-00-ICT-ENL-SD-11 | Ict Rooms Detailed Layouts (2 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
680 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 12 | 1300403-ATS-B01-00-00-ICT-ENL-SD-12 | Ict Rooms Detailed Layouts (3 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
681 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 13 | 1300403-ATS-B01-00-00-ICT-ENL-SD-13 | Ict Rooms Detailed Layouts (4 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
682 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 14 | 1300403-ATS-B01-00-00-ICT-ENL-SD-14 | Ict Rooms Detailed Layouts (5 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
683 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 15 | 1300403-ATS-B01-00-00-ICT-ENL-SD-15 | Ict Rooms Detailed Layouts (6 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
684 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 16 | 1300403-ATS-B01-00-00-ICT-ENL-SD-16 | Ict Rooms Detailed Layouts (7 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
685 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 17 | 1300403-ATS-B01-00-00-ICT-ENL-SD-17 | Ict Rooms Detailed Layouts (8 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
686 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 18 | 1300403-ATS-B01-00-00-ICT-ENL-SD-18 | Ict Rooms Detailed Layouts (9 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
687 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 19 | 1300403-ATS-B01-00-00-ICT-ENL-SD-19 | Ict Rooms Detailed Layouts (10 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
688 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 20 | 1300403-ATS-B01-00-00-ICT-ENL-SD-20 | Ict Rooms Detailed Layouts (11 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
689 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 21 | 1300403-ATS-B01-00-00-ICT-ENL-SD-21 | Ict Rooms Detailed Layouts (12 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
690 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 22 | 1300403-ATS-B01-00-00-ICT-ENL-SD-22 | Ict Rooms Detailed Layouts (13 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
691 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 23 | 1300403-ATS-B01-00-00-ICT-ENL-SD-23 | Ict Rooms Detailed Layouts (14 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
692 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 24 | 1300403-ATS-B01-00-00-ICT-ENL-SD-24 | Ict Rooms Detailed Layouts (15 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
693 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 25 | 1300403-ATS-B01-00-00-ICT-ENL-SD-25 | Ict Rooms Detailed Layouts (16 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
694 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 26 | 1300403-ATS-B01-00-00-ICT-ENL-SD-26 | Ict Rooms Detailed Layouts (17 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
695 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 00 | ICT | ENL | SD | 27 | 1300403-ATS-B01-00-00-ICT-ENL-SD-27 | Ict Rooms Detailed Layouts (18 Of 18) | 2025-08-27 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
696 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-00-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm Overall System Plan | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
697 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-01-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-01 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
698 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-02-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-02 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
699 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-03-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-03 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
700 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-04-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-04 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
701 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-05-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-05 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
702 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-06-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-06 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
703 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-07-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-07 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
704 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-08-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-08 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
705 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-09-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-09 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
706 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-10-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-10 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
707 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-11-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-11 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
708 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | FAS | SD | 00 | 1300403-ATS-B01-BF-12-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-12 | 2025-06-30 | #VALUE! | #VALUE! | 00 | 2025-07-08 | ATLS-004-SD-ICT-00075-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00075-R00 | 2025-07-08 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
709 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-00-ICT-FAS-SD-00 | First Floor Fire Alarm Ovrall System Plan (Departure Level) | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
710 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-01-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-01 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
711 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-02-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-02 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
712 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-03-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-03 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
713 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-04-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-04 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
714 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-05-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-05 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
715 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-06-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-06 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
716 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-07-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-07 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
717 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-08-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-08 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
718 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-09-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-09 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
719 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-10-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-10 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
720 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-11-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-11 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
721 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-12-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-12 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
722 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-13-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-13 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
723 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-14-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-14 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
724 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | FAS | SD | 00 | 1300403-ATS-B01-GF-15-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-15 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
725 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-00-ICT-FAS-SD-00 | First Floor Fire Alarm Ovrall System Plan (Departure Level) | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
726 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-01-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-01 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
727 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-02-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-02 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
728 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-03-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-03 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
729 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-04-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-04 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
730 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-05-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-05 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
731 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-06-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-06 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
732 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-07-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-07 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
733 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-08-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-08 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
734 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-09-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-09 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
735 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-10-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-10 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
736 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-11-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-11 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
737 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-12-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-12 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
738 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-13-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-13 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
739 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-14-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-14 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
740 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | FAS | SD | 00 | 1300403-ATS-B01-FF-15-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-15 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
741 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-FAS-SD-00 | Mezzanine Fire Alarm Overall System Plan | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
742 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-01 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
743 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-02 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
744 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-03 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
745 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-04 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
746 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-05 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
747 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-06 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
748 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-07 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
749 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-08 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
750 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-09 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
751 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-10 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
752 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-11 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
753 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-12 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
754 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-13-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-13 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
755 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-14-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-14 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
756 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | FAS | SD | 00 | 1300403-ATS-B01-MZ-15-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-15 | 2025-08-09 | 0 | #VALUE! | 00 | 2025-08-05 | ATLS-004-SD-ICT-00118-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00118-R00 | 2025-08-05 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
757 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | FAS | SD | 01 | 1300403-ATS-B01-GF-00-ICT-FAS-SD-01 | Locker Area Fire Alarm System Plan | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
758 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-00-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification Overall System Plan | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
759 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-01-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-01 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
760 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-02-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-02 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
761 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-03-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-03 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
762 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-04-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-04 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
763 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-05-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-05 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
764 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-06-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-06 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
765 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-07-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-07 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
766 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-08-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-08 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
767 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-09-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-09 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
768 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-10-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-10 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
769 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-11-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-11 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
770 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | PAS | SD | 00 | 1300403-ATS-B01-BF-12-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-12 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
771 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-00-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Overall System Plan (Arrival Level) | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
772 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-01-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-01 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
773 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-02-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-02 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
774 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-03-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-03 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
775 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-04-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-04 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
776 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-05-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-05 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
777 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-06-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-06 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
778 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-07-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-07 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
779 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-08-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-08 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
780 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-09-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-09 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
781 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-10-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-10 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
782 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-11-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-11 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
783 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-12-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-12 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
784 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-13-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-13 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
785 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-14-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-14 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
786 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | PAS | SD | 00 | 1300403-ATS-B01-GF-15-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-15 | 2025-08-19 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
787 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | 00 | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B01-00-00-ICT-PAS-SD-00 | Locker Area Public Address And Mass Notification System Plan | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
788 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-00-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification Overall System Plan(Departure Level) | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
789 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-01-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-01 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
790 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-02-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-02 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
791 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-03-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-03 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
792 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-04-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-04 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
793 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-05-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-05 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
794 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-06-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-06 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
795 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-07-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-07 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
796 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-08-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-08 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
797 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-09-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-09 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
798 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-10-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-10 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
799 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-11-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-11 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
800 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-12-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-12 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
801 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-13-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-13 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
802 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-14-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-14 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
803 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | PAS | SD | 00 | 1300403-ATS-B01-FF-15-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-15 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
804 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification Overall System Plan | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
805 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-01 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
806 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-02 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
807 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-03 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
808 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-04 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
809 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-05 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
810 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-06 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
811 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-07 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
812 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-08 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
813 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-09 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
814 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-10 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
815 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-11 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
816 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | PAS | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-12 | 2025-08-21 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 4 | Supplier hasn't been finalized
817 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-01-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-01 | 2025-08-05 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00117-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00117-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
818 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-09-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-09 | 2025-08-05 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00117-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00117-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
819 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | TEL | SD | 00 | 1300403-ATS-B01-BF-12-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-12 | 2025-08-05 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00117-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00117-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
820 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | 00 | 00 | ICT | TEL | SD | 00 | 1300403-ATS-B01-00-00-ICT-TEL-SD-00 | Locker Area Ip Telephony System Plan | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
821 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-06-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-06 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
822 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-07-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-07 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
823 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-10-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-10 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
824 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | TEL | SD | 00 | 1300403-ATS-B01-FF-15-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-15 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 3 | RFC Raised - Exceeding 90 m
825 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 00 | 1300403-ATS-B01-00-00-ICT-SLD-SD-00 | Fire Alarm Single Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
826 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 01 | 1300403-ATS-B01-00-00-ICT-SLD-SD-01 | Public Address & Voice Evacuation System Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
827 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 02 | 1300403-ATS-B01-00-00-ICT-SLD-SD-02 | Ict Aan Telephone Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
828 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 03 | 1300403-ATS-B01-00-00-ICT-SLD-SD-03 | Ip Video Surveillance System Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
829 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 04 | 1300403-ATS-B01-00-00-ICT-SLD-SD-04 | Access Control System Single Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
830 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 05 | 1300403-ATS-B01-00-00-ICT-SLD-SD-05 | Master Clock System Single Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
831 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 06 | 1300403-ATS-B01-00-00-ICT-SLD-SD-06 | Emergency Communication System And Disabled Alarm Toilet Single Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
832 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 07 | 1300403-ATS-B01-00-00-ICT-SLD-SD-07 | Ict Backbone Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
833 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 08 | 1300403-ATS-B01-00-00-ICT-SLD-SD-08 | Ict Aan Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
834 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 09 | 1300403-ATS-B01-00-00-ICT-SLD-SD-09 | Ict Customs Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
835 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 10 | 1300403-ATS-B01-00-00-ICT-SLD-SD-10 | Ict Gdp Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
836 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 11 | 1300403-ATS-B01-00-00-ICT-SLD-SD-11 | Ict Gid Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
837 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 12 | 1300403-ATS-B01-00-00-ICT-SLD-SD-12 | Ict Intelligent Services Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
838 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 13 | 1300403-ATS-B01-00-00-ICT-SLD-SD-13 | Ict Nic_Myphone Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
839 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 14 | 1300403-ATS-B01-00-00-ICT-SLD-SD-14 | Ict Pan (Wap) Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
840 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 15 | 1300403-ATS-B01-00-00-ICT-SLD-SD-15 | Ict Rsaf Data Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
841 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 16 | 1300403-ATS-B01-00-00-ICT-SLD-SD-16 | Sas Equipment Single Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
842 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 17 | 1300403-ATS-B01-00-00-ICT-SLD-SD-17 | Flight Information Dispaly System (Fids) Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
843 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 00 | ICT | SLD | SD | 18 | 1300403-ATS-B01-00-00-ICT-SLD-SD-18 | E-Gate Gdp Network Single-Line Diagram | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
844 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | BRS | SD | 00 | 1300403-ATS-B01-GF-00-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation Overall System Plan (Arrival Level) | 2025-06-26 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00089-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00089-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
845 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | BRS | SD | 00 | 1300403-ATS-B01-GF-05-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-05 | 2025-06-26 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00089-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00089-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
846 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | BRS | SD | 00 | 1300403-ATS-B01-GF-09-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-09 | 2025-06-26 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00089-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00089-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
847 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | BRS | SD | 00 | 1300403-ATS-B01-GF-13-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-13 | 2025-06-26 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00089-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00089-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
848 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | BRS | SD | 00 | 1300403-ATS-B01-GF-14-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-14 | 2025-06-26 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00089-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00089-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
849 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | BRS | SD | 00 | 1300403-ATS-B01-GF-15-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-15 | 2025-06-26 | #VALUE! | #VALUE! | 00 | 2025-06-28 | ATLS-004-SD-ICT-00089-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00089-R00 | 2025-06-28 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
850 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-00-ICT-ACS-SD-00 | Terminal Basement Floor Access Control Overall System Plan | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
851 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-01-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-01 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
852 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-02-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-02 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
853 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-03-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-03 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
854 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-04-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-04 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
855 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-05-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-05 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
856 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-06-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-06 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
857 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-07-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-07 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
858 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-08-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-08 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
859 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-09-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-09 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
860 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-10-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-10 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
861 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-11-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-11 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
862 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | ACS | SD | 00 | 1300403-ATS-B01-BF-12-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-12 | 2025-05-26 | 5 | --- | 00 | 2025-06-18 | ATLS-004-SD-ICT-00063-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 |  | ATLS-004-SD-ICT-00063-R00 | 2025-06-18 | ATV-1300000403-SDS-ICT-00044-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00044-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
863 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control Overall System Plan (Arrival Level) | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
864 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-01-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-01 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
865 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-02-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-02 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
866 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-03-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-03 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
867 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-04-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-04 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
868 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-05-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-05 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
869 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-06-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-06 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
870 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-07-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-07 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
871 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-08-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-08 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
872 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-09-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-09 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
873 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-10-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-10 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
874 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-11-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-11 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
875 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-12-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-12 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
876 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-13-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-13 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
877 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-14-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-14 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
878 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | ACS | SD | 00 | 1300403-ATS-B01-GF-15-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-15 | 2025-06-24 | 6 | --- | 00 | 2025-06-24 | ATLS-004-SD-ICT-00070-R00 | Code 2 | 30 Jun 25 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 |  | ATLS-004-SD-ICT-00070-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | 2025-06-24 | ATV-1300000403-SDS-ICT-00058-R00 | Code 2 | 30 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
879 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-00-ICT-ACS-SD-00 | First Floor Access Control Overall System Plan(Departure Level) | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
880 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-01-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-01 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
881 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-02-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-02 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
882 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-03-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-03 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
883 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-04-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-04 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
884 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-05-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-05 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
885 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-06-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-06 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
886 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-07-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-07 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
887 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-08-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-08 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
888 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-09-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-09 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
889 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-10-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-10 | 2025-05-12 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
890 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-11-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-11 | 2025-05-12 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
891 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-12-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-12 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
892 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-13-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-13 | 2025-05-26 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
893 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-14-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-14 | 2025-05-12 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
894 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | ACS | SD | 00 | 1300403-ATS-B01-FF-15-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-15 | 2025-05-12 | 4 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00064-R00 | Code 2 | 24 Jun 25 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 |  | ATLS-004-SD-ICT-00064-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00043-R00 | 2025-06-19 | ATV-1300000403-SDS-ICT-00043-R00 | Code 2 | 24 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
895 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-ACS-SD-00 | Mezzanine Floor Access Control Overall System Plan | 2025-05-26 | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
896 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-01 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
897 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-02 | 2025-05-26 | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
898 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-03 | 2025-05-26 | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
899 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 04 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-04-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-04 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
900 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 05 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-05-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-05 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
901 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-06 | 2025-05-26 | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
902 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-07 | 2025-05-26 | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
903 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 08 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-08-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-08 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
904 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 09 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-09-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-09 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
905 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-10 | 2025-05-26 | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
906 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-11 | 2025-05-26 | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
907 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-12 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
908 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-13-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-13 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
909 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-14-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-14 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
910 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | ACS | SD | 00 | 1300403-ATS-B01-MZ-15-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-15 |  | 3 | --- | 00 | 2025-06-20 | ATLS-004-SD-ICT-00065-R00 | Code 2 | 23 Jun 25 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 |  | ATLS-004-SD-ICT-00065-R00 | 2025-06-20 | ATV-1300000403-SDS-ICT-00045-R00 | 2025-06-21 | ATV-1300000403-SDS-ICT-00045-R00 | Code 2 | 23 Jun 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
911 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-00-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance Overall System Plan | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
912 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-01-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-01 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
913 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-02-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-02 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
914 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-03-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-03 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
915 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 04 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-04-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-04 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
916 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 05 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-05-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-05 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
917 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 06 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-06-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-06 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
918 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 07 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-07-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-07 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
919 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 08 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-08-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-08 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
920 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-09-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-09 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
921 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-10-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-10 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
922 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-11-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-11 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
923 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | VSS | SD | 00 | 1300403-ATS-B01-BF-12-ICT-VSS-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-12 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
924 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-00-ICT-VSS-SD-00 | Ground Floor Video Survelliance Overall System Plan (Arrival Level) | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
925 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-01-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-01 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
926 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-02-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-02 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
927 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-03-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-03 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
928 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-04-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-04 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
929 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-05-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-05 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
930 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-06-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-06 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
931 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-07-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-07 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
932 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-08-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-08 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
933 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-09-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-09 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
934 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-10-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-10 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
935 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-11-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-11 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
936 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-12-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-12 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
937 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-13-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-13 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
938 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-14-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-14 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
939 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | VSS | SD | 00 | 1300403-ATS-B01-GF-15-ICT-VSS-SD-00 | Ground Floor Video Survelliance System Plan Part-15 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
940 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | 00 | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B01-00-00-ICT-VSS-SD-00 | Local Area Video Survelliance System Plan | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
941 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-00-ICT-VSS-SD-00 | First Floor Video Survelliance Overall System Plan (Departure Level) | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
942 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-01-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-01 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
943 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-02-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-02 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
944 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-03-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-03 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
945 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-04-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-04 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
946 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-05-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-05 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
947 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-06-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-06 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
948 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-07-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-07 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
949 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-08-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-08 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
950 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-09-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-09 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
951 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-10-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-10 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
952 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-11-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-11 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
953 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-12-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-12 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
954 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-13-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-13 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
955 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-14-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-14 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
956 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | VSS | SD | 00 | 1300403-ATS-B01-FF-15-ICT-VSS-SD-00 | First Floor Video Survelliance System Plan Part-15 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
957 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance Overall System Plan | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
958 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 01 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-01-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-01 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
959 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-02 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
960 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-03 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
961 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | ;04 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-;04-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-04 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
962 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | ;05 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-;05-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-05 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
963 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-06 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
964 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-07 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
965 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | ;08 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-;08-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-08 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
966 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | ;09 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-;09-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-09 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
967 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-10 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
968 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-11 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
969 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-12-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-12 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
970 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-13-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-13 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
971 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-14-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-14 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
972 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | VSS | SD | 00 | 1300403-ATS-B01-MZ-15-ICT-VSS-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-15 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- | Category 2 | FOV Details have been provided to raise RFC
973 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | 00 | 00 | ICT | WAP | SD | 00 | 1300403-ATS-B01-00-00-ICT-WAP-SD-00 | Locker Area Wireless Lan Communication System Plan | 2025-06-30 | 4 | --- | 00 | 2025-07-26 | ATLS-004-SD-ICT-00081-R00 | Code 2 | 30-Jul-25 | ATV-1300000403-SDS-ICT-00077-R00 | Code 2 |  | ATLS-004-SD-ICT-00081-R00 | 2025-07-26 | ATV-1300000403-SDS-ICT-00077-R00 | 2025-07-27 | ATV-1300000403-SDS-ICT-00077-R00 | --- | 30-Jul-25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
974 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-00-ICT-WAP-SD-00 | First Floor Wireless Lan Communication Overall System Plan (Departure Level) | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
975 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-01-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-01 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
976 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-02-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-02 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
977 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-03-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-03 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
978 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-04-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-04 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
979 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-05-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-05 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
980 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-06-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-06 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
981 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-07-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-07 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
982 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-08-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-08 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
983 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-09-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-09 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
984 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-10-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-10 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
985 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-11-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-11 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
986 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-12-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-12 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
987 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-13-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-13 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
988 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-14-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-14 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
989 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | WAP | SD | 00 | 1300403-ATS-B01-FF-15-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-15 | 2025-06-30 | 8 | --- | 00 | 2025-06-25 | ATLS-004-SD-ICT-00074-R00 | Code 2 | 03 Jul 25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 |  | ATLS-004-SD-ICT-00074-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | 2025-06-25 | ATV-1300000403-SDS-ICT-00063-R00 | Code 2 | 03 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
990 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | WAP | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication Overall System Plan | 2025-06-30 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00082-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00082-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00081-R00 | 2025-07-29 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
991 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | WAP | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication System Plan Part-06 | 2025-06-30 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00082-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00082-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00081-R00 | 2025-07-29 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
992 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | WAP | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication System Plan Part-07 | 2025-06-30 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00082-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00082-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00081-R00 | 2025-07-29 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
993 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | WAP | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication System Plan Part-10 | 2025-06-30 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00082-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00082-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00081-R00 | 2025-07-29 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
994 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | WAP | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication System Plan Part-11 | 2025-06-30 | 7 | --- | 00 | 2025-07-29 | ATLS-004-SD-ICT-00082-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00082-R00 | 2025-07-29 | ATV-1300000403-SDS-ICT-00081-R00 | 2025-07-29 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
995 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-01-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-01 | 2025-08-03 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00116-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00116-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
996 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 09 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-09-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-09 | 2025-08-03 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00116-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00116-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
997 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | DAT | SD | 00 | 1300403-ATS-B01-BF-12-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-12 | 2025-08-03 | 1 | #VALUE! | 00 | 2025-08-04 | ATLS-004-SD-ICT-00116-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00116-R00 | 2025-08-04 |  |  |  | UR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
998 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network Overall System Plan (Arrival Level) | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
999 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-01-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-01 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1000 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-02-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-02 | 2025-08-09 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1001 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-03-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-03 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1002 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 04 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-04-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-04 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1003 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 05 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-05-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-05 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1004 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 06 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-06-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-06 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1005 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 07 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-07-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-07 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1006 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 08 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-08-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-08 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1007 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 09 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-09-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-09 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1008 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-10-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-10 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1009 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-11-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-11 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1010 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-12-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-12 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1011 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-13-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-13 | 2025-08-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1012 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-14-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-14 | 2025-08-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1013 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | DAT | SD | 00 | 1300403-ATS-B01-GF-15-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-15 | 2025-08-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1014 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | 00 | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B01-00-00-ICT-DAT-SD-00 | Locker Area Data Network System Plan | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1015 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-00-ICT-DAT-SD-00 | First Floor Data Network Overall System Plan (Departure Level) | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1016 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 01 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-01-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-01 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1017 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-02-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-02 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1018 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-03-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-03 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1019 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 04 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-04-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-04 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1020 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 05 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-05-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-05 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1021 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 06 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-06-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-06 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1022 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-07-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-07 | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1023 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 08 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-08-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-08 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1024 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 09 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-09-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-09 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1025 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-10-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-10 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1026 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-11-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-11 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1027 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-12-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-12 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1028 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-13-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-13 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1029 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-14-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-14 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1030 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | DAT | SD | 00 | 1300403-ATS-B01-FF-15-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-15 | 2025-08-05 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1031 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 00 | ICT | DAT | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-DAT-SD-00 | Mezzanine Floor Data Network Overall System Plan | 2025-08-28 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1032 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 02 | ICT | DAT | SD | 00 | 1300403-ATS-B01-MZ-02-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-02 | 2025-08-28 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1033 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 03 | ICT | DAT | SD | 00 | 1300403-ATS-B01-MZ-03-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-03 | 2025-08-28 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1034 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 06 | ICT | DAT | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-06 | 2025-08-28 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1035 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 07 | ICT | DAT | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-07 | 2025-08-28 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1036 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 00 | 1300403-ATS-B0X-00-00-ICT-STL-SD-00 | Master Site Plan Telecommunication Works | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1037 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 01 | 1300403-ATS-B0X-00-00-ICT-STL-SD-01 | Partial Site Telecommunication Plan (Part1) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1038 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 02 | 1300403-ATS-B0X-00-00-ICT-STL-SD-02 | Partial Site Telecommunication Plan (Part2) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1039 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 03 | 1300403-ATS-B0X-00-00-ICT-STL-SD-03 | Partial Site Telecommunication Plan (Part3) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1040 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 04 | 1300403-ATS-B0X-00-00-ICT-STL-SD-04 | Partial Site Telecommunication Plan (Part4) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1041 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 05 | 1300403-ATS-B0X-00-00-ICT-STL-SD-05 | Partial Site Telecommunication Plan (Part5) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1042 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 06 | 1300403-ATS-B0X-00-00-ICT-STL-SD-06 | Partial Site Telecommunication Plan (Part6) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1043 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 07 | 1300403-ATS-B0X-00-00-ICT-STL-SD-07 | Partial Site Telecommunication Plan (Part7) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1044 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 08 | 1300403-ATS-B0X-00-00-ICT-STL-SD-08 | Partial Site Telecommunication Plan (Part8) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1045 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 09 | 1300403-ATS-B0X-00-00-ICT-STL-SD-09 | Partial Site Telecommunication Plan (Part9) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1046 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 10 | 1300403-ATS-B0X-00-00-ICT-STL-SD-10 | Partial Site Telecommunication Plan (Part10) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1047 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 11 | 1300403-ATS-B0X-00-00-ICT-STL-SD-11 | Partial Site Telecommunication Plan (Part11) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1048 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 12 | 1300403-ATS-B0X-00-00-ICT-STL-SD-12 | Partial Site Telecommunication Plan (Part12) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1049 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 13 | 1300403-ATS-B0X-00-00-ICT-STL-SD-13 | Partial Site Telecommunication Plan (Part13) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1050 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 14 | 1300403-ATS-B0X-00-00-ICT-STL-SD-14 | Partial Site Telecommunication Plan (Part14) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1051 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 15 | 1300403-ATS-B0X-00-00-ICT-STL-SD-15 | Partial Site Telecommunication Plan (Part15) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1052 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 16 | 1300403-ATS-B0X-00-00-ICT-STL-SD-16 | Partial Site Telecommunication Plan (Part16) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1053 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 17 | 1300403-ATS-B0X-00-00-ICT-STL-SD-17 | Partial Site Telecommunication Plan (Part17) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1054 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 18 | 1300403-ATS-B0X-00-00-ICT-STL-SD-18 | Partial Site Telecommunication Plan (Part18) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1055 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 19 | 1300403-ATS-B0X-00-00-ICT-STL-SD-19 | Partial Site Telecommunication Plan (Part19) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1056 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 20 | 1300403-ATS-B0X-00-00-ICT-STL-SD-20 | Partial Site Telecommunication Plan (Part20) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1057 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 21 | 1300403-ATS-B0X-00-00-ICT-STL-SD-21 | Partial Site Telecommunication Plan (Part21) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1058 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 22 | 1300403-ATS-B0X-00-00-ICT-STL-SD-22 | Partial Site Telecommunication Plan (Part22) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1059 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 23 | 1300403-ATS-B0X-00-00-ICT-STL-SD-23 | Partial Site Telecommunication Plan (Part23) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1060 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 24 | 1300403-ATS-B0X-00-00-ICT-STL-SD-24 | Partial Site Telecommunication Plan (Part24) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1061 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 25 | 1300403-ATS-B0X-00-00-ICT-STL-SD-25 | Partial Site Telecommunication Plan (Part25) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1062 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 26 | 1300403-ATS-B0X-00-00-ICT-STL-SD-26 | Partial Site Telecommunication Plan (Part26) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1063 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 27 | 1300403-ATS-B0X-00-00-ICT-STL-SD-27 | Partial Site Telecommunication Plan (Part27) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1064 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 28 | 1300403-ATS-B0X-00-00-ICT-STL-SD-28 | Partial Site Telecommunication Plan (Part28) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1065 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 29 | 1300403-ATS-B0X-00-00-ICT-STL-SD-29 | Partial Site Telecommunication Plan (Part29) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1066 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 30 | 1300403-ATS-B0X-00-00-ICT-STL-SD-30 | Partial Site Telecommunication Plan (Part30) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1067 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 31 | 1300403-ATS-B0X-00-00-ICT-STL-SD-31 | Partial Site Telecommunication Plan (Part31) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1068 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 32 | 1300403-ATS-B0X-00-00-ICT-STL-SD-32 | Site Plan Telecommunication Works ( For Departure Level ) | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1069 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 33 | 1300403-ATS-B0X-00-00-ICT-STL-SD-33 | Site Plan Telecommunication Works ( For Departure Level ) Part 01 | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1070 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 34 | 1300403-ATS-B0X-00-00-ICT-STL-SD-34 | Site Plan Telecommunication Works ( For Departure Level ) Part 02 | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1071 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 35 | 1300403-ATS-B0X-00-00-ICT-STL-SD-35 | Site Plan Telecommunication Works ( For Departure Level ) Part 03 | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1072 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 00 | ICT | STL | SD | 36 | 1300403-ATS-B0X-00-00-ICT-STL-SD-36 | Site Plan Telecommunication Works ( For Departure Level ) Part 04 | 2025-08-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1073 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 14 | 1300403-ATS-00-00-00-ICT-TYP-SD-14 | ACCESS CONTROL SYSTEM SINGLE LINE DIAGRAM FOR BUILDING 05 | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1074 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 15 | 1300403-ATS-00-00-00-ICT-TYP-SD-15 | Typical for DTAS | 2025-09-01 | #VALUE! | #VALUE! | 00 | 2025-07-18 | ATLS-004-SD-ICT-00108-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00108-R00 | 2025-07-18 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1075 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 16 | 1300403-ATS-00-00-00-ICT-TYP-SD-16 | Typical for ECS | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1076 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 17 | 1300403-ATS-00-00-00-ICT-TYP-SD-17 | INSTALLATION DETAIL FOR IPTV | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1077 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 18 | 1300403-ATS-00-00-00-ICT-TYP-SD-18 | INSTALLATION DETAIL FOR MASTER CLOCK | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1078 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 19 | 1300403-ATS-00-00-00-ICT-TYP-SD-19 | SIGNAGE TYP 01 | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1079 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 20 | 1300403-ATS-00-00-00-ICT-TYP-SD-20 | SIGNAGE TYP 02 | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1080 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 21 | 1300403-ATS-00-00-00-ICT-TYP-SD-21 | SIGNAGE TYP 03 | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1081 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 22 | 1300403-ATS-00-00-00-ICT-TYP-SD-22 | SIGNAGE TYP 04 | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1082 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 23 | 1300403-ATS-00-00-00-ICT-TYP-SD-23 | ICT RM -B0001BS-047-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1083 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 24 | 1300403-ATS-00-00-00-ICT-TYP-SD-24 | MMR -B0001BS-025-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1084 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 25 | 1300403-ATS-00-00-00-ICT-TYP-SD-25 | ICT RM -B0001BS-058-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1085 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 26 | 1300403-ATS-00-00-00-ICT-TYP-SD-26 | ICT RM / SERVIES CORRIDOR -B0001BS-105/155-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1086 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 27 | 1300403-ATS-00-00-00-ICT-TYP-SD-27 | MMR -B0001BS-110-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1087 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 28 | 1300403-ATS-00-00-00-ICT-TYP-SD-28 | MTR-B0001BS-140-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1088 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 29 | 1300403-ATS-00-00-00-ICT-TYP-SD-29 | ICT RM -B0001BS-116-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1089 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 30 | 1300403-ATS-00-00-00-ICT-TYP-SD-30 | ICT RM-B0001GR-190-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1090 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 31 | 1300403-ATS-00-00-00-ICT-TYP-SD-31 | DAS/TETRA RM-B0001GR-450-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1091 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 32 | 1300403-ATS-00-00-00-ICT-TYP-SD-32 | ICT RM-B0001GR-172-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1092 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 33 | 1300403-ATS-00-00-00-ICT-TYP-SD-33 | SERVER RM -B0001GR-361-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1093 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 34 | 1300403-ATS-00-00-00-ICT-TYP-SD-34 | ICT RM -B0001GR-363-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1094 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 35 | 1300403-ATS-00-00-00-ICT-TYP-SD-35 | ICT RM -B0001GR-353-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1095 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 36 | 1300403-ATS-00-00-00-ICT-TYP-SD-36 | SERVER RM -B0001GR-218-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1096 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 37 | 1300403-ATS-00-00-00-ICT-TYP-SD-37 | ICT RM-B0001GR-216-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1097 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 38 | 1300403-ATS-00-00-00-ICT-TYP-SD-38 | ICT RM-B0001GR-136-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1098 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 39 | 1300403-ATS-00-00-00-ICT-TYP-SD-39 | ICT RM-B0001GR-155-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1099 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 40 | 1300403-ATS-00-00-00-ICT-TYP-SD-40 | ICT RM-B0001GR-097-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1100 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 41 | 1300403-ATS-00-00-00-ICT-TYP-SD-41 | ICT RM-B0001GR-028-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1101 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 42 | 1300403-ATS-00-00-00-ICT-TYP-SD-42 | ICT RM-B0001GR-014-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1102 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 43 | 1300403-ATS-00-00-00-ICT-TYP-SD-43 | ELEC RM-B0001GR-233-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1103 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 44 | 1300403-ATS-00-00-00-ICT-TYP-SD-44 | ICT RM -B0001GR-295-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1104 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 45 | 1300403-ATS-00-00-00-ICT-TYP-SD-45 | ICT RM-B0001 01-262-264-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1105 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 46 | 1300403-ATS-00-00-00-ICT-TYP-SD-46 | ICT RM-B0001 01-106-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1106 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 47 | 1300403-ATS-00-00-00-ICT-TYP-SD-47 | ICT RM-B0001 01-205-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1107 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 48 | 1300403-ATS-00-00-00-ICT-TYP-SD-48 | ICT RM-B0001 01-286-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1108 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 49 | 1300403-ATS-00-00-00-ICT-TYP-SD-49 | ICT RM-B0001 01-130-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1109 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 50 | 1300403-ATS-00-00-00-ICT-TYP-SD-50 | ICT RM-B000 1MZ-009-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1110 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 51 | 1300403-ATS-00-00-00-ICT-TYP-SD-51 | ICT RM-B000 1MZ-049-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1111 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 52 | 1300403-ATS-00-00-00-ICT-TYP-SD-52 | ICT RM-B000 1MZ-100-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-01 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1112 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 53 | 1300403-ATS-00-00-00-ICT-TYP-SD-53 | ICT RM-B000 1MZ-123-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1113 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 54 | 1300403-ATS-00-00-00-ICT-TYP-SD-54 | LC CLOSET -B0002-GR-108-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1114 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 55 | 1300403-ATS-00-00-00-ICT-TYP-SD-55 | ICT RM-B0002-GR-030-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1115 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 56 | 1300403-ATS-00-00-00-ICT-TYP-SD-56 | TELECOM RM-B0002-GR-025-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1116 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 57 | 1300403-ATS-00-00-00-ICT-TYP-SD-57 | ICT RM-B0002-01-021-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1117 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 58 | 1300403-ATS-00-00-00-ICT-TYP-SD-58 | LC ROOM-B0002-01-002-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1118 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 59 | 1300403-ATS-00-00-00-ICT-TYP-SD-59 | LC ROOM-B0003 BS-007-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1119 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 60 | 1300403-ATS-00-00-00-ICT-TYP-SD-60 | COMM.CLOSET-B0003 GR-002-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1120 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 61 | 1300403-ATS-00-00-00-ICT-TYP-SD-61 | COMM. ROOM-B0004 BS-011-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1121 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 62 | 1300403-ATS-00-00-00-ICT-TYP-SD-62 | COMM. ROOM-B0004 BS-012-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1122 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 63 | 1300403-ATS-00-00-00-ICT-TYP-SD-63 | COMM. ROOM-B0004 GD-010-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1123 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 64 | 1300403-ATS-00-00-00-ICT-TYP-SD-64 | COMM. ROOM-B0004 GD-009-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1124 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 65 | 1300403-ATS-00-00-00-ICT-TYP-SD-65 | COMM.ROOM-B0005 BS-032-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1125 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 66 | 1300403-ATS-00-00-00-ICT-TYP-SD-66 | COMM.ROOM-B0005 BS-026-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1126 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 67 | 1300403-ATS-00-00-00-ICT-TYP-SD-67 | TELEPHONE EQUIPMENT-B0005 BS-004-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1127 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 68 | 1300403-ATS-00-00-00-ICT-TYP-SD-68 | ICT RM-B0006 GR-004-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1128 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 69 | 1300403-ATS-00-00-00-ICT-TYP-SD-69 | COMM. ROOM-B0007-GR-006-SCR ROOM DETAILS AND RACK LAYOUT | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1129 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 70 | 1300403-ATS-00-00-00-ICT-TYP-SD-70 | TETRA DAS INDOOR OMNI ANTENNA TYPICAL INSTALLATION DETAILS (CEILING MOUNTED) | 2025-09-03 | 8 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00111-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00111-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00083-R00 | 2025-07-31 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1130 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 71 | 1300403-ATS-00-00-00-ICT-TYP-SD-71 | Telecommunication Cable Tray/Containment Typical Installation Details ( SHEET-01) | 2025-08-12 | 10 | --- | 00 | 2025-07-03 | ATLS-004-SD-ICT-00092-R00 | Code 2 | 13 Jul 25 | ATV-1300000403-SDS-ICT-00073-R00 | Code 2 |  | ATLS-004-SD-ICT-00092-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00073-R00 | 2025-07-07 | ATV-1300000403-SDS-ICT-00073-R00 | Code 2 | 13 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1131 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 72 | 1300403-ATS-00-00-00-ICT-TYP-SD-72 | Telecommunication Cable Tray/Containment Typical Installation Details ( SHEET-02) | 2025-08-12 | 10 | --- | 00 | 2025-07-03 | ATLS-004-SD-ICT-00092-R00 | Code 2 | 13 Jul 25 | ATV-1300000403-SDS-ICT-00073-R00 | Code 2 |  | ATLS-004-SD-ICT-00092-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00073-R00 | 2025-07-07 | ATV-1300000403-SDS-ICT-00073-R00 | Code 2 | 13 Jul 25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1132 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 73 | 1300403-ATS-00-00-00-ICT-TYP-SD-73 | Panoramic Camera Typical External Pole and Enclosure Installation Details | 2025-08-12 | 6 | --- | 00 | 2025-07-23 | ATLS-004-SD-ICT-00104-R00 | Code 2 | 29-Jul-25 | ATV-1300000403-SDS-ICT-00076-R00 | Code 2 |  | ATLS-004-SD-ICT-00104-R00 | 2025-07-23 | ATV-1300000403-SDS-ICT-00076-R00 | 2025-07-24 | ATV-1300000403-SDS-ICT-00076-R00 | --- | 29-Jul-25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1133 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 74 | 1300403-ATS-00-00-00-ICT-TYP-SD-74 | Bullet Camera Typical External Pole and Enclosure Installation Details | 2025-08-12 | 6 | --- | 00 | 2025-07-23 | ATLS-004-SD-ICT-00104-R00 | Code 2 | 29-Jul-25 | ATV-1300000403-SDS-ICT-00076-R00 | Code 2 |  | ATLS-004-SD-ICT-00104-R00 | 2025-07-23 | ATV-1300000403-SDS-ICT-00076-R00 | 2025-07-24 | ATV-1300000403-SDS-ICT-00076-R00 | --- | 29-Jul-25 | Code 2 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1134 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 75 | 1300403-ATS-00-00-00-ICT-TYP-SD-75 | Telecommunications Typical Conduit Metal Box Installation Details | 2025-08-12 | 5 | --- | 00 | 2025-07-23 | ATLS-004-SD-ICT-00109-R00 | Code 1 | 28 Jul 25 | ATV-1300000403-SDS-ICT-00075-R00 | Code 1 |  | ATLS-004-SD-ICT-00109-R00 | 2025-07-23 | ATV-1300000403-SDS-ICT-00075-R00 | 2025-07-24 | ATV-1300000403-SDS-ICT-00075-R00 | Code 1 | 28 Jul 25 | Code 1 | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1135 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 76 | 1300403-ATS-00-00-00-ICT-TYP-SD-76 | TETRA DAS INDOOR OMNI ANTENNA TYPICAL INSTALLATION DETAILS (SUSPENDED SLAB SOFFIT) | 2025-09-03 | 8 | --- | 00 | 2025-07-28 | ATLS-004-SD-ICT-00111-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00111-R00 | 2025-07-28 | ATV-1300000403-SDS-ICT-00083-R00 | 2025-07-31 |  | --- |  | UR (DAR) | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1136 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 77 | 1300403-ATS-00-00-00-ICT-TYP-SD-77 | DOME CAMERA TYPICAL INSTALLATION DETAILS PART-01 | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1137 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 78 | 1300403-ATS-00-00-00-ICT-TYP-SD-78 | DOME CAMERA TYPICAL INSTALLATION DETAILS PART-02 | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1138 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 79 | 1300403-ATS-00-00-00-ICT-TYP-SD-79 | BULLET CAMERA TYPICAL INSTALLATION DETAILS PART-01 | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1139 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 80 | 1300403-ATS-00-00-00-ICT-TYP-SD-80 | BULLET CAMERA TYPICAL INSTALLATION DETAILS PART-02 | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1140 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 81 | 1300403-ATS-00-00-00-ICT-TYP-SD-81 | ACCESS CONTROL AIO TYPICAL INSTALLATION DETAIL | 2025-09-03 | #VALUE! | #VALUE! | 00 | 2025-07-30 | ATLS-004-SD-ICT-00113-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00113-R00 | 2025-07-30 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1141 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 82 | 1300403-ATS-00-00-00-ICT-TYP-SD-82 | ACCESS CONTROL AIO2 TYPICAL INSTALLATION DETAIL | 2025-09-03 | #VALUE! | #VALUE! | 00 | 2025-07-30 | ATLS-004-SD-ICT-00113-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00113-R00 | 2025-07-30 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1142 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 83 | 1300403-ATS-00-00-00-ICT-TYP-SD-83 | ACCESS CONTROL AIO3 TYPICAL INSTALLATION DETAIL | 2025-09-03 | #VALUE! | #VALUE! | 00 | 2025-07-30 | ATLS-004-SD-ICT-00113-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00113-R00 | 2025-07-30 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1143 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 84 | 1300403-ATS-00-00-00-ICT-TYP-SD-84 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1144 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 85 | 1300403-ATS-00-00-00-ICT-TYP-SD-85 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1145 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 86 | 1300403-ATS-00-00-00-ICT-TYP-SD-86 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1146 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 87 | 1300403-ATS-00-00-00-ICT-TYP-SD-87 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1147 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 88 | 1300403-ATS-00-00-00-ICT-TYP-SD-88 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1148 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 89 | 1300403-ATS-00-00-00-ICT-TYP-SD-89 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1149 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 90 | 1300403-ATS-00-00-00-ICT-TYP-SD-90 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1150 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 91 | 1300403-ATS-00-00-00-ICT-TYP-SD-91 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1151 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 92 | 1300403-ATS-00-00-00-ICT-TYP-SD-92 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1152 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 93 | 1300403-ATS-00-00-00-ICT-TYP-SD-93 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1153 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 94 | 1300403-ATS-00-00-00-ICT-TYP-SD-94 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1154 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 95 | 1300403-ATS-00-00-00-ICT-TYP-SD-95 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1155 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 96 | 1300403-ATS-00-00-00-ICT-TYP-SD-96 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1156 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 00 | ICT | TYP | SD | 97 | 1300403-ATS-00-00-00-ICT-TYP-SD-97 | Typical Drawings | 2025-09-03 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1157 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | XX | ICT | SCH | SD | 01 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-01 | Antenna Schedule For Tetra System Sheet-01 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1158 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | XX | ICT | SCH | SD | 05 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-05 | Antenna Schedule For Tetra System Sheet-02 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1159 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | XX | ICT | SCH | SD | 06 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-06 | Tetra Remote Units And Hubs Sheet-01 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1160 | GSM-DAS & TETRA | TETRA ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 02 | ICT | DET | SD | 00 | 1300403-ATS-BXX-XX-02-ICT-DET-SD-00 | Installation And Mounting Details Sheet-01 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1161 | GSM-DAS & TETRA | TETRA ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 03 | ICT | DET | SD | 00 | 1300403-ATS-BXX-XX-03-ICT-DET-SD-00 | Installation And Mounting Details Sheet-02 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1162 | GSM-DAS & TETRA | TETRA ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 04 | ICT | DET | SD | 00 | 1300403-ATS-BXX-XX-04-ICT-DET-SD-00 | Installation And Mounting Details Sheet-03 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1163 | GSM-DAS & TETRA | TETRA ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 00 | ICT | DET | SD | 00 | 1300403-ATS-BXX-XX-00-ICT-DET-SD-00 | Installation And Mounting Details Sheet-04 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1164 | GSM-DAS & TETRA | TETRA ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 01 | ICT | DET | SD | 00 | 1300403-ATS-BXX-XX-01-ICT-DET-SD-00 | Installation And Mounting Details Sheet-01 | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1165 | GSM-DAS & TETRA | TETRA ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 02 | ICT | DET | SD | 01 | 1300403-ATS-BXX-XX-02-ICT-DET-SD-01 | Gsm & Tetra System Room Layout(B001-Gr-450) | 2025-09-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1166 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-00-ICT-TET-SD-00 | B0001 - Terminal Basement Floor Tetra Das Prediction Heatmap | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1167 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B01-GF-00-ICT-TET-SD-01 | B0001 - Terminal Ground Floor Tetra Das Prediction Heatmap | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1168 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 00 | ICT | TET | SD | 01 | 1300403-ATS-B01-MZ-00-ICT-TET-SD-01 | B0001 - Terminal Mezzanine Floor Tetra Das Prediction Heatmap | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1169 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B01-FF-00-ICT-TET-SD-01 | B0001 - Terminal First Floor Tetra Das Prediction Heatmap | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1170 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B02-GF-00-ICT-TET-SD-01 | B0002 - Group Check In Ground Floor Tetra Das Prediction Heatmap Over All Layout | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1171 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B02-FF-00-ICT-TET-SD-01 | B0002 - Group Check In First Floor Tetra Das Prediction Heatmap Over All Layout | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1172 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | BF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B03-BF-00-ICT-TET-SD-01 | B0003 - Mosque Basement Floor Tetra Das Prediction Heatmap | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1173 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B03-GF-00-ICT-TET-SD-01 | B0003 - Mosque Ground Floor Tetra Das Prediction Heatmap Over All Layout | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1174 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B03-FF-00-ICT-TET-SD-01 | B0003 - Mosque First Floor Tetra Das Prediction Heatmap Over All Layout | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1175 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | LF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B04-LF-00-ICT-TET-SD-01 | B0004 - West Parking Lower Level Tetra Das Prediction Heatmap Over All Layout | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1176 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | UF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B04-UF-00-ICT-TET-SD-01 | B0004 - West Parking Upper Level Tetra Das Prediction Heatmap Over All Layout | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1177 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | LF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B05-LF-00-ICT-TET-SD-01 | B0005 - East Parking Lower Level Tetra Das Prediction Heatmap Over All Layout | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1178 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B06 | GF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B06-GF-00-ICT-TET-SD-01 | B0006 - Baggage Handling Area Tetra Das Prediction Heatmap | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1179 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B07 | GF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B07-GF-00-ICT-TET-SD-01 | B0007 - Hajj Building Tetra Das Prediction Heatmap | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1180 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 00 | ICT | TET | SD | 01 | 1300403-ATS-B01-BF-00-ICT-TET-SD-01 | Terminal Basement Floor Tetra Das System Overall Plan |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1181 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-01-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-01 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1182 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-02-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-02 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1183 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-03-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-03 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1184 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 04 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-04-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-04 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1185 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 05 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-05-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-05 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1186 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 06 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-06-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-06 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1187 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 07 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-07-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-07 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1188 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 08 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-08-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-08 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1189 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 09 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-09-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-09 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1190 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 10 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-10-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-10 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1191 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 11 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-11-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-11 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1192 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 12 | ICT | TET | SD | 00 | 1300403-ATS-B01-BF-12-ICT-TET-SD-00 | Terminal Basement Floor Tetra Das System PART-12 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00077-R01 | UR (ATJV) | 8 Jul 25 | ATV-1300000403-SDS-ICT-00071-R01 | UR (ATJV) |  | ATLS-004-SD-ICT-00077-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00071-R00 | Code 3 | 8 Jul 25 | Code 3 | ATLS-004-SD-ICT-00077-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00071-R01 |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1193 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-00-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System Overall Plan |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1194 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-01-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-01 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1195 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-02-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-02 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1196 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-03-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-03 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1197 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 04 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-04-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-04 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1198 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 05 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-05-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-05 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1199 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 06 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-06-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-06 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1200 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 07 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-07-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-07 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1201 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 08 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-08-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-08 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1202 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 09 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-09-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-09 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1203 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 10 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-10-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-10 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1204 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 11 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-11-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-11 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1205 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 12 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-12-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-12 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1206 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 13 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-13-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-13 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1207 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 14 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-14-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-14 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1208 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 15 | ICT | TET | SD | 00 | 1300403-ATS-B01-GF-15-ICT-TET-SD-00 | Terminal Ground Floor Tetra Das System PART-15 |  | 7 | --- | 01 | 2025-07-29 | ATLS-004-SD-ICT-00090-R01 | UR (DAR) | 10 Jul 25 | ATV-1300000403-SDS-ICT-00072-R01 | UR (DAR) |  | ATLS-004-SD-ICT-00090-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | 2025-07-03 | ATV-1300000403-SDS-ICT-00072-R00 | Code 3 | 10 Jul 25 | Code 3 | ATLS-004-SD-ICT-00090-R01 | 2025-07-29 | ATV-1300000403-SDS-ICT-00072-R01 | 2025-07-31 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1209 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 00 | ICT | TET | SD | 00 | 1300403-ATS-B01-MZ-00-ICT-TET-SD-00 | TERMINAL MEZZANINE FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00094-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00094-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1210 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 06 | ICT | TET | SD | 00 | 1300403-ATS-B01-MZ-06-ICT-TET-SD-00 | TERMINAL MEZZANINE FLOOR TETRA DAS SYSTEM PLAN PART-06 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00094-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00094-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1211 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 07 | ICT | TET | SD | 00 | 1300403-ATS-B01-MZ-07-ICT-TET-SD-00 | TERMINAL MEZZANINE FLOOR TETRA DAS SYSTEM PLAN PART-07 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00094-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00094-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1212 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 10 | ICT | TET | SD | 00 | 1300403-ATS-B01-MZ-10-ICT-TET-SD-00 | TERMINAL MEZZANINE FLOOR TETRA DAS SYSTEM PLAN PART-10 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00094-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00094-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1213 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 11 | ICT | TET | SD | 00 | 1300403-ATS-B01-MZ-11-ICT-TET-SD-00 | TERMINAL MEZZANINE FLOOR TETRA DAS SYSTEM PLAN PART-11 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00094-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00094-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1214 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-00-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Overall Plan | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1215 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-01-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-01 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1216 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-02-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-02 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1217 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-03-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-03 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1218 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 04 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-04-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-04 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1219 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 05 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-05-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-05 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1220 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 06 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-06-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-06 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1221 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 07 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-07-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-07 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1222 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 08 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-08-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-08 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1223 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 09 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-09-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-09 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1224 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 10 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-10-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-10 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1225 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 11 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-11-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-11 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1226 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 12 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-12-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-12 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1227 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 13 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-13-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-13 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1228 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 14 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-14-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-14 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1229 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 15 | ICT | TET | SD | 00 | 1300403-ATS-B01-FF-15-ICT-TET-SD-00 | Terminal First Floor Tetra Das System Plan PART-15 |  | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00093-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00093-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1230 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B02-GF-00-ICT-TET-SD-00 | GROUND FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00095-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00095-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1231 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B02-GF-01-ICT-TET-SD-00 | GROUND FLOOR TETRA DAS SYSTEM PLAN PART - 01 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00095-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00095-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1232 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B02-GF-02-ICT-TET-SD-00 | GROUND FLOOR TETRA DAS SYSTEM PLAN PART - 02 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00095-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00095-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1233 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B02-GF-03-ICT-TET-SD-00 | GROUND FLOOR TETRA DAS SYSTEM PLAN PART - 03 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00095-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00095-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1234 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B02-FF-00-ICT-TET-SD-00 | FIRST FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00096-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00096-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1235 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B02-FF-01-ICT-TET-SD-00 | FIRST FLOOR TETRA DAS SYSTEM PLAN PART-01 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00096-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00096-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1236 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B02-FF-02-ICT-TET-SD-00 | FIRST FLOOR TETRA DAS SYSTEM PLAN PART-02 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00096-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00096-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1237 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B02-FF-03-ICT-TET-SD-00 | FIRST FLOOR TETRA DAS SYSTEM PLAN PART-03 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00096-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00096-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1238 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | BF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B03-BF-00-ICT-TET-SD-00 | BASEMENT FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00097-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00097-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1239 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B03-GF-00-ICT-TET-SD-00 | GROUND FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00097-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00097-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1240 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B03-FF-00-ICT-TET-SD-00 | FIRST FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00097-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00097-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1241 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | LF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B04-LF-00-ICT-TET-SD-00 | LOWER LEVEL FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1242 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | LF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B04-LF-01-ICT-TET-SD-00 | LOWER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 01 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1243 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | LF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B04-LF-02-ICT-TET-SD-00 | LOWER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 02 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1244 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | LF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B04-LF-03-ICT-TET-SD-00 | LOWER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 03 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1245 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | LF | 04 | ICT | TET | SD | 00 | 1300403-ATS-B04-LF-04-ICT-TET-SD-00 | LOWER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 04 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1246 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | UF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B04-UF-00-ICT-TET-SD-00 | UPPER LEVEL FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1247 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | UF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B04-UF-01-ICT-TET-SD-00 | UPPER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 01 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1248 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | UF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B04-UF-02-ICT-TET-SD-00 | UPPER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 02 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1249 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | UF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B04-UF-03-ICT-TET-SD-00 | UPPER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 03 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1250 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | UF | 04 | ICT | TET | SD | 00 | 1300403-ATS-B04-UF-04-ICT-TET-SD-00 | UPPER LEVEL FLOOR TETRA DAS SYSTEM PLAN PART - 04 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00098-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00098-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1251 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | LF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B05-LF-00-ICT-TET-SD-00 | LOWER FLOOR OVERALL PLAN AT LEVEL - 1.5 AND LEVEL- 5.0M TETRA DAS SYSTEM PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00099-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00099-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1252 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | LF | 01 | ICT | TET | SD | 00 | 1300403-ATS-B05-LF-01-ICT-TET-SD-00 | LOWER FLOOR AT LEVEL - 1.5 AND LEVEL- 5.0M TETRA DAS SYSTEM PLAN PART - 01 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00099-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00099-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1253 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | LF | 02 | ICT | TET | SD | 00 | 1300403-ATS-B05-LF-02-ICT-TET-SD-00 | LOWER FLOOR AT LEVEL - 1.5 AND LEVEL- 5.0M TETRA DAS SYSTEM PLAN PART - 02 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00099-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00099-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1254 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | LF | 03 | ICT | TET | SD | 00 | 1300403-ATS-B05-LF-03-ICT-TET-SD-00 | LOWER FLOOR AT LEVEL - 1.5 AND LEVEL- 5.0M TETRA DAS SYSTEM PLAN PART - 03 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00099-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00099-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1255 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | LF | 04 | ICT | TET | SD | 00 | 1300403-ATS-B05-LF-04-ICT-TET-SD-00 | LOWER FLOOR AT LEVEL - 1.5 AND LEVEL- 5.0M TETRA DAS SYSTEM PLAN PART - 04 | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00099-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00099-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1256 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B06 | GF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B06-GF-00-ICT-TET-SD-00 | B0006 - Baggage Handling Area Tetra Das Plan Layout | 2025-08-10 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1257 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B07 | GF | 00 | ICT | TET | SD | 00 | 1300403-ATS-B07-GF-00-ICT-TET-SD-00 | GROUND FLOOR TETRA DAS SYSTEM OVERALL PLAN | 2025-07-04 | #VALUE! | #VALUE! | 00 | 2025-08-01 | ATLS-004-SD-ICT-00100-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00100-R00 | 2025-08-01 |  |  |  | AR (ATJV) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1258 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 00 | ICT | SLD | SD | 07 | 1300403-ATS-BXX-XX-00-ICT-SLD-SD-07 | Single Line Diagram For Tetra System | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1259 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 00 | ICT | RCK | SD | 00 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-00 | Rack Elevation For Tetra System Sheet - 01 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1260 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 00 | ICT | RCK | SD | 01 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-01 | Rack Elevation For Tetra System Sheet - 02 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1261 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 00 | ICT | RCK | SD | 02 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-02 | Rack Elevation For Tetra System Sheet - 03 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1262 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 00 | ICT | RCK | SD | 03 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-03 | Rack Elevation For Tetra System Sheet - 04 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1263 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 00 | ICT | RCK | SD | 04 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-04 | Rack Elevation For Tetra System Sheet - 05 | 2025-08-15 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1264 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 00 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-00-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Overall System Plan (Arrival Level) |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1265 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 01 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-01-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-01 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1266 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 02 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-02-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-02 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1267 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 03 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-03-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-03 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1268 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 04 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-04-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-04 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1269 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 05 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-05-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-05 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1270 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 06 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-06-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-06 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1271 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 07 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-07-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-07 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1272 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 08 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-08-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-08 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1273 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 09 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-09-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-09 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1274 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 10 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-10-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-10 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1275 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 11 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-11-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-11 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1276 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 12 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-12-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-12 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1277 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 13 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-13-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-13 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1278 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 14 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-14-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-14 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1279 | ICT | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 1300403 | ATS | B01 | GF | 15 | ICT | BHS | SD | 00 | 1300403-ATS-B01-GF-15-ICT-BHS-SD-00 | Ground Floor Bhs And Customs Screening Network Infrastructure Plan PART-15 |  | #VALUE! | #VALUE! | 00 | 2025-07-21 | ATLS-004-SD-ICT-00080-R00 | RTN (AS) | --- |  | RTN (AS) |  | ATLS-004-SD-ICT-00080-R00 | 2025-07-21 |  |  |  | RTN (AS) |  | --- | [5 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---

## Dashboard
| Dashboard |  | 1279 | 809 | 63.25% |  | 470 |  | 1 | 563 | 0 | 0 | 0 | 65 | 78 | 55 | 47
|  |  | TOTAL QUANTITY | SUBMITTED |  |  | REV 0 TO GO |  | CODE 1 | CODE 2 | CODE 3 | CODE 4 | CODE 5 | AR (ATJV) | Return to Atlas By ATJV | UR with ATJV | UR with DAR
| 1172 |  |  | 732 |  |  | 440 |  | 1 | 563 | 0 | 0 | 0 | 17 | 78 | 42 | 31
ICT | ICT | ICT TECHNICAL ROOMS | 35 | 0 | 0% |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | FIRE ALARM SYSTEM | 93 | 36 | 38.71% |  | 57 |  | 0 | 0 | 0 | 0 | 0 | 5 | 15 | 16 | 0
ICT |  | DATA NETWORK SYSTEM | 79 | 37 | 46.84% |  | 42 |  | 0 | 27 | 0 | 0 | 0 | 2 | 4 | 4 | 0
ICT |  | IP TELEPHONE SYSTEM | 71 | 66 | 92.96% |  | 5 |  | 0 | 53 | 0 | 0 | 0 | 0 | 2 | 3 | 8
ICT |  | VIDEO SURVELLIANCE SYSTEM | 90 | 20 | 22.22% |  | 70 |  | 0 | 7 | 0 | 0 | 0 | 0 | 10 | 0 | 3
ICT |  | ACCESS CONTROL SYSTEM | 88 | 88 | 100% |  | 0 |  | 0 | 84 | 0 | 0 | 0 | 0 | 4 | 0 | 0
ICT |  | SINGLE LINE DIAGRAM | 54 | 0 | 0% |  | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | MASTER CLOCK SYSTEM | 70 | 70 | 100% |  | 0 |  | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | COMMUNICATION EQUIPMENT SYSTEM | 85 | 85 | 100% |  | 0 |  | 0 | 74 | 0 | 0 | 0 | 0 | 10 | 1 | 0
ICT |  | CONTAINMENT SYSTEM | 87 | 87 | 100% |  | 0 |  | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | SOUND MANAGEMENT SYSTEM | 70 | 3 | 4.286% |  | 67 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
ICT |  | WIRELESS LAN COMMUNICATION SYSTEM | 59 | 59 | 100% |  | 0 |  | 0 | 47 | 0 | 0 | 0 | 0 | 7 | 0 | 5
ICT |  | DISABLED TOILET ALARM SYSTEM | 25 | 25 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 18 | 0
ICT |  | BAGGAGE RECONCILIATION SYSTEM | 6 | 6 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
ICT |  | SIGNAGE SYSTEM | 40 | 40 | 100% |  | 0 |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | SITE TELECOMMUNICATION SYSTEM | 37 | 0 | 0% |  | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | IPTV SYSTEM | 57 | 57 | 100% |  | 0 |  | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | EMERGENCY COMMUNICATION SYSTEM | 13 | 13 | 100% |  | 0 |  | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT |  | BHS SECURITY AND CUSTOMS NETWORK INFRASTRUCTURE | 16 | 16 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0
ICT |  | TYPICAL DRAWINGS | 97 | 24 | 24.74% |  | 73 |  | 1 | 4 | 0 | 0 | 0 | 3 | 1 | 0 | 15
| 107 |  |  | 77 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 13 | 16
GSM-DAS & TETRA |  | TETRA | 101 | 77 | 76.24% |  | 24 |  | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 13 | 16
GSM-DAS & TETRA |  | TETRA ICT TECHNICAL ROOMS | 6 | 0 | 0% |  | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL | CIVIL | CIVIL | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Barrier Fence | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | NDRC | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Power and Lighting Trench Layout | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Electric Manhole | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | CCTV and Radar Trench Layout | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Communication Trench Layout | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Manhole | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Survey Control Points | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Chain Link Fence Foundation | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | Foundation Detail | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
CIVIL |  | GENERAL | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | 0 |  | #REF!
ARCHITECTURE | ARCH | ARCHITECTURAL DRAWINGS | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
ARCHITECTURE |  | GENERAL | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
| #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | 0 |  | #REF!
Drawing List | GEN | GENERAL | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
| #REF! |  |  | #REF! |  |  | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL | STRUCTURE | General | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Radar and Camera Pole | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Foundation Detail | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Precast Manhole Typical | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Precast Foundation Details | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Pilling Setting | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Pilling Layout | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Footing Detail | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | UPS BASE STAND | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
STRUCTURAL |  | Branch Duct bank connection | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| #REF! |  |  | #REF! |  | 0 | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 |  | #REF!
MECHANICAL | MCH | HVAC LAYOUT | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! |  |  | #REF!
MECHANICAL |  | AIR CONDITIONING | #REF! | #REF! |  |  | #REF! |  | #REF! | #REF! | #REF! | #REF! |  |  | #REF!

## RFC to be Raised
An RFC is required for the below-listed shop drawings before proceeding
Atlas requires the RFC response in order to proceed with 165 drawings out of the total 1,540 drawings defined within the project scope.
Categories | Justification for raising the RFC | Building | No of Drawings | Action by | Remarks | Action Plan | Resullt
Category 1 | Cannot find the Redundancy Route | B3,B4,B5 | 18 | Atlas | Fiber optic cable redundancy is required; however, the IFC drawings only show the primary route, and no alternative routing could be identified | Completed | Atlas has been cordinated with ATJV and concluded shop drawing submitted with primary roue and upon confirmation shop drawing are officially submitted through Sharepoints on 23rd June 2025
Category 2 | FOV Details have been provided to raise RFC | B1,B2,B6 | 25 | ATJV / Atlas | Atlas has addressed ATJV regarding 25 drawings that do not include the FOV. We are currently awaiting ATJV’s response in order to proceed with the FOV RFC submission since June 10th | AT JV
Category 3 | RFC Raised - Exceeding 90 m | B1 | 8 | ATJV / Atlas | The data cable length exceeds 90 meters based on the current routing in the IFC drawings. Atlas has proposed a solution to address this issue and is currently awaiting the official RFC response from the client. The submitted RFC is presently under review with ATJV since June 11th | AT JV
Category 4 | Supplier hasn't been finalized | B1,B2,B3 | 70 | Atlas | Sound Management System | ATLAS | This is our internal Issues to finalisse the PAVA sub-contractor
Category 5 | Supplier not confirmed | B4,B5 | 0 | Atlas | Car park mangement System | Completed | The RFC, officially received under reference ATV-1300000403-RFC-ICT-00009-R00, has been concluded as descoped.
Category 6 | Waiting for supplier confirmation for cable route | B1,B2,B6 | 25 | Atlas | Waiting for supplier confirmation for cable route | ATLAS | This is our internal Issues to finalisse the t Disabled Toilet Alaram sub-contractor

## Summary (RFC Issues)
Sno | Issues for RFC to be raised | ACS | BRS | CNT | CPM | DTA | PAS | SEC | Sub-Dec | TEL | Grand Total
1 | Cannot find the Redundancy Route |  |  | 18 | [6 empty] | 18
| B03 |  |  | 3 | [6 empty] | 3
| B04 |  |  | 10 | [6 empty] | 10
| B05 |  |  | 5 | [6 empty] | 5
2 | FOV Details have been provided to raise RFC | [6 empty] | 25 |  |  | 25
| B01 | [6 empty] | 16 |  |  | 16
| B02 | [6 empty] | 8 |  |  | 8
| B06 | [6 empty] | 1 |  |  | 1
3 | RFC Raised - Exceeding 90 m | [8 empty] | 8 | 8
| B01 | [8 empty] | 8 | 8
4 | Supplier hasn't been finalized | [5 empty] | 70 |  |  |  | 70
| B01 | [5 empty] | 59 |  |  |  | 59
| B02 | [5 empty] | 8 |  |  |  | 8
| B03 | [5 empty] | 3 |  |  |  | 3
5 | Supplier not confirmed |  |  |  | 19 | [5 empty] | 19
| B04 |  |  |  | 14 | [5 empty] | 14
| B05 |  |  |  | 5 | [5 empty] | 5
6 | Waiting for supplier confirmation for cable route |  |  |  |  | 25 |  |  |  |  | 25
| B01 |  |  |  |  | 20 |  |  |  |  | 20
| B02 |  |  |  |  | 4 |  |  |  |  | 4
| B06 |  |  |  |  | 1 |  |  |  |  | 1
| Grand Total |  |  | 18 | 19 | 25 | 70 | 25 | 1 | 8 | 166

## Summary (Drawing Counts)
System | To be submitted | AR (ATJV) | Code 2 | RTN (AS) | UR (ATJV) | UR (DAR) | Grand Total
ACCESS CONTROL SYSTEM | 16 |  | 17 | 10 | 16 | 29 | 88
B01 | 16 |  |  |  | 16 | 29 | 61
B02 |  |  |  | 8 |  |  | 8
B03 |  |  | 2 |  |  |  | 2
B04 |  |  | 10 |  |  |  | 10
B05 |  |  | 5 |  |  |  | 5
B06 |  |  |  | 1 |  |  | 1
B07 |  |  |  | 1 |  |  | 1
BAGGAGE RECONCILIATION SYSTEM | 10 | [5 empty] | 10
B01 | 10 | [5 empty] | 10
COMMUNICATION EQUIPMENT SYSTEM | 1 | 8 | 66 |  | 8 |  | 83
B01 |  |  | 58 |  |  |  | 58
B02 |  |  | 8 |  |  |  | 8
B03 | 1 |  |  |  | 1 |  | 2
B04 |  | 8 |  |  |  |  | 8
B05 |  |  |  |  | 5 |  | 5
B06 |  |  |  |  | 1 |  | 1
B07 |  |  |  |  | 1 |  | 1
CONTAINMENT SYSTEM |  |  | 69 | 18 |  |  | 87
B01 |  |  | 61 |  |  |  | 61
B02 |  |  | 8 |  |  |  | 8
B03 |  |  |  | 3 |  |  | 3
B04 |  |  |  | 10 |  |  | 10
B05 |  |  |  | 5 |  |  | 5
DATA NETWORK SYSTEM | 53 | 10 | 10 | 1 | 5 |  | 79
B01 | 41 |  | 10 |  |  |  | 51
B02 | 8 | [5 empty] | 8
B03 | 3 | [5 empty] | 3
B04 |  | 10 |  |  |  |  | 10
B05 |  |  |  |  | 5 |  | 5
B06 | 1 | [5 empty] | 1
B07 |  |  |  | 1 |  |  | 1
DISABLED TOILET ALARM SYSTEM |  |  |  | 25 |  |  | 25
B01 |  |  |  | 20 |  |  | 20
B02 |  |  |  | 4 |  |  | 4
B06 |  |  |  | 1 |  |  | 1
EMERGENCY COMMUNICATION SYSTEM |  |  |  | 12 |  |  | 12
B01 |  |  |  | 12 |  |  | 12
FIRE ALARM SYSTEM | 93 | [5 empty] | 93
B01 | 62 | [5 empty] | 62
B02 | 11 | [5 empty] | 11
B03 | 3 | [5 empty] | 3
B04 | 10 | [5 empty] | 10
B05 | 5 | [5 empty] | 5
B06 | 1 | [5 empty] | 1
B07 | 1 | [5 empty] | 1
GSM | 226 | [5 empty] | 226
B01 | 24 | [5 empty] | 24
B02 | 48 | [5 empty] | 48
B03 | 42 | [5 empty] | 42
B04 | 60 | [5 empty] | 60
B05 | 30 | [5 empty] | 30
B06 | 6 | [5 empty] | 6
B07 | 6 | [5 empty] | 6
BXX | 10 | [5 empty] | 10
ICT TECHNICAL ROOMS | 41 | [5 empty] | 41
B01 | 28 | [5 empty] | 28
B02 | 2 | [5 empty] | 2
B03 | 1 | [5 empty] | 1
B04 | 1 | [5 empty] | 1
B05 | 1 | [5 empty] | 1
B06 | 1 | [5 empty] | 1
B07 | 1 | [5 empty] | 1
BXX | 6 | [5 empty] | 6
IP TELEPHONE SYSTEM | 18 |  | 39 |  | 1 | 12 | 70
B01 | 8 |  | 39 |  |  | 12 | 59
B02 | 7 | [5 empty] | 7
B03 | 2 | [5 empty] | 2
B06 | 1 | [5 empty] | 1
B07 |  |  |  |  | 1 |  | 1
IPTV SYSTEM |  |  | 57 |  |  |  | 57
B01 |  |  | 48 |  |  |  | 48
B02 |  |  | 8 |  |  |  | 8
B06 |  |  | 1 |  |  |  | 1
MASTER CLOCK SYSTEM |  |  | 70 |  |  |  | 70
B01 |  |  | 61 |  |  |  | 61
B02 |  |  | 8 |  |  |  | 8
B06 |  |  | 1 |  |  |  | 1
SECURITY SYSTEM ACS AND CCTV SCHEDULES | 57 | [5 empty] | 57
B01 | 20 | [5 empty] | 20
B02 | 15 | [5 empty] | 15
B03 | 6 | [5 empty] | 6
B04 | 4 | [5 empty] | 4
B05 | 4 | [5 empty] | 4
B06 | 4 | [5 empty] | 4
B07 | 4 | [5 empty] | 4
SIGNAGE SYSTEM | [5 empty] | 40 | 40
B01 | [5 empty] | 32 | 32
B02 | [5 empty] | 8 | 8
SINGLE LINE DIAGRAM | 54 | [5 empty] | 54
B01 | 19 | [5 empty] | 19
B02 | 12 | [5 empty] | 12
B03 | 7 | [5 empty] | 7
B04 | 6 | [5 empty] | 6
B05 | 6 | [5 empty] | 6
B06 | 2 | [5 empty] | 2
B07 | 2 | [5 empty] | 2
SITE TELECOMMUNICATION SYSTEM | 37 | [5 empty] | 37
B0X | 37 | [5 empty] | 37
SOUND MANAGEMENT SYSTEM | 70 | [5 empty] | 70
B01 | 59 | [5 empty] | 59
B02 | 8 | [5 empty] | 8
B03 | 3 | [5 empty] | 3
TETRA | 81 | [5 empty] | 81
B01 | 8 | [5 empty] | 8
B02 | 16 | [5 empty] | 16
B03 | 14 | [5 empty] | 14
B04 | 20 | [5 empty] | 20
B05 | 10 | [5 empty] | 10
B06 | 2 | [5 empty] | 2
B07 | 2 | [5 empty] | 2
BXX | 9 | [5 empty] | 9
TYPICAL DRAWINGS | 84 |  | 13 |  |  |  | 97
00 | 84 |  | 13 |  |  |  | 97
VIDEO SURVELLIANCE SYSTEM | 83 | 5 | 2 |  |  |  | 90
B01 | 62 | [5 empty] | 62
B02 | 8 | [5 empty] | 8
B03 | 3 | [5 empty] | 3
B04 | 10 | [5 empty] | 10
B05 |  | 5 |  |  |  |  | 5
B06 |  |  | 1 |  |  |  | 1
B07 |  |  | 1 |  |  |  | 1
WIRELESS LAN COMMUNICATION SYSTEM | 28 |  |  | 26 |  |  | 54
B01 | 20 |  |  | 26 |  |  | 46
B02 | 8 | [5 empty] | 8
Grand Total | 971 | 23 | 343 | 92 | 30 | 81 | 1541

## Sheet4 (hidden)
494 | ICT | EMERGENCY COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 07 | ICT | ECS | SD | 00 | 1300403-ATS-B01-FF-07-ICT-ECS-SD-00 | First Floor Emergency Communication System Plan Part-07 | 0 | #VALUE! | 00 | 2025-06-23 | ATLS-004-SD-ICT-00057-R00 | UR (ATJV) | --- | UR (ATJV) | ATLS-004-SD-ICT-00057-R00 | 2025-06-23 | UR (ATJV) | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---

## Sheet1 (hidden)
SUBMISSION WEEK |  | <42566 | <42573 | <42580 | <42587 | <42594 | <42601 | <42608 | <42615 | <42622 | <42629 | <42636 | <42643 | <42650 | <42657 | <42664 | <42671 | <42678 | <42685 | <42692 | <42699 | <42706 | <42713 | <42720 | <42727 | <42734 | <42741 | <42748 | <42755 | <42762 | <42769 | <42776 | <42783 | <42790 | <42797 | <42804 | <42811 | <42818 | <42825 | <42832 | <42839 | <42846 | <42853 | <42860 | <42867 | <42874 | <42881 | <42888 | <42895 | <42972 | < | < | < | < | < | < | < | < | < | <
|  | >=42559 | >=42566 | >=42573 | >=42580 | >=42587 | >=42594 | >=42601 | >=42608 | >=42615 | >=42622 | >=42629 | >=42636 | >=42643 | >=42650 | >=42657 | >=42664 | >=42671 | >=42678 | >=42685 | >=42692 | >=42699 | >=42706 | >=42713 | >=42720 | >=42727 | >=42734 | >=42741 | >=42748 | >=42755 | >=42762 | >=42769 | >=42776 | >=42783 | >=42790 | >=42797 | >=42804 | >=42811 | >=42818 | >=42825 | >=42832 | >=42839 | >=42846 | >=42853 | >=42860 | >=42867 | >=42874 | >=42881 | >=42888 | >=42895 | >=42902 | >=42909 | >=42916 | >=42923 | >=42930 | >=42937 | >=42944 | >=42951 | >=42958 | >=42965
 | time axis 2016-07-08 to 2017-08-25
 | time axis 2016-07-08 to 2017-08-25
 | time axis 2016-07-01 to 2017-08-25
CMA REV 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CMA REV >0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL SUBM |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CUM REV 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Data (hidden)
Data Date | 2025-08-05 |  | <=45786 | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856 | <=45863 | <=45870
Cutoff | 2025-08-01 |  | >45779 | >45786 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849 | >45856 | >45863
|  |  | W -12 | W -11 | W -10 | W -9 | W -8 | W -7 | W -6 | W -5 | W -4 | W -3 | W -2 | W -1 | This Week
|  |  | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01
|  | Submitted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | <=45786 | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856
APPROVED | #REF! |  | >0 | >45786 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849
UNDER REVIEW | #REF! |  | Over | 11 Weeks | 10 Weeks | 9 Weeks | 8 Weeks | 7 Weeks | 6 Weeks | 5 Weeks | 4 Weeks | 3 Weeks | 2 Weeks
REJECTED | #REF! | Pending Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REV. 0 TO GO | #REF! | Cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | <=45702 | <=45709 | <=45716 | <=45723 | <=45730 | <=45737 | <=45744 | <=45751 | <=45758 | <=45765 | <=45772 | <=45779 | <=45786 | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856 | <=45863 | <=45870
|  |  | >45695 | >45702 | >45709 | >45716 | >45723 | >45730 | >45737 | >45744 | >45751 | >45758 | >45765 | >45772 | >45779 | >45786 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849 | >45856 | >45863
|  |  | W -24 | W -23 | W -22 | W -21 | W -20 | W -19 | W -18 | W -17 | W -16 | W -15 | W -14 | W -13 | W -12 | W -11 | W -10 | W -9 | W -8 | W -7 | W -6 | W -5 | W -4 | W -3 | W -2 | W -1 | THIS WEEK
|  |  | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Q.ty Reviewed (or UR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rev Time Overdue (Avg) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0