## INTERNAL Submittal Log
|  | 4 | 9 |  | 10 | 11 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
|  | Project Name | Constuction of East Midfiled Cargo Terminal Facility at ZIA |  |  |  | 131
DATA DATE | 2025-08-12 | Contract No |  | Clinet |  | ADA
|  | Sub Contractor | ATLAS SECURITY | Contractor |  | RAQ Contracting Co LLC
Use this field only for any comment.
[8 empty] | REVISION 00 | [5 empty] | REVISION 01 | [5 empty] | REVISION 02 | [5 empty] | REVISION 03 | [5 empty] | REVISION 04 | [5 empty] | REVISION 05
|  |  | DOCUMENT | CATEGORIES |  | DOCUMENT | FORECAST SUBMISSION | SUB CONTRACTOR REFERENCE | SUBMISSION | REPLY DOCUMENT |  | APPROVAL | REVIEW PERIOD | SUB CONTRACTOR REFERENCE | SUBMISSION | REPLY DOCUMENT |  | APPROVAL | REVIEW PERIOD | SUB CONTRACTOR REFERENCE | SUBMISSION | REPLY DOCUMENT |  | APPROVAL | REVIEW | SUB CONTRACTOR REFERENCE | SUBMISSION | REPLY DOCUMENT |  | APPROVAL | REVIEW | SUB CONTRACTOR REFERENCE | SUBMISSION | REPLY DOCUMENT |  | APPROVAL | REVIEW | SUB CONTRACTOR REFERENCE | SUBMISSION | REPLY DOCUMENT |  | APPROVAL | REVIEW
|  | DISCIPLINE | TYPE | TYPE | DOC REF NO | NAME | DATE | SUBMISSION REFERENCE | DATE | REFERENCE | DATE | CODE | DAYS | SUBMISSION REFERENCE | DATE | REFERENCE | DATE | CODE | DAYS | SUBMISSION REFERENCE | DATE | REFERENCE | DATE | CODE | DAYS | SUBMISSION REFERENCE | DATE | REFERENCE | DATE | CODE | DAYS | SUBMISSION REFERENCE | DATE | REFERENCE | DATE | CODE | DAYS | SUBMISSION REFERENCE | DATE | REFERENCE | DATE | CODE | DAYS
R_TYPE | R_DOC_S | SPEC_DESC | DOCTYPE | Column2 | DISC | DNAME | Date | ST0 | STD0 | JVT0 | JVD0 | STATUS0 | REVIEW0 | ST1 | STD1 | JVT1 | JVD1 | STATUS1 | REVIEW1 | ST2 | STD2 | JVT2 | JVD2 | STATUS2 | REVIEW2 | ST3 | STD3 | JVT3 | JVD3 | STATUS3 | REVIEW3 | ST4 | STD4 | JVT4 | JVD4 | STATUS4 | REVIEW5 | ST5 | STD5 | JVT5 | JVD5 | STATUS5 | REVIEW52 | REMARKS
PQ | --- | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00003 | PQ Approval for Subcontractor - ICT System, Security System, Distribution Antenna System/TETRA/MSI System Works - M/s Atlas Security Company LLC. | N/A | 24: PQ-23A25-Y000-0003-00; 25: 2025-01-27; 26: PQ-23A25-Y000-0003-00; 27: 2025-02-01; 28: 3; 30: PQ-23A25-Y000-0003-01; 31: 2025-02-01; 32: PQ-23A25-Y000-0003-01; 33: 2025-02-10; 34: 2; 36: PQ-23A25-Y000-0003-02; 37: 2025-03-05; 38: PQ-23A25-Y000-0003-02; 39: 2025-03-17; 40: 2
HSE Plan | --- | General | HSE Plan | Project Submittal | MTC-23A35-ATLASLLC-PL-HP-0001 | Health, Safety and Environment (HSE) Plan |  | 24: DS-23A25-G000-0002-00; 25: 2025-02-27; 28: UR
PQMP | --- | General | PQMP | Project Submittal | MTC-23A35-ATLASLLC-PL-QP-0001 | Project Quality Management Plan |  | 24: DS-23A25-G000-0001-00; 25: 2025-02-27; 28: UR
Baseline | --- | General | Baseline | Project Submittal |  | Baseline Narrative Report
ERP | --- | General | ERP | Project Submittal | MTC-23A35-ATLASLLC-PL-GE-0001 | Site Specific Emergency Response Plan |  | 24: DS-23A25-G000-0003-00; 25: 2025-03-03; 28: UR
SLP | --- | General | SLP | Project Submittal | MTC-23A35-ATLASLLC-PL-GE-0002 | Site Logistic Plan |  | 24: DS-23A25-G000-0004-00; 25: 2025-03-12; 28: UR
MS | --- | Security | MS | Project Submittal | MTC-23A25-Y100-SD-MS-00002 | Material Submittal for Access Control System & Accessories |  | 24: MS-23A25-Y100-0002-00; 25: 2025-02-20; 26: MS-23A25-Y100-0002-00; 27: 2025-03-06; 28: 2
MS | --- | Special System | MS | Project Submittal | MTC-23A25-Y000-SD-MS-00001 | Material Submittal for Racks |  | 24: MS-23A25-Y000-0001-00; 25: 2025-03-11; 26: MS-23A25-Y000-0022-00; 27: 2025-06-09; 28: 3; 30: MS-23A25-Y000-0022-01; 31: 2025-06-18; 32: MS-23A25-Y000-0022-01; 33: 2025-07-17; 34: 3
MS | --- | Telecommunication | MS | Project Submittal | MTC-23A25-T000-SD-MS-00002 | Material Submittal for Structured Cabling |  | 24: MS-23A25-T000-0002-00; 25: 2025-03-03; 26: MS-23A25-T000-0002-00; 27: 2025-03-17; 28: 3; 30: MS-23A25-T000-0002-01; 31: 2025-06-18; 32: MS-23A25-T000-0002-01; 33: 2025-07-03; 34: 2
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00001 | Material Submittal for Computer Network Equipment - LAN |  | 24: MS-23A25-Y300-0001-00; 25: 2025-04-03; 26: MS-23A25-Y300-0001-00; 27: 2025-05-08; 28: 3; 30: MS-23A25-Y300-0001-01; 31: 2025-05-28; 32: MS-23A25-Y300-0001-01; 33: 2025-06-19; 34: 3
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00002 | Material Submittal for Computer Network Equipment - GLAN |  | 24: MS-23A25-Y300-0002-00; 25: 2025-04-03; 26: MS-23A25-Y300-0002-00; 27: 2025-05-08; 28: 3; 30: MS-23A25-Y300-0002-01; 31: 2025-05-28; 32: MS-23A25-Y300-0002-01; 33: 2025-06-18; 34: 2
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00003 | Material Submittal for Wireless LAN |  | 24: MS-23A25-Y300-0003-00; 25: 2025-04-03; 26: MS-23A25-Y300-0003-00; 27: 2025-05-02; 28: 3; 30: MS-23A25-Y300-0003-01; 31: 2025-06-18; 32: MS-23A25-Y300-0003-01; 33: 2025-07-14; 34: 4
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00012 | Material Submittal for Data Communication Hardware - Govt |  | 24: MS-23A25-Y300-0012-00; 25: 2025-05-29; 26: MS-23A25-Y300-0045-00; 27: 2025-07-15; 28: 4
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00013 | Material Submittal for Data Communication Hardware - ICT |  | 24: MS-23A25-Y300-0013-00; 25: 2025-06-02; 26: MS-23A25-Y300-0047-00; 27: 2025-07-14; 28: 4
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00004 | Material Submittal for Voice Over Internet Protocol |  | 24: MS-23A25-Y300-0004-00; 25: 2025-04-03; 26: MS-23A25-Y300-0004-00; 27: 2025-05-09; 28: 3; 30: MS-23A25-Y300-0004-01; 31: 2025-05-29; 32: MS-23A25-Y300-0004-01; 33: 2025-06-24; 34: 3
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00006 | Material Submittal for Audio and Video System |  | 24: MS-23A25-Y300-0006-00; 25: 2025-04-16; 26: MS-23A25-Y300-0006-00; 27: 2025-05-28; 28: 3; 30: MS-23A25-Y300-0006-01; 31: 2025-07-28; 34: UR
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00011 | Material Submittal for Internet Protocol Television (IPTV) System |  | 24: MS-23A25-Y300-0011-00; 25: 2025-05-28; 26: MS-23A25-Y300-0044-00; 27: 2025-06-24; 28: 3
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00009 | Material Submittal for Flight Information Display System |  | 24: MS-23A25-Y300-0009-00; 25: 2025-05-26; 26: MS-23A25-Y300-0057-00; 27: 2025-07-14; 28: 3; 30: MS-23A25-Y300-0057-01; 31: 2025-08-09; 34: UR
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00010 | Material Submittal for Master Clock System (MCS) |  | 24: MS-23A25-Y300-0010-00; 25: 2025-05-26; 26: MS-23A25-Y300-0039-00; 27: 2025-06-30; 28: 2
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00005 | Material Submittal for Car Park Management System |  | 24: MS-23A25-Y300-0005-00; 25: 2025-05-14; 26: MS-23A25-Y300-0033-00; 27: 2025-05-31; 28: 4
MS | --- | Security | MS | Project Submittal | MTC-23A25-Y100-SD-MS-00001 | Material Submittal for CCTV and Accessories |  | 24: MS-23A25-Y100-0001-00; 25: 2025-02-19; 26: MS-23A25-Y100-0001-00; 27: 2025-03-06; 28: 2
MS | --- | Telecommunication | MS | Project Submittal | MTC-23A25-T000-SD-MS-00003 | Material Submittal for Video Wall System |  | 24: MS-23A25-T000-0003-00; 25: 2025-02-20; 26: MS-23A25-T000-0024-00; 27: 2025-04-03; 28: 2
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00007 | Material Submittal for Distributed Antenna System |  | 24: MS-23A25-Y300-0007-00; 25: 2025-04-21; 28: UR
MS | --- | Security | MS | Project Submittal | MTC-23A25-Y100-SD-MS-00003 | Material Submittal for ANPR Camera and Associated Components |  | 24: MS-23A25-Y100-0003-00; 25: 2025-02-25; 26: MS-23A25-Y100-0003-00; 27: 2025-06-21; 28: 3; 30: MS-23A25-Y100-0003-01; 31: 2025-07-25; 32: MS-23A25-Y100-0003-01; 33: 2025-07-31; 34: 3
MSS | --- | Special System | MSS | Project Submittal | MTC-23A35-Y000-PR-MS-00001 | Method Statement & Risk Assessment of Racks |  | 24: MSS-23A25-Y000-0001-00; 25: 2025-03-18; 28: UR
MSS | --- | ICT | MSS | Project Submittal |  | Method Statement & Risk Assessment for Installation of Structured Cabling Network
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00004 | Method Statement & Risk Assessment for Installation of Computer Network Equipment - LAN |  | 24: MSS-23A25-Y300-0004-00; 25: 2025-04-11; 28: UR
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00002 | Method Statement & Risk Assessment for Installation of Computer Network Equipment - GLAN |  | 24: MSS-23A25-Y300-0002-00; 25: 2025-04-11; 28: UR
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00003 | Method Statement & Risk Assessment for Installation of Wireless LAN |  | 24: MSS-23A25-Y300-0003-00; 25: 2025-04-11; 26: MSS-23A25-Y300-0003-00; 27: 2025-05-12; 28: 3
MSS | --- | ICT | MSS | Project Submittal |  | Method Statement & Risk Assessment for Installation of Data Communication Hardware - ICT
MSS | --- | Security | MSS | Project Submittal |  | Method Statement & Risk Assessment for Installation of Data Communication Hardware - GOVT
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00005 | Method Statement & Risk Assessment for Installation of Voice Over Internet Protocol |  | 24: MSS-23A25-Y300-0005-00; 25: 2025-04-11; 26: MSS-23A25-Y300-0005-00; 27: 2025-05-20; 28: 3
MSS | --- | ICT | MSS | Project Submittal |  | Method Statement & Risk Assessment for Installation of Audio Video System
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00009 | Method Statement & Risk Assessment for Installation of Internet Protocol Television System |  | 24: MSS-23A25-Y300-0009-00; 25: 2025-06-09; 26: MSS-23A25-Y300-0033-00; 27: 2025-06-19; 28: 4
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00008 | Method Statement & Risk Assessment for Installation of Flight Information Display System |  | 24: MSS-23A25-Y300-0008-00; 25: 2025-06-09; 28: UR
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00010 | Method Statement & Risk Assessment for Installation of Master Clock System |  | 24: MSS-23A25-Y300-0010-00; 25: 2025-06-10; 26: MSS-23A25-Y300-0034-00; 27: 2025-06-19; 28: 4
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00006 | Method Statement & Risk Assessment for Installation of Car Park Management System |  | 24: MSS-23A25-Y300-0006-00; 25: 2025-04-11; 26: MSS-23A25-Y300-0006-00; 27: 2025-06-29; 28: 3
MSS | --- | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00003 | Method Statement & Risk Assessment for Installation of Security Access Control System |  | 24: MSS-23A25-Y100-0003-00; 25: 2025-02-27; 26: MSS-23A25-Y100-0003-00; 27: 2025-04-03; 28: 2; 30: MSS-23A25-Y100-0003-01; 31: 2025-06-09; 32: MSS-23A25-Y100-0003-01; 33: 2025-07-24; 34: 2
MSS | --- | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00001 | Method Statement & Risk Assessment for Installation of Closed-Circuit Television System |  | 24: MSS-23A25-Y100-0001-00; 25: 2025-02-27; 26: MSS-23A25-Y100-0001-00; 27: 2025-04-03; 28: 2; 30: MSS-23A25-Y100-0001-01; 31: 2025-06-03; 32: MSS-23A25-Y100-0001-01; 33: 2025-06-25; 34: 4
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00001 | Method Statement & Risk Assessment for Installation of Video Wall System |  | 24: MSS-23A25-Y300-0001-00; 25: 2025-04-04; 26: MSS-23A25-Y300-0001-00; 27: 2025-06-29; 28: 3
MSS | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00007 | Method Statement & Risk Assessment for Installation of Distributed Antenna System | MSS-23A25-Y300-0007-00
MSS | --- | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00002 | Method Statement & Risk Assessment for Installation of ANPR Camera |  | 24: MSS-23A25-Y100-0002-00; 25: 2025-02-27; 26: MSS-23A25-Y100-0002-00; 27: 2025-04-03; 28: 2; 30: MSS-23A25-Y100-0002-01; 31: 2025-06-09; 32: MSS-23A25-Y100-0002-01; 33: 2025-06-25; 34: 4
MSS | --- | Telecommunication | MSS | Project Submittal | MTC-23A35-T000-PR-MS-00001 | Method Statement & Risk Assessment for Relocation of Structured Cabling - Phase 2 |  | 24: MSS-23A25-T000-0001-00; 25: 2025-02-27; 26: MSS-23A25-T000-0001-00; 27: 2025-04-03; 28: 3; 30: MSS-23A25-T000-0001-01; 31: 2025-05-27; 34: UR
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Computer Network Equipment - LAN
SDD | --- | Security | SDD | Project Submittal |  | System Design Document for Copmuter Network Equipment - GLAN
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Wireless LAN
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Data Communication Hardware - ICT
SDD | --- | Security | SDD | Project Submittal |  | System Design Document for Data Communication Hardware - GOVT
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Voice Over Internet Protocol
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Audio Video System
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Internet Protocol Television System
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Flight Information System
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Master Clock System
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Car Park Management System
SDD | --- | Security | SDD | Project Submittal |  | System Design Document for Security Access Control System
SDD | --- | Security | SDD | Project Submittal |  | System Design Document for Closed Circuit Television System
SDD | --- | Special System | SDD | Project Submittal |  | System Design Document for Video Wall System
SDD | --- | ICT | SDD | Project Submittal |  | System Design Document for Dsitributed Antenna System
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Structured Cabling Network
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Computer Network Equipment - LAN
TCP | --- | Security | TCP | Project Submittal |  | Testing and Commisioning Procedure for Computer Network Equipment - GLAN
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Wireless LAN
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Data Communication Hardware - ICT
TCP | --- | Security | TCP | Project Submittal |  | Testing and Commisioning Procedure for Data Communication Hardware - GOVT
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Voice Over Internet Protocol
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Audio Video System
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Internet Protocol Television System
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Flight Information System
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Master Clock System
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Car Park Management System
TCP | --- | Security | TCP | Project Submittal |  | Testing and Commisioning Procedure for Security Access Control System
TCP | --- | Security | TCP | Project Submittal |  | Testing and Commisioning Procedure for Closed-Circuit Television System
TCP | --- | Special System | TCP | Project Submittal |  | Testing and Commisioning Procedure for Video Wall System
TCP | --- | ICT | TCP | Project Submittal |  | Testing and Commisioning Procedure for Distributed Antenna System
TCP | --- | Security | TCP | Project Submittal |  | Testing and Commisioning Procedure for ANPR
MS (Fence Relocation) | --- | Telecommunication | MS (Fence Relocation) | Project Submittal | MTC-23A25-T000-SD-MS-00001 | Material Submittal for Relocation of Fiber Cable |  | 24: MS-23A25-T000-0001-00; 25: 2025-03-03; 26: MS-23A25-T000-0001-00; 27: 2025-03-17; 28: 3; 30: MS-23A25-T000-0001-01; 31: 2025-07-03; 32: MS-23A25-T000-0001-01; 33: 2025-07-19; 34: 2
PQ | --- | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00004 | PQ Approval for Subcontractor - DataOne Technologies L.L.C - Structured Cabling Network |  | 24: PQ-23A25-Y000-0004-00; 25: 2025-04-07; 26: PQ-23A25-Y000-0004-00; 27: 2025-04-14; 28: 2
Report | --- | General | Report | Project Submittal | MTC-23A35-ATLASLLC-PL-GE-0003 | Weekly Progress Report |  | 24: DS-23A25-G000-0005-00; 25: 2025-04-07; 28: UR
PQ | --- | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00005 | PQ Approval for Subcontractor - Commnet Systems Consultancy LLC |  | 24: PQ-23A25-Y000-0005-00; 25: 2025-04-07; 26: PQ-23A25-Y000-0005-00; 27: 2025-04-14; 28: 2
MS (Fence Relocation) | --- | Security | MS (Fence Relocation) | Project Submittal | MTC-23A25-Y100-SD-MS-00004 | Material Submittal for Camera and Radar Poles (Fence Relocation) |  | 24: MS-23A25-Y100-0004-00; 25: 2025-04-21; 26: MS-23A25-Y100-0004-00; 27: 2025-05-06; 28: 2 | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MS (Fence Relocation) | --- | ICT | MS (Fence Relocation) | Project Submittal | MTC-23A25-Y300-SD-MS-00008 | Material Submittal for Local Area Network - Nexans (Fence Relocation) |  | 24: MS-23A25-Y300-0008-00; 25: 2025-04-21; 26: MS-23A25-Y300-0008-00; 27: 2025-05-06; 28: 2 | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MS (Fence Relocation) | --- | Telecommunication | MS (Fence Relocation) | Project Submittal | MTC-23A25-T000-SD-MS-00004 | Material Submittal for CommScope Cables and Accessories (Fence Relocation) |  | 24: MS-23A25-T000-0004-00; 25: 2025-04-21; 26: MS-23A25-T000-0004-00; 27: 2025-05-12; 28: 3; 30: MS-23A25-T000-0004-01; 31: 2025-05-16; 32: MS-23A25-T000-0004-01; 33: 2025-06-24; 34: 2 | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MS (Fence Relocation) | --- | Security | MS (Fence Relocation) | Project Submittal | MTC-23A25-Y100-SD-MS-00005 | Material Submittal for CCTV Cameras (Fence Relocation) |  | 24: MS-23A25-Y100-0005-00; 25: 2025-04-21; 26: MS-23A25-Y100-0005-00; 27: 2025-05-06; 28: 2 | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MSS (Fence Relocation) | --- | Security | MSS (Fence Relocation) | Project Submittal | MTC-23A35-Y100-PR-MS-00004 | Method Statement & Risk Assessment for Installation of Video Surveillance System (Fence Relocation) |  | 24: MSS-23A25-Y100-0004-00; 25: 2025-04-22; 26: MSS-23A25-Y100-0004-00; 27: 2025-05-09; 28: 2; 30: MSS-23A25-Y100-0004-01; 31: 2025-06-09; 32: MSS-23A25-Y100-0004-01; 33: 2025-06-16; 34: 3; 36: MSS-23A25-Y100-0004-02; 37: 2025-08-07; 40: UR | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MSS (Fence Relocation) | --- | Telecommunication | MSS (Fence Relocation) | Project Submittal | MTC-23A35-T000-PR-MS-00002 | Method Statement & Risk Assessment for Installation of Structure cabling and Camera Field Cabinet Installation (Fence Relocation) |  | 24: MSS-23A25-T000-0002-00; 25: 2025-04-22; 26: MSS-23A25-T000-0005 -00; 27: 2025-05-08; 28: 2; 30: MSS-23A25-T000-0005-01; 31: 2025-06-09; 32: MSS-23A25-T000-0005-01; 33: 2025-06-16; 34: 3; 36: MSS-23A25-T000-0005-02; 37: 2025-08-07; 40: UR | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MSS (Fence Relocation) | --- | Security | MSS (Fence Relocation) | Project Submittal | MTC-23A35-Y100-PR-MS-00005 | Method Statement & Risk Assessment for Installation of FDC components on Pole tray and Wall mounted enclosure plate (Fence Relocation) |  | 24: MSS-23A25-Y100-0005-00; 25: 2025-04-22; 26: MSS-23A25-Y100-0005-00; 27: 2025-05-08; 28: 2; 30: MSS-23A25-Y100-0005-01; 31: 2025-06-09; 32: MSS-23A25-Y100-0005-01; 33: 2025-06-16; 34: 3; 36: MSS-23A25-Y100-0005-02; 37: 2025-08-07; 40: UR | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MSS (Fence Relocation) | --- | Civil | MSS (Fence Relocation) | Project Submittal | MTC-23A35-C000-PR-MS-00001 | Method Statement & Risk Assessment for Pole Erection (Fence Relocation) |  | 24: MSS-23A25-C000-0001-00; 25: 2025-04-22; 26: MSS-23A25-C000-0011-00; 27: 2025-05-05; 28: 2; 30: MSS-23A25-C000-0011-01; 31: 2025-08-07; 34: UR | [5 empty] | Newly Added as per Ibrar email on 19/4/2025 - (Fence Relocation)
MS (Fence Relocation) | --- | Electrical | MS (Fence Relocation) | Project Submittal | MTC-23A25-E000-SD-MS-00001 | Material Submittal for LV Power Cables and Single Core Wires (Fence Relocation) |  | 24: MS-23A25-E000-0001-00; 25: 2025-04-22; 26: MS-23A25-E000-0012-00; 27: 2025-04-29; 28: 2 | [5 empty] | Newly Added as per Ibrar email on 21/4/2025 - (Fence Relocation)
MS (Fence Relocation) | --- | Electrical | MS (Fence Relocation) | Project Submittal | MTC-23A25-E000-SD-MS-00002 | Material Submittal for Electrical Cutout for Street Poles (Fence Relocation) |  | 24: MS-23A25-E000-0002-00; 25: 2025-04-22; 26: MS-23A25-E000-0013-00; 27: 2025-04-29; 28: 2 | [5 empty] | Newly Added as per Ibrar email on 21/4/2025 - (Fence Relocation)
MS (Fence Relocation) | --- | Electrical | MS (Fence Relocation) | Project Submittal | MTC-23A25-E000-SD-MS-00003 | Material Submittal for Light Fittings thorn (option A) - (Fence Relocation) |  | 24: MS-23A25-E000-0003-00; 25: 2025-04-22; 26: MS-23A25-E000-0014-00; 27: 2025-05-05; 28: 2 | [5 empty] | Newly Added as per Ibrar email on 21/4/2025 - (Fence Relocation)
MSS (Fence Relocation) | --- | Electrical | MSS (Fence Relocation) | Project Submittal | MTC-23A35-E000-PR-MS-00001 | Method Statement & Risk Assessment for Installation of Pole Light Fixture (Fence Relocation) |  | 24: MSS-23A25-E000-0001-00; 25: 2025-04-22; 26: MSS-23A25-E000-0012-00; 27: 2025-04-29; 28: 2; 30: MSS-23A25-E000-0012-01; 31: 2025-08-07; 34: UR | [5 empty] | Newly Added as per Ibrar email on 21/4/2025 - (Fence Relocation)
TS | --- | Telecommunication | TS | Project Submittal | MTC-23A35-T000-CA-DE-0001 | Technical Solution for Rerouting Existing Fiber Communication Cables |  | 24: DS-23A25-T000-0001-00; 25: 2025-05-15; 26: DS-23A25-T000-0057-00; 27: 2025-05-22; 28: 3; 30: DS-23A25-T000-0057-01; 31: 2025-05-27; 32: DS-23A25-T000-0057-01; 33: 2025-06-09; 34: 3; 36: DS-23A25-T000-0057-02; 37: 2025-06-18; 38: DS-23A25-T000-0057-02; 39: 2025-06-29; 40: 2
PQ | --- | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00006 | PQ Approval for Subcontractor - Fiber Optic Supplier & Services LLC (FOSS) |  | 24: PQ-23A25-Y000-0006-00; 25: 2025-05-15; 26: PQ-23A25-Y000-0009-00; 27: 2025-06-07; 28: 4
TS | --- | Telecommunication | TS | Project Submittal | MTC-23A35-T000-CA-DE-0002 | Technical Solution for Rerouting Existing Fiber Communication Cables - Phase 2 |  | 24: DS-23A25-T000-0002-00; 25: 2025-05-15; 26: DS-23A25-T000-0058-00; 27: 2025-05-22; 28: 3; 30: DS-23A25-T000-0058-01; 31: 2025-05-27; 32: DS-23A25-T000-0058-01; 33: 2025-06-09; 34: 3
OC | --- | General | OC | Project Submittal | MTC-23A25-GOOO-SD-GE-00002 | Organization Chart & Resource CV's - SCN Subcontractor M/s. DataONE, |  | 24: DS-23A25-G000-0046-00; 25: 2025-04-21; 26: DS-23A25-G000-0046-00; 27: 2025-05-13; 28: 2 | [5 empty] | Submitted by RAQ
OC | --- | General | OC | Project Submittal | MTC-23A25-GOOO-SD-GE-00001 | Organization Chart & Resource CV's M/s. (ATLAS) |  | 24: DS-23A25-G000-0041-00; 25: 2025-04-10; 26: DS-23A25-G000-0041-00; 27: 2025-05-20; 28: 2 | [5 empty] | Submitted by RAQ
MSS | --- | Telecommunication | MSS | Project Submittal | MTC-23A35-T000-PR-MS-00003 | Method Statement & Risk Assessment for Relocation of Structured Cabling |  | 24: MSS-23A25-T000-0003-00; 25: 2025-05-27; 26: MSS-23A25-T000-0029-00; 27: 2025-06-09; 28: 3; 30: MSS-23A25-T000-0029-01; 31: 2025-07-10; 34: UR
MS | --- | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00014 | Material Submittal for Car Park Management System |  | 24: MS-23A25-Y300-0014-00; 25: 2025-06-18; 28: UR
MSI | --- | ICT | MSI | Project Submittal | MTC-23A35-Y313-PR-GE-00001 | Master System Integration (MSI) Methodology |  | 24: DS-23A25-Y300-0001-00; 25: 2025-07-22; 26: DS-23A25-Y300-0099-00; 27: 2025-07-28; 28: 3; 30: DS-23A25-Y300-0099-01; 31: 2025-08-05; 34: UR
MSI | --- | ICT | MSI | Project Submittal | MTC-23A35-Y313-SC-PL-00001 | Master System Integration (MSI) Architecture & ICD Schedule
PQ | --- | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00007 | PQ Approval for Subcontractor - Advanced Integration Technologies |  | 24: PQ-23A25-Y000-0007-00; 25: 2025-08-01; 28: UR
MSS | --- | Special System | MSS | Project Submittal | MTC-23A35-Y000-PR-MS-00002 | Method Statement & Risk Assessment for Installation of Master Clock System |  | 24: MSS-23A25-Y000-0002-00; 25: 2025-08-07; 28: UR
PQ | --- | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00008 | PQ Approval for Subcontractor - 2i Integrated Industries L.L.C (Telecom Shelter) |  | 24: PQ-23A25-Y000-0008-00; 25: 2025-08-08; 28: UR
ITP | --- | Special System | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Racks
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Structured Cabling Network
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Computer Network Equipment - LAN
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Computer Network Equipment - GLAN
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Wireless LAN
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Data Communication Hardware - ICT
ITP | --- | Security | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Data Communication Hardware - GOVT
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Voice Over Internet Protocol
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Audio Video System
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Internet Protocol Television System
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Flight Information Display System
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Master Clock System
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Car Park Management System
ITP | --- | Security | ITP | Project Submittal | MTC-23A35-Y100-PR-IP-00003 | Inspection & Test Plan for Installation of Security Access Control System |  | 24: DS-23A25-Y100-0001-00; 25: 2025-08-11; 28: UR
ITP | --- | Security | ITP | Project Submittal | MTC-23A35-Y100-PR-IP-00001 | Inspection & Test Plan for Installation of Closed-Circuit Television System
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Video Wall System
ITP | --- | ICT | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Distributed Antenna System
ITP | --- | Security | ITP | Project Submittal |  | Inspection & Test Plan for Installation of ANPR Camera
ITP | --- | Telecommunication | ITP | Project Submittal |  | Inspection & Test Plan for Relocation of Structured Cabling - Phase 2
ITP | --- | Security | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Video Surveillance System (Fence Relocation)
ITP | --- | Telecommunication | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Structure cabling and Camera Field Cabinet Installation (Fence Relocation)
ITP | --- | Security | ITP | Project Submittal | MTC-23A35-Y100-PR-IP-00005 | Inspection & Test Plan for Installation of FDC components on Pole tray and Wall mounted enclosure plate (Fence Relocation)
ITP | --- | Civil | ITP | Project Submittal |  | Inspection & Test Plan for Pole Erection (Fence Relocation)
ITP | --- | Electrical | ITP | Project Submittal |  | Inspection & Test Plan for Installation of Pole Light Fixture (Fence Relocation)
ITP | --- | Telecommunication | ITP | Project Submittal |  | Inspection & Test Plan for Relocation of Structured Cabling
MSS | --- | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00006 | Method Statement & Risk Assessment for Installation of Closed-Circuit Television System |  | 24: MSS-23A25-Y100-0006-00; 25: 2025-08-11; 28: UR
N-ICD | --- | ICT | N-ICD | Project Submittal | MTC-23A35-Y312-SP-IF-00001 | Network - Interface Control Document (N-ICD)Template |  | 24: DS-23A25-Y300-0003-00; 25: 2025-08-12; 28: UR
S-ICD | --- | ICT | S-ICD | Project Submittal | MTC-23A35-Y312-SP-IF-00002 | Software - Interface Control Document (S-ICD) Template |  | 24: DS-23A25-Y300-0004-00; 25: 2025-08-12; 28: UR

## Sheet3 (hidden)
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00001 | Material Submittal for Radar System (Terma)
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00002 | Material Submittal for CCTV Cameras
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00003 | Material Submittal for Tamper Switch
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00004 | Material Submittal for LED Light
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00006 | Material Submittal for Camera and Radar Poles
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00007 | Material Submittal for Power Supply - Phoenix
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00008 | Material Submittal for wiring accessories for FDB enclosure
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00009 | Material Submittal for snap fit filter fan
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00010 | Material Submittal for Wall Mount Enclosure for FDC
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00011 | Material Submittal for Pole Mount Bracket for Axis Q1786-LE and Q1951-E
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00012 | Material Submittal for 8 Way Earth Bar
Security | MS | Project Submittal | SFP-22A78-Y100-SD-MS-00005 | Material Submittal for Automatic Number Plate Recognition

## Dashboard
|  |  | TOTAL | SUBMITTED |  | CODE 1 | CODE 2 | CODE 5 | CODE 4 | UNDER REVIEW | CODE 3 | Cancelled | REV 0 TO SUBMIT
|  |  | 131 | 68 | 51.91% | 0 | 21 | 0 | 9 | 28 | 10 | 0 | 63
Baseline | PROJECT | Baseline Program | 1 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Baseline Program
HSE Plan |  | (HSE) Plan | 1 | 1 | 100% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | (HSE) Plan
ERP |  | Emergency Response Plan | 1 | 1 | 100% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Emergency Response Plan
PQMP |  | Project Quality Management Plan | 1 | 1 | 100% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Project Quality Management Plan
SLP |  | Site Logistic Plan | 1 | 1 | 100% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Site Logistic Plan
PQ |  | Pre-Qualification | 6 | 6 | 100% | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | Pre-Qualification
MS |  | Material Submittal | 19 | 19 | 100% | 0 | 6 | 0 | 4 | 4 | 5 | 0 | 0 | Material Submittal
MS (Fence Relocation) |  | Material Submittal (Fence Relocation) | 8 | 8 | 100% | 0 | 8 | 0 | 0 | 0 | 0 |  | 0 | Material Submittal (Fence Relocation)
MSS |  | Method Statement & Risk Assessment | 22 | 17 | 77.27% | 0 | 1 | 0 | 4 | 8 | 4 | 0 | 5 | Method Statement & Risk Assessment
MSS (Fence Relocation) |  | Method Statement & Risk Assessment (Fence Relocation) | 5 | 5 | 100% | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 | Method Statement & Risk Assessment (Fence Relocation)
SDD |  | System Design Document | 15 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | System Design Document
TCP |  | Testing and Commisioning Procedure | 17 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | Testing and Commisioning Procedure
Report |  | Weekly Progress Reports | 1 | 1 | 100% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Weekly Progress Reports
TS |  | Technical Solution | 2 | 2 | 100% | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Technical Solution
OC |  | Organization Chart & Resource CV's | 2 | 2 | 100% | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Organization Chart & Resource CV's
MSI |  | Master System Integration | 2 | 1 | 50% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | Master System Integration
ITP |  | Inspection & Test Plan | 25 | 1 | 4% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 24 | Inspection & Test Plan
N-ICD |  | Network - Interface Control Document | 1 | 1 | 100% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Network - Interface Control Document
S-ICD |  | Software - Interface Control Document | 1 | 1 | 100% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Software - Interface Control Document
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DESIGN |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T&C |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CLOSEOUT |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| OTHER |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.09%

## CURRENT STATUS
|  |  | 4 | 9 |  | 10 | 11 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
|  |  | Project Name | Constuction of East Midfiled Cargo Terminal Facility at ZIA |  |  |  |  | 15: Total Documents
DATA DATE | 2025-08-12 |  | Contract No |  | Clinet |  | ADA |  | 15: 131
|  |  | Sub Contractor | ATLAS SECURITY | Contractor |  | RAQ Contracting Co LLC
[9 empty] | TODAY is : |  | 2025-08-12
CURRENT DOCUMENT STATUS
|  |  |  | DOCUMENT | CATEGORIES |  | DOCUMENT |  | CONTRACTOR REFERENCE | CURRENT | SUBMISSION | REPLY DOCUMENT |  |  | APPROVAL | REVIEW PERIOD | OVERDUE
|  |  | DISCIPLINE | TYPE | TYPE | DOC REF NO | NAME |  | LATEST SUBMISSION | REVISION | DATE | CURRENT REV. REFERENCE | LATEST REV. REFERENCE | DATE | CODE | DAYS | DAYS
R_TYPE | R_DOC_S | R_APP_S | SPEC_DESC | DOCTYPE | Column2 | DISC | DNAME | Column1 | SD_C | REV_C | Sub_Date | Current_Status | JV_LRR | Reply_Date | Status_Approval | REVIEW_C | REVIEW_C2 | S1
PQ | --- | APPROVED | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00003 | PQ Approval for Subcontractor - ICT System, Security System, Distribution Antenna System/TETRA/MSI System Works - M/s Atlas Security Company LLC. |  | PQ-23A25-Y000-0003-02 | 2 | 2025-03-05 | PQ-23A25-Y000-0003-02 | PQ-23A25-Y000-0003-02 | 2025-03-17 | 2 | 12 | 5 | 7
HSE Plan | --- | UR | General | HSE Plan | Project Submittal | MTC-23A35-ATLASLLC-PL-HP-0001 | Health, Safety and Environment (HSE) Plan |  | DS-23A25-G000-0002-00 | 0 | 2025-02-27 | UNDER REVIEW |  |  | UR | 166 | 145 | 21
PQMP | --- | UR | General | PQMP | Project Submittal | MTC-23A35-ATLASLLC-PL-QP-0001 | Project Quality Management Plan |  | DS-23A25-G000-0001-00 | 0 | 2025-02-27 | UNDER REVIEW |  |  | UR | 166 | 145 | 21
Baseline | --- | --- | General | Baseline | Project Submittal | 0 | Baseline Narrative Report |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ERP | --- | UR | General | ERP | Project Submittal | MTC-23A35-ATLASLLC-PL-GE-0001 | Site Specific Emergency Response Plan |  | DS-23A25-G000-0003-00 | 0 | 2025-03-03 | UNDER REVIEW |  |  | UR | 162 | 141 | 21
SLP | --- | UR | General | SLP | Project Submittal | MTC-23A35-ATLASLLC-PL-GE-0002 | Site Logistic Plan |  | DS-23A25-G000-0004-00 | 0 | 2025-03-12 | UNDER REVIEW |  |  | UR | 153 | 132 | 21
MS | --- | APPROVED | Security | MS | Project Submittal | MTC-23A25-Y100-SD-MS-00002 | Material Submittal for Access Control System & Accessories |  | MS-23A25-Y100-0002-00 | 0 | 2025-02-20 | MS-23A25-Y100-0002-00 | MS-23A25-Y100-0002-00 | 2025-03-06 | 2 | 14 | --- | 21
MS | --- | REJECTED | Special System | MS | Project Submittal | MTC-23A25-Y000-SD-MS-00001 | Material Submittal for Racks |  | MS-23A25-Y000-0022-01 | 1 | 2025-06-18 | MS-23A25-Y000-0022-01 | MS-23A25-Y000-0022-01 | 2025-07-17 | 3 | 29 | 15 | 14
MS | --- | APPROVED | Telecommunication | MS | Project Submittal | MTC-23A25-T000-SD-MS-00002 | Material Submittal for Structured Cabling |  | MS-23A25-T000-0002-01 | 1 | 2025-06-18 | MS-23A25-T000-0002-01 | MS-23A25-T000-0002-01 | 2025-07-03 | 2 | 15 | 1 | 14
MS | --- | REJECTED | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00001 | Material Submittal for Computer Network Equipment - LAN |  | MS-23A25-Y300-0001-01 | 1 | 2025-05-28 | MS-23A25-Y300-0001-01 | MS-23A25-Y300-0001-01 | 2025-06-19 | 3 | 22 | 8 | 14
MS | --- | APPROVED | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00002 | Material Submittal for Computer Network Equipment - GLAN |  | MS-23A25-Y300-0002-01 | 1 | 2025-05-28 | MS-23A25-Y300-0002-01 | MS-23A25-Y300-0002-01 | 2025-06-18 | 2 | 21 | 7 | 14
MS | --- | FALSE | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00003 | Material Submittal for Wireless LAN |  | MS-23A25-Y300-0003-01 | 1 | 2025-06-18 | MS-23A25-Y300-0003-01 | MS-23A25-Y300-0003-01 | 2025-07-14 | 4 | 26 | 12 | 14
MS | --- | FALSE | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00012 | Material Submittal for Data Communication Hardware - Govt |  | MS-23A25-Y300-0012-00 | 0 | 2025-05-29 | MS-23A25-Y300-0045-00 | MS-23A25-Y300-0045-00 | 2025-07-15 | 4 | 47 | 26 | 21
MS | --- | FALSE | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00013 | Material Submittal for Data Communication Hardware - ICT |  | MS-23A25-Y300-0013-00 | 0 | 2025-06-02 | MS-23A25-Y300-0047-00 | MS-23A25-Y300-0047-00 | 2025-07-14 | 4 | 42 | 21 | 21
MS | --- | REJECTED | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00004 | Material Submittal for Voice Over Internet Protocol |  | MS-23A25-Y300-0004-01 | 1 | 2025-05-29 | MS-23A25-Y300-0004-01 | MS-23A25-Y300-0004-01 | 2025-06-24 | 3 | 26 | 12 | 14
MS | --- | UR | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00006 | Material Submittal for Audio and Video System |  | MS-23A25-Y300-0006-01 | 1 | 2025-07-28 | UNDER REVIEW | MS-23A25-Y300-0006-00 | 2025-05-28 | UR | 15 | --- | 14
MS | --- | REJECTED | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00011 | Material Submittal for Internet Protocol Television (IPTV) System |  | MS-23A25-Y300-0011-00 | 0 | 2025-05-28 | MS-23A25-Y300-0044-00 | MS-23A25-Y300-0044-00 | 2025-06-24 | 3 | 27 | 6 | 21
MS | --- | UR | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00009 | Material Submittal for Flight Information Display System |  | MS-23A25-Y300-0057-01 | 1 | 2025-08-09 | UNDER REVIEW | MS-23A25-Y300-0057-00 | 2025-07-14 | UR | 3 | --- | 14
MS | --- | APPROVED | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00010 | Material Submittal for Master Clock System (MCS) |  | MS-23A25-Y300-0010-00 | 0 | 2025-05-26 | MS-23A25-Y300-0039-00 | MS-23A25-Y300-0039-00 | 2025-06-30 | 2 | 35 | 14 | 21
MS | --- | FALSE | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00005 | Material Submittal for Car Park Management System |  | MS-23A25-Y300-0005-00 | 0 | 2025-05-14 | MS-23A25-Y300-0033-00 | MS-23A25-Y300-0033-00 | 2025-05-31 | 4 | 17 | --- | 21
MS | --- | APPROVED | Security | MS | Project Submittal | MTC-23A25-Y100-SD-MS-00001 | Material Submittal for CCTV and Accessories |  | MS-23A25-Y100-0001-00 | 0 | 2025-02-19 | MS-23A25-Y100-0001-00 | MS-23A25-Y100-0001-00 | 2025-03-06 | 2 | 15 | --- | 21
MS | --- | APPROVED | Telecommunication | MS | Project Submittal | MTC-23A25-T000-SD-MS-00003 | Material Submittal for Video Wall System |  | MS-23A25-T000-0003-00 | 0 | 2025-02-20 | MS-23A25-T000-0024-00 | MS-23A25-T000-0024-00 | 2025-04-03 | 2 | 42 | 21 | 21
MS | --- | UR | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00007 | Material Submittal for Distributed Antenna System |  | MS-23A25-Y300-0007-00 | 0 | 2025-04-21 | UNDER REVIEW |  |  | UR | 113 | 92 | 21
MS | --- | REJECTED | Security | MS | Project Submittal | MTC-23A25-Y100-SD-MS-00003 | Material Submittal for ANPR Camera and Associated Components |  | MS-23A25-Y100-0003-01 | 1 | 2025-07-25 | MS-23A25-Y100-0003-01 | MS-23A25-Y100-0003-01 | 2025-07-31 | 3 | 6 | --- | 14
MSS | --- | UR | Special System | MSS | Project Submittal | MTC-23A35-Y000-PR-MS-00001 | Method Statement & Risk Assessment of Racks |  | MSS-23A25-Y000-0001-00 | 0 | 2025-03-18 | UNDER REVIEW |  |  | UR | 147 | 126 | 21
MSS | --- | --- | ICT | MSS | Project Submittal | 0 | Method Statement & Risk Assessment for Installation of Structured Cabling Network |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
MSS | --- | UR | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00004 | Method Statement & Risk Assessment for Installation of Computer Network Equipment - LAN |  | MSS-23A25-Y300-0004-00 | 0 | 2025-04-11 | UNDER REVIEW |  |  | UR | 123 | 102 | 21
MSS | --- | UR | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00002 | Method Statement & Risk Assessment for Installation of Computer Network Equipment - GLAN |  | MSS-23A25-Y300-0002-00 | 0 | 2025-04-11 | UNDER REVIEW |  |  | UR | 123 | 102 | 21
MSS | --- | REJECTED | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00003 | Method Statement & Risk Assessment for Installation of Wireless LAN |  | MSS-23A25-Y300-0003-00 | 0 | 2025-04-11 | MSS-23A25-Y300-0003-00 | MSS-23A25-Y300-0003-00 | 2025-05-12 | 3 | 31 | 10 | 21
MSS | --- | --- | ICT | MSS | Project Submittal | 0 | Method Statement & Risk Assessment for Installation of Data Communication Hardware - ICT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
MSS | --- | --- | Security | MSS | Project Submittal | 0 | Method Statement & Risk Assessment for Installation of Data Communication Hardware - GOVT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
MSS | --- | REJECTED | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00005 | Method Statement & Risk Assessment for Installation of Voice Over Internet Protocol |  | MSS-23A25-Y300-0005-00 | 0 | 2025-04-11 | MSS-23A25-Y300-0005-00 | MSS-23A25-Y300-0005-00 | 2025-05-20 | 3 | 39 | 18 | 21
MSS | --- | --- | ICT | MSS | Project Submittal | 0 | Method Statement & Risk Assessment for Installation of Audio Video System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
MSS | --- | FALSE | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00009 | Method Statement & Risk Assessment for Installation of Internet Protocol Television System |  | MSS-23A25-Y300-0009-00 | 0 | 2025-06-09 | MSS-23A25-Y300-0033-00 | MSS-23A25-Y300-0033-00 | 2025-06-19 | 4 | 10 | --- | 21
MSS | --- | UR | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00008 | Method Statement & Risk Assessment for Installation of Flight Information Display System |  | MSS-23A25-Y300-0008-00 | 0 | 2025-06-09 | UNDER REVIEW |  |  | UR | 64 | 43 | 21
MSS | --- | FALSE | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00010 | Method Statement & Risk Assessment for Installation of Master Clock System |  | MSS-23A25-Y300-0010-00 | 0 | 2025-06-10 | MSS-23A25-Y300-0034-00 | MSS-23A25-Y300-0034-00 | 2025-06-19 | 4 | 9 | --- | 21
MSS | --- | REJECTED | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00006 | Method Statement & Risk Assessment for Installation of Car Park Management System |  | MSS-23A25-Y300-0006-00 | 0 | 2025-04-11 | MSS-23A25-Y300-0006-00 | MSS-23A25-Y300-0006-00 | 2025-06-29 | 3 | 79 | 58 | 21
MSS | --- | APPROVED | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00003 | Method Statement & Risk Assessment for Installation of Security Access Control System |  | MSS-23A25-Y100-0003-01 | 1 | 2025-06-09 | MSS-23A25-Y100-0003-01 | MSS-23A25-Y100-0003-01 | 2025-07-24 | 2 | 45 | 31 | 14
MSS | --- | FALSE | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00001 | Method Statement & Risk Assessment for Installation of Closed-Circuit Television System |  | MSS-23A25-Y100-0001-01 | 1 | 2025-06-03 | MSS-23A25-Y100-0001-01 | MSS-23A25-Y100-0001-01 | 2025-06-25 | 4 | 22 | 8 | 14
MSS | --- | REJECTED | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00001 | Method Statement & Risk Assessment for Installation of Video Wall System |  | MSS-23A25-Y300-0001-00 | 0 | 2025-04-04 | MSS-23A25-Y300-0001-00 | MSS-23A25-Y300-0001-00 | 2025-06-29 | 3 | 86 | 65 | 21
MSS | --- | --- | ICT | MSS | Project Submittal | MTC-23A35-Y300-PR-MS-00007 | Method Statement & Risk Assessment for Installation of Distributed Antenna System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
MSS | --- | FALSE | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00002 | Method Statement & Risk Assessment for Installation of ANPR Camera |  | MSS-23A25-Y100-0002-01 | 1 | 2025-06-09 | MSS-23A25-Y100-0002-01 | MSS-23A25-Y100-0002-01 | 2025-06-25 | 4 | 16 | 2 | 14
MSS | --- | UR | Telecommunication | MSS | Project Submittal | MTC-23A35-T000-PR-MS-00001 | Method Statement & Risk Assessment for Relocation of Structured Cabling - Phase 2 |  | MSS-23A25-T000-0001-01 | 1 | 2025-05-27 | UNDER REVIEW | MSS-23A25-T000-0001-00 | 2025-04-03 | UR | 77 | --- | 14
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Computer Network Equipment - LAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | Security | SDD | Project Submittal | 0 | System Design Document for Copmuter Network Equipment - GLAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Wireless LAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Data Communication Hardware - ICT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | Security | SDD | Project Submittal | 0 | System Design Document for Data Communication Hardware - GOVT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Voice Over Internet Protocol |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Audio Video System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Internet Protocol Television System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Flight Information System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Master Clock System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Car Park Management System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | Security | SDD | Project Submittal | 0 | System Design Document for Security Access Control System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | Security | SDD | Project Submittal | 0 | System Design Document for Closed Circuit Television System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | Special System | SDD | Project Submittal | 0 | System Design Document for Video Wall System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
SDD | --- | --- | ICT | SDD | Project Submittal | 0 | System Design Document for Dsitributed Antenna System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Structured Cabling Network |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Computer Network Equipment - LAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | Security | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Computer Network Equipment - GLAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Wireless LAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Data Communication Hardware - ICT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | Security | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Data Communication Hardware - GOVT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Voice Over Internet Protocol |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Audio Video System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Internet Protocol Television System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Flight Information System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Master Clock System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Car Park Management System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | Security | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Security Access Control System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | Security | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Closed-Circuit Television System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | Special System | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Video Wall System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | ICT | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for Distributed Antenna System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
TCP | --- | --- | Security | TCP | Project Submittal | 0 | Testing and Commisioning Procedure for ANPR |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
MS (Fence Relocation) | --- | APPROVED | Telecommunication | MS (Fence Relocation) | Project Submittal | MTC-23A25-T000-SD-MS-00001 | Material Submittal for Relocation of Fiber Cable |  | MS-23A25-T000-0001-01 | 1 | 2025-07-03 | MS-23A25-T000-0001-01 | MS-23A25-T000-0001-01 | 2025-07-19 | 2 | 16 | 2 | 14
PQ | --- | APPROVED | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00004 | PQ Approval for Subcontractor - DataOne Technologies L.L.C - Structured Cabling Network |  | PQ-23A25-Y000-0004-00 | 0 | 2025-04-07 | PQ-23A25-Y000-0004-00 | PQ-23A25-Y000-0004-00 | 2025-04-14 | 2 | 7 | --- | 21
Report | --- | UR | General | Report | Project Submittal | MTC-23A35-ATLASLLC-PL-GE-0003 | Weekly Progress Report |  | DS-23A25-G000-0005-00 | 0 | 2025-04-07 | UNDER REVIEW |  |  | UR | 127 | 106 | 21
PQ | --- | APPROVED | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00005 | PQ Approval for Subcontractor - Commnet Systems Consultancy LLC |  | PQ-23A25-Y000-0005-00 | 0 | 2025-04-07 | PQ-23A25-Y000-0005-00 | PQ-23A25-Y000-0005-00 | 2025-04-14 | 2 | 7 | --- | 21
MS (Fence Relocation) | --- | APPROVED | Security | MS (Fence Relocation) | Project Submittal | MTC-23A25-Y100-SD-MS-00004 | Material Submittal for Camera and Radar Poles (Fence Relocation) |  | MS-23A25-Y100-0004-00 | 0 | 2025-04-21 | MS-23A25-Y100-0004-00 | MS-23A25-Y100-0004-00 | 2025-05-06 | 2 | 15 | --- | 21
MS (Fence Relocation) | --- | APPROVED | ICT | MS (Fence Relocation) | Project Submittal | MTC-23A25-Y300-SD-MS-00008 | Material Submittal for Local Area Network - Nexans (Fence Relocation) |  | MS-23A25-Y300-0008-00 | 0 | 2025-04-21 | MS-23A25-Y300-0008-00 | MS-23A25-Y300-0008-00 | 2025-05-06 | 2 | 15 | --- | 21
MS (Fence Relocation) | --- | APPROVED | Telecommunication | MS (Fence Relocation) | Project Submittal | MTC-23A25-T000-SD-MS-00004 | Material Submittal for CommScope Cables and Accessories (Fence Relocation) |  | MS-23A25-T000-0004-01 | 1 | 2025-05-16 | MS-23A25-T000-0004-01 | MS-23A25-T000-0004-01 | 2025-06-24 | 2 | 39 | 25 | 14
MS (Fence Relocation) | --- | APPROVED | Security | MS (Fence Relocation) | Project Submittal | MTC-23A25-Y100-SD-MS-00005 | Material Submittal for CCTV Cameras (Fence Relocation) |  | MS-23A25-Y100-0005-00 | 0 | 2025-04-21 | MS-23A25-Y100-0005-00 | MS-23A25-Y100-0005-00 | 2025-05-06 | 2 | 15 | --- | 21
MSS (Fence Relocation) | --- | UR | Security | MSS (Fence Relocation) | Project Submittal | MTC-23A35-Y100-PR-MS-00004 | Method Statement & Risk Assessment for Installation of Video Surveillance System (Fence Relocation) |  | MSS-23A25-Y100-0004-02 | 2 | 2025-08-07 | UNDER REVIEW | MSS-23A25-Y100-0004-01 | 2025-06-16 | UR | 5 | --- | 7
MSS (Fence Relocation) | --- | UR | Telecommunication | MSS (Fence Relocation) | Project Submittal | MTC-23A35-T000-PR-MS-00002 | Method Statement & Risk Assessment for Installation of Structure cabling and Camera Field Cabinet Installation (Fence Relocation) |  | MSS-23A25-T000-0005-02 | 2 | 2025-08-07 | UNDER REVIEW | MSS-23A25-T000-0005-01 | 2025-06-16 | UR | 5 | --- | 7
MSS (Fence Relocation) | --- | UR | Security | MSS (Fence Relocation) | Project Submittal | MTC-23A35-Y100-PR-MS-00005 | Method Statement & Risk Assessment for Installation of FDC components on Pole tray and Wall mounted enclosure plate (Fence Relocation) |  | MSS-23A25-Y100-0005-02 | 2 | 2025-08-07 | UNDER REVIEW | MSS-23A25-Y100-0005-01 | 2025-06-16 | UR | 5 | --- | 7
MSS (Fence Relocation) | --- | UR | Civil | MSS (Fence Relocation) | Project Submittal | MTC-23A35-C000-PR-MS-00001 | Method Statement & Risk Assessment for Pole Erection (Fence Relocation) |  | MSS-23A25-C000-0011-01 | 1 | 2025-08-07 | UNDER REVIEW | MSS-23A25-C000-0011-00 | 2025-05-05 | UR | 5 | --- | 14
MS (Fence Relocation) | --- | APPROVED | Electrical | MS (Fence Relocation) | Project Submittal | MTC-23A25-E000-SD-MS-00001 | Material Submittal for LV Power Cables and Single Core Wires (Fence Relocation) |  | MS-23A25-E000-0001-00 | 0 | 2025-04-22 | MS-23A25-E000-0012-00 | MS-23A25-E000-0012-00 | 2025-04-29 | 2 | 7 | --- | 21
MS (Fence Relocation) | --- | APPROVED | Electrical | MS (Fence Relocation) | Project Submittal | MTC-23A25-E000-SD-MS-00002 | Material Submittal for Electrical Cutout for Street Poles (Fence Relocation) |  | MS-23A25-E000-0002-00 | 0 | 2025-04-22 | MS-23A25-E000-0013-00 | MS-23A25-E000-0013-00 | 2025-04-29 | 2 | 7 | --- | 21
MS (Fence Relocation) | --- | APPROVED | Electrical | MS (Fence Relocation) | Project Submittal | MTC-23A25-E000-SD-MS-00003 | Material Submittal for Light Fittings thorn (option A) - (Fence Relocation) |  | MS-23A25-E000-0003-00 | 0 | 2025-04-22 | MS-23A25-E000-0014-00 | MS-23A25-E000-0014-00 | 2025-05-05 | 2 | 13 | --- | 21
MSS (Fence Relocation) | --- | UR | Electrical | MSS (Fence Relocation) | Project Submittal | MTC-23A35-E000-PR-MS-00001 | Method Statement & Risk Assessment for Installation of Pole Light Fixture (Fence Relocation) |  | MSS-23A25-E000-0012-01 | 1 | 2025-08-07 | UNDER REVIEW | MSS-23A25-E000-0012-00 | 2025-04-29 | UR | 5 | --- | 14
TS | --- | APPROVED | Telecommunication | TS | Project Submittal | MTC-23A35-T000-CA-DE-0001 | Technical Solution for Rerouting Existing Fiber Communication Cables |  | DS-23A25-T000-0057-02 | 2 | 2025-06-18 | DS-23A25-T000-0057-02 | DS-23A25-T000-0057-02 | 2025-06-29 | 2 | 11 | 4 | 7
PQ | --- | FALSE | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00006 | PQ Approval for Subcontractor - Fiber Optic Supplier & Services LLC (FOSS) |  | PQ-23A25-Y000-0006-00 | 0 | 2025-05-15 | PQ-23A25-Y000-0009-00 | PQ-23A25-Y000-0009-00 | 2025-06-07 | 4 | 23 | 2 | 21
TS | --- | REJECTED | Telecommunication | TS | Project Submittal | MTC-23A35-T000-CA-DE-0002 | Technical Solution for Rerouting Existing Fiber Communication Cables - Phase 2 |  | DS-23A25-T000-0058-01 | 1 | 2025-05-27 | DS-23A25-T000-0058-01 | DS-23A25-T000-0058-01 | 2025-06-09 | 3 | 13 | --- | 14
OC | --- | APPROVED | General | OC | Project Submittal | MTC-23A25-GOOO-SD-GE-00002 | Organization Chart & Resource CV's - SCN Subcontractor M/s. DataONE, |  | DS-23A25-G000-0046-00 | 0 | 2025-04-21 | DS-23A25-G000-0046-00 | DS-23A25-G000-0046-00 | 2025-05-13 | 2 | 22 | 1 | 21
OC | --- | APPROVED | General | OC | Project Submittal | MTC-23A25-GOOO-SD-GE-00001 | Organization Chart & Resource CV's M/s. (ATLAS) |  | DS-23A25-G000-0041-00 | 0 | 2025-04-10 | DS-23A25-G000-0041-00 | DS-23A25-G000-0041-00 | 2025-05-20 | 2 | 40 | 19 | 21
MSS | --- | UR | Telecommunication | MSS | Project Submittal | MTC-23A35-T000-PR-MS-00003 | Method Statement & Risk Assessment for Relocation of Structured Cabling |  | MSS-23A25-T000-0029-01 | 1 | 2025-07-10 | UNDER REVIEW | MSS-23A25-T000-0029-00 | 2025-06-09 | UR | 33 | --- | 14
MS | --- | UR | ICT | MS | Project Submittal | MTC-23A25-Y300-SD-MS-00014 | Material Submittal for Car Park Management System |  | MS-23A25-Y300-0014-00 | 0 | 2025-06-18 | UNDER REVIEW |  |  | UR | 55 | 55
MSI | --- | UR | ICT | MSI | Project Submittal | MTC-23A35-Y313-PR-GE-00001 | Master System Integration (MSI) Methodology |  | DS-23A25-Y300-0099-01 | 1 | 2025-08-05 | UNDER REVIEW | DS-23A25-Y300-0099-00 | 2025-07-28 | UR | -8 | ---
MSI | --- | --- | ICT | MSI | Project Submittal | MTC-23A35-Y313-SC-PL-00001 | Master System Integration (MSI) Architecture & ICD Schedule |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
PQ | --- | UR | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00007 | PQ Approval for Subcontractor - Advanced Integration Technologies |  | PQ-23A25-Y000-0007-00 | 0 | 2025-08-01 | UNDER REVIEW |  |  | UR | 11 | 11
MSS | --- | UR | Special System | MSS | Project Submittal | MTC-23A35-Y000-PR-MS-00002 | Method Statement & Risk Assessment for Installation of Master Clock System |  | MSS-23A25-Y000-0002-00 | 0 | 2025-08-07 | UNDER REVIEW |  |  | UR | 5 | 5
PQ | --- | UR | Special System | PQ | Project Submittal | MTC-23A25-Y000-SD-PQ-00008 | PQ Approval for Subcontractor - 2i Integrated Industries L.L.C (Telecom Shelter) |  | PQ-23A25-Y000-0008-00 | 0 | 2025-08-08 | UNDER REVIEW |  |  | UR | 4 | 4
ITP | --- | --- | Special System | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Racks |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Structured Cabling Network |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Computer Network Equipment - LAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Computer Network Equipment - GLAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Wireless LAN |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Data Communication Hardware - ICT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Security | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Data Communication Hardware - GOVT |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Voice Over Internet Protocol |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Audio Video System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Internet Protocol Television System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Flight Information Display System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Master Clock System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Car Park Management System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | UR | Security | ITP | Project Submittal | MTC-23A35-Y100-PR-IP-00003 | Inspection & Test Plan for Installation of Security Access Control System |  | DS-23A25-Y100-0001-00 | 0 | 2025-08-11 | UNDER REVIEW |  |  | UR | 1 | 1
ITP | --- | --- | Security | ITP | Project Submittal | MTC-23A35-Y100-PR-IP-00001 | Inspection & Test Plan for Installation of Closed-Circuit Television System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Video Wall System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | ICT | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Distributed Antenna System |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Security | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of ANPR Camera |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Telecommunication | ITP | Project Submittal | 0 | Inspection & Test Plan for Relocation of Structured Cabling - Phase 2 |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Security | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Video Surveillance System (Fence Relocation) |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Telecommunication | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Structure cabling and Camera Field Cabinet Installation (Fence Relocation) |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Security | ITP | Project Submittal | MTC-23A35-Y100-PR-IP-00005 | Inspection & Test Plan for Installation of FDC components on Pole tray and Wall mounted enclosure plate (Fence Relocation) |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Civil | ITP | Project Submittal | 0 | Inspection & Test Plan for Pole Erection (Fence Relocation) |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Electrical | ITP | Project Submittal | 0 | Inspection & Test Plan for Installation of Pole Light Fixture (Fence Relocation) |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
ITP | --- | --- | Telecommunication | ITP | Project Submittal | 0 | Inspection & Test Plan for Relocation of Structured Cabling |  | 15: ---; 17: ---; 18: ---; 21: ---; 22: ---
MSS | --- | UR | Security | MSS | Project Submittal | MTC-23A35-Y100-PR-MS-00006 | Method Statement & Risk Assessment for Installation of Closed-Circuit Television System |  | MSS-23A25-Y100-0006-00 | 0 | 2025-08-11 | UNDER REVIEW |  |  | UR | 1 | 1
N-ICD | --- | UR | ICT | N-ICD | Project Submittal | MTC-23A35-Y312-SP-IF-00001 | Network - Interface Control Document (N-ICD)Template |  | DS-23A25-Y300-0003-00 | 0 | 0 | UNDER REVIEW |  |  | UR | 45881 | 45881
S-ICD | --- | UR | ICT | S-ICD | Project Submittal | MTC-23A35-Y312-SP-IF-00002 | Software - Interface Control Document (S-ICD) Template |  | DS-23A25-Y300-0004-00 | 0 | 0 | UNDER REVIEW |  |  | UR | 45881 | 45881

## Remove Documents
Sn | SPEC_DESC | DOCTYPE | Column2 | DNAME
1 | Security | ITP | Project Submittal | Inspection & Test Plan for Installation of Racks | Inspection & Test Plan for Installation of Racks | Special System | Method Statement & Risk Assessment of Racks
2 | ICT | ITP | Project Submittal | Inspection & Test Plan for for Installation of Structured Cabling Network | Inspection & Test Plan for Installation of Structured Cabling Network | ICT | Method Statement & Risk Assessment for Installation of Structured Cabling Network
3 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Computer Network Equipment - LAN | Inspection & Test Plan for Installation of Computer Network Equipment - LAN | ICT | Method Statement & Risk Assessment for Installation of Computer Network Equipment - LAN
4 | Security | ITP | Project Submittal | Inspection & Test Plan for Installation of Computer Network Equipment - GLAN | Inspection & Test Plan for Installation of Computer Network Equipment - GLAN | ICT | Method Statement & Risk Assessment for Installation of Computer Network Equipment - GLAN
5 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Wireless LAN | Inspection & Test Plan for Installation of Wireless LAN | ICT | Method Statement & Risk Assessment for Installation of Wireless LAN
6 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Data Communication Hardware - ICT | Inspection & Test Plan for Installation of Data Communication Hardware - ICT | ICT | Method Statement & Risk Assessment for Installation of Data Communication Hardware - ICT
7 | Security | ITP | Project Submittal | Inspection & Test Plan for Installation of Data Communication Hardware - GOVT | Inspection & Test Plan for Installation of Data Communication Hardware - GOVT | Security | Method Statement & Risk Assessment for Installation of Data Communication Hardware - GOVT
8 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Voice Over Internet Protocol | Inspection & Test Plan for Installation of Voice Over Internet Protocol | ICT | Method Statement & Risk Assessment for Installation of Voice Over Internet Protocol
9 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Audio Video System | Inspection & Test Plan for Installation of Audio Video System | ICT | Method Statement & Risk Assessment for Installation of Audio Video System
10 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Internet Protocol Television System | Inspection & Test Plan for Installation of Internet Protocol Television System | ICT | Method Statement & Risk Assessment for Installation of Internet Protocol Television System
11 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Flight Information System | Inspection & Test Plan for Installation of Flight Information Display System | ICT | Method Statement & Risk Assessment for Installation of Flight Information Display System
12 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Master Clock System | Inspection & Test Plan for Installation of Master Clock System | ICT | Method Statement & Risk Assessment for Installation of Master Clock System
13 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Car Park Management System | Inspection & Test Plan for Installation of Car Park Management System | ICT | Method Statement & Risk Assessment for Installation of Car Park Management System
14 | Security | ITP | Project Submittal | Inspection & Test Plan for Installation of Security Access Control System | Inspection & Test Plan for Installation of Security Access Control System | Security | Method Statement & Risk Assessment for Installation of Security Access Control System
15 | Security | ITP | Project Submittal | Inspection & Test Plan for Installation of Closed-Circuit Television System | Inspection & Test Plan for Installation of Closed-Circuit Television System | Security | Method Statement & Risk Assessment for Installation of Closed-Circuit Television System
16 | Special System | ITP | Project Submittal | Inspection & Test Plan for Installation of Video Wall System | Inspection & Test Plan for Installation of Video Wall System | ICT | Method Statement & Risk Assessment for Installation of Video Wall System
17 | ICT | ITP | Project Submittal | Inspection & Test Plan for Installation of Distributed Antenna System | Inspection & Test Plan for Installation of Distributed Antenna System | ICT | Method Statement & Risk Assessment for Installation of Distributed Antenna System
18 | Security | ITP | Project Submittal | Inspection & Test Plan for Installation of ANPR | Inspection & Test Plan for Installation of ANPR Camera | Security | Method Statement & Risk Assessment for Installation of ANPR Camera
[5 empty] | Inspection & Test Plan for Relocation of Structured Cabling - Phase 2 | Telecommunication | Method Statement & Risk Assessment for Relocation of Structured Cabling - Phase 2
[5 empty] | Inspection & Test Plan for Installation of Video Surveillance System (Fence Relocation) | Security | Method Statement & Risk Assessment for Installation of Video Surveillance System (Fence Relocation)
[5 empty] | Inspection & Test Plan for Installation of Structure cabling and Camera Field Cabinet Installation (Fence Relocation) | Telecommunication | Method Statement & Risk Assessment for Installation of Structure cabling and Camera Field Cabinet Installation (Fence Relocation)
[5 empty] | Inspection & Test Plan for Installation of FDC components on Pole tray and Wall mounted enclosure plate (Fence Relocation) | Security | Method Statement & Risk Assessment for Installation of FDC components on Pole tray and Wall mounted enclosure plate (Fence Relocation)
[5 empty] | Inspection & Test Plan for Pole Erection (Fence Relocation) | Civil | Method Statement & Risk Assessment for Pole Erection (Fence Relocation)
[5 empty] | Inspection & Test Plan for Installation of Pole Light Fixture (Fence Relocation) | Electrical | Method Statement & Risk Assessment for Installation of Pole Light Fixture (Fence Relocation)
[5 empty] | Inspection & Test Plan for Relocation of Structured Cabling | Telecommunication | Method Statement & Risk Assessment for Relocation of Structured Cabling

## Sheet4
Submission Type | Doc Number | Description | Submital Re | Rev | Sub_Date | Current_Status | Overdue
DS | MTC-23A35-ATLASLLC-PL-HP-0001 | Health, Safety and Environment (HSE) Plan | DS-23A25-G000-0002-00 | 0 | 2025-02-27 | UR | 144
DS | MTC-23A35-ATLASLLC-PL-QP-0001 | Project Quality Management Plan | DS-23A25-G000-0001-00 | 0 | 2025-02-27 | UR | 144
DS | MTC-23A35-ATLASLLC-PL-GE-0001 | Site Specific Emergency Response Plan | DS-23A25-G000-0003-00 | 0 | 2025-03-03 | UR | 140
DS | MTC-23A35-ATLASLLC-PL-GE-0002 | Site Logistic Plan | DS-23A25-G000-0004-00 | 0 | 2025-03-12 | UR | 131
MS | MTC-23A25-Y300-SD-MS-00007 | Material Submittal for Distributed Antenna System | MS-23A25-Y300-0007-00 | 0 | 2025-04-21 | UR | 91
MSS | MTC-23A35-Y000-PR-MS-00001 | Method Statement & Risk Assessment of Racks | MSS-23A25-Y000-0001-00 | 0 | 2025-03-18 | UR | 125
MSS | MTC-23A35-Y300-PR-MS-00004 | Method Statement & Risk Assessment for Installation of Computer Network Equipment - LAN | MSS-23A25-Y300-0004-00 | 0 | 2025-04-11 | UR | 101
MSS | MTC-23A35-Y300-PR-MS-00002 | Method Statement & Risk Assessment for Installation of Computer Network Equipment - GLAN | MSS-23A25-Y300-0002-00 | 0 | 2025-04-11 | UR | 101
MSS | MTC-23A35-Y300-PR-MS-00008 | Method Statement & Risk Assessment for Installation of Flight Information Display System | MSS-23A25-Y300-0008-00 | 0 | 2025-06-09 | UR | 42
WPR | MTC-23A35-ATLASLLC-PL-GE-0003 | Weekly Progress Report | DS-23A25-G000-0005-00 | 0 | 2025-04-07 | UR | 105
MS | MTC-23A25-Y300-SD-MS-00014 | Material Submittal for Car Park Management System | MS-23A25-Y300-0014-00 | 0 | 2025-06-18 | UR | 54

## Sheet2 (hidden)
Documents Submittal Plan |  |  | ​ | ​ | ​
DOCUMENTS ​ | ATLAS PLANNED DATE OF SUBMISSION​ | ACTION BY | CURRENT STATUS​ | REMARKS | SUBMITTED DATE
Low Level Design for SACS
Low Level Design for SAN
High Level Design for SACS
High Level Design for SAN
Hardwired ICD for PBB/SACS (SUBMITTED BY TCA/JV)
Software ICD for BLTS/BHS
Software ICD for SMIS/IVA (T & T)
Traceability Matrix for CSE
Traceability Matrix for FR
Traceability Matrix for LPR
Traceability Matrix for BLTS
Traceability Matrix for LAN
Traceability Matrix for SACS
Traceability Matrix for SAN
Traceability Matrix for SMIS
Traceability Matrix for VSS
System Design Document for GEMS
System Design Document for SIEM

## Change LOG (hidden)
REVISION DATE | REQUESTED BY (TCAJV) | REQUESTED BY (ATLAS) | SS NUMBER | DOC TYPE | DOCUMENT NAME | ACTION | REMARKS
|  |  | SS-19872 | MAR | Material Approval Request for ACVIS (Alternative for Gate Barrier Only) | ADDITION
|  |  | SS-19873 | MAR | Material Approval Request for Network Switches for Passport Control Area | ADDITION
|  |  | SS-19927 | MAR | Material Approval Request for NAS Hard Disk -Tech Refresh | ADDITION
|  |  | SS-20035 | MAR | Material Approval Request for FR Camera Lens | ADDITION
|  |  | SS-20108 | MAR | Material Approval Request VSS - Accessories & Brackets Vol 3 | ADDITION
|  |  | SS-20133 | MAR | Material Approval Request for Break Glass Unit for SACS | ADDITION
|  |  | SS-12829 | LLD | Low Level Design for ACVIS | DELETION | LLD - LPR & ACVIS Have been merged to one document
2017-09-03 |  |  | SS-16262 | MAR | Material Approval Request for CSE Vol. 2 | DELETION | Submitted for cancellation and deleted from log after confirming with JV
2017-09-03 |  |  | SS-16263 | MAR | Material Approval Request for Storage - NAS - Vol. 2 | DELETION | Submitted for cancellation and deleted from log after confirming with JV
2017-09-12 |  |  | SS-17216 | SICD | Software ICD for SMIS/ATRS | DELETION | As per Murali Instructed / Submitted by Jv and it is Code 2
|  |  |  | CMS | Commissioning Method Statement for LAN | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for SACS | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for BLTS | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for SMIS | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for SAN | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for VSS | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for CSE | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for LPR | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | CMS | Commissioning Method Statement for ACVIS | DELETION | Changed the description to Precommissioning Test Procedure on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for LAN | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for CSE | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for SAN | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for VSS | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for SACS | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for LPR | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for ACVIS | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for BLTS | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | I-SAT | Initial Site Acceptance Procedure (I-SAT) for G-EMS | ADDITION | Newly Added on 12 Oct 2017
|  |  |  | HLD/ITP | HICD Interface Testing Procedure (Reference to existing HICD IVTP's) | ADDITION | Newly Added on 12 Oct 2017
2017-11-02 |  |  | SS-20833 | MAR | Material Approval Request for Single Phase Boom Barrier | ADDITION | Newly Added on 2nd Nov 2017
2017-12-06 |  |  | SS-21036 | MAR | Material Approval Request for SOC KVM Solution | ADDITION | Newly Added on 6th Nov 2017
2017-12-06 |  |  | SS-21213 | MAR | Material Approval Request for SIEM-LAN VOL 1 | ADDITION | Newly Added on 6th Dec 2017
2017-12-06 |  |  | SS-21214 | MAR | Material Approval Request for Master Clock – Gov. Network | ADDITION | Newly Added on 6th Dec 2017
2017-12-19 |  |  | SS-21268 | SICD | Software ICD for SMIS/BLTS | ADDITION | Newly Added on 19th Dec 2017
2017-12-17 |  |  | SS-21271 | MAR | Material Approval Request for Occupancy sensor for SACS controlled LET | ADDITION | Newly Added on 17th Dec 2017
2017-12-17 |  |  | SS-21272 | MAR | Material Approval Request for LAN Equipment for BP42 | ADDITION | Newly Added on 17th Dec 2017
2018-01-04 |  |  | SS-21309 | EJ | Engineering Judgment for the firestop application of embedded junction box in concrete block wall | ADDITION
|  |  | SS-21214 | MAR | Material Approval Request for Master Clock – Gov. Network | DELETION | Deleted as pert the Leter :- MTB/TCA/ATLAS/L/000442
|  |  | SS-21556 | MS | Installation Method Statement for SOC Videowall System | ADDITION | Newly Added on 19 th Feb 2018
|  |  | SS-21557 | ITP | Inspection and Test Plan for SOC Videowall System | ADDITION | Newly Added on 19th Feb 2018
2018-09-19 |  |  | SS-13385 | EDI | Electronic Data Interchange for BIM Implementation | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12841 | RAM | RAM Calculation for ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12854 | ITP | Inspection and Testing Plan for ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-14252 | ITP (*) | Inspection and Testing Plan for Drilling and Installation of Anchor in Hollow Core Slab | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-14254 | ITP (*) | Inspection and Testing Plan for Identification of Security System | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-11989 | SFATP | Standalone Functional Acceptance Test Procedure for IVA | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-11990 | SFATP | Standalone Functional Acceptance Test Procedure for FR | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12005 | SFATP | Standalone Functional Acceptance Test Procedure for ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12863 | SICD | Software ICD for SMIS/ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12866 | SICD (Ext.) | Software ICD for IB/SMIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12867 | SICD (Ext.) | Software ICD for LET/SMIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12868 | SICD (Ext.) | Software ICD for BMS/SMIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12870 | SICD (Ext.) | Software ICD for FAS/SMIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12872 | SICD (Ext.) | Software ICD for SACS/CPMS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12874 | SICD (Ext.) | Software ICD for SMIS/LCS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12876 | SICD (Ext.) | Software ICD for SMIS/PAVE | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-14301 | SICD (Ext.) | Software ICD for SACS/ HR | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-11995 | IVTP | Interface Verification Test Procedure for SMIS/ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-12907 | IVTP | Interface Verification Test Procedure Network/ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-14313 | SIDDTP | Software Interface Detail Document Test Plan for Life Safety (SMIS-FAS-PAS-LET-SACS-VSS-LCS-IB) | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-13341 | CMP | Configuration Management Plan for ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-13352 | MS | Installation Method Statement for ACVIS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-15897 | TM | Traceability Matrix for IVA | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-17214 | SFATP | Standalone Acceptance Test Procedure for GEMS | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-17215 | SFATP | Stand Alone Acceptance Test Procedure for SIEM | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-14325 | TCP | Testing & Commissioning Procedure for SMIS (Pre-Commissioning Phase) | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-14328 | TCP | Testing & Commissioning Procedure for ACVIS (Pre-Commissioning Phase) | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-20825 | I-SAT | Testing & Commissioning Procedure for ACVIS (I-SAT Phase) | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-20828 | HICD/ITP | HICD Interface Testing Procedure (Reference to existing HICD IVTP's) | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-22675 | I-SAT | Testing & Commissioning Procedure for SACS (I-SAT Phase) Volume - 2 | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-16856 | DS | Government LAN MTB - Labelling Scheme | DELETION
2018-09-19 |  |  | SS-12020 | MAR (old) | Material Approval Request for STORAGE | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-11998 | SFATP | Standalone Functional Acceptance Test Procedure for LPR | DELETION | As per PM Instructed
2018-09-19 |  |  | SS-14314 | SIDDTP | Software Interface Detail Document Test Procedure for Bag Track (SMIS-BLTS-VSS-T&T) | UPDATED | Description has been changed to SIT
2018-09-19 |  |  | SS-14315 | SIDDTP | Software Interface Detail Document Test Procedure for Screening (SMIS-PBSS-VSS-FR) | UPDATED | Description has been changed to SIT
2018-09-19 |  |  | SS-14316 | SIDDTP | Software Interface Detail Document Test Procedure for Security (SMIS-SACS-VSS-FR-IVA-LET-T&T,BLTS) | UPDATED | Description has been changed to SIT
2018-09-19 |  |  | SS-14317 | SIDDTP | Software Interface Detail Document Test Procedure for Curbside (SMIS-LPR-ACVIS-SACS-VSS) | UPDATED | Description has been changed to SIT
2018-09-20 |  |  | SS-15494 | I-SAT (T) | Testing & Commissioning Procedure for TETRA & LTE (I-SAT Phase) | DELETION | As per "TETRA BASE STATION (TBS) Acceptance & Commissioning Tests" document
2018-12-20 |  |  | SS-13385 | EDI | Electronic Data Interchange for BIM Implementation | DELETION | Not Required
2018-12-20 |  |  | SS-12841 | RAM | RAM Calculation for ACVIS | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-12854 | ITP | Inspection and Testing Plan for ACVIS | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-14252 | ITP (*) | Inspection and Testing Plan for Drilling and Installation of Anchor in Hollow Core Slab | DELETION | Not Required
2018-12-20 |  |  | SS-14254 | ITP (*) | Inspection and Testing Plan for Identification of Security System | DELETION | Not Required
2018-12-20 |  |  | SS-11989 | SFATP | Standalone Functional Acceptance Test Procedure for IVA | DELETION | Not Required
2018-12-20 |  |  | SS-11990 | SFATP | Standalone Functional Acceptance Test Procedure for FR | DELETION | Not Required
2018-12-20 |  |  | SS-12005 | SFATP | Standalone Functional Acceptance Test Procedure for ACVIS | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-12863 | SICD | Software ICD for SMIS/ACVIS | DELETION | Not Required
2018-12-20 |  |  | SS-12866 | SICD (Ext.) | Software ICD for IB/SMIS | DELETION | Not Required
2018-12-20 |  |  | SS-12867 | SICD (Ext.) | Software ICD for LET/SMIS | DELETION | Not Required
2018-12-20 |  |  | SS-12868 | SICD (Ext.) | Software ICD for BMS/SMIS | DELETION | Not Required
2018-12-20 |  |  | SS-12870 | SICD (Ext.) | Software ICD for FAS/SMIS | DELETION | Not Required
2018-12-20 |  |  | SS-12872 | SICD (Ext.) | Software ICD for SACS/CPMS | DELETION | Not Required
2018-12-20 |  |  | SS-12874 | SICD (Ext.) | Software ICD for SMIS/LCS | DELETION | Not Required
2018-12-20 |  |  | SS-12876 | SICD (Ext.) | Software ICD for SMIS/PAVE | DELETION | Not Required
2018-12-20 |  |  | SS-14301 | SICD (Ext.) | Software ICD for SACS/ HR | DELETION | Not Required
2018-12-20 |  |  | SS-11995 | IVTP | Interface Verification Test Procedure for SMIS/ACVIS | DELETION | Not Required
2018-12-20 |  |  | SS-12907 | IVTP | Interface Verification Test Procedure Network/ACVIS | DELETION | Not Required
2018-12-20 |  |  | SS-14313 | SIDDTP | Software Interface Detail Document Test Plan for Life Safety (SMIS-FAS-PAS-LET-SACS-VSS-LCS-IB) | DELETION | Not Required
2018-12-20 |  |  | SS-13341 | CMP | Configuration Management Plan for ACVIS | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-13352 | MS | Installation Method Statement for ACVIS | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-15897 | TM | Traceability Matrix for IVA | DELETION | Not Required
2018-12-20 |  |  | SS-17214 | SFATP | Standalone Acceptance Test Procedure for GEMS | DELETION | Not Required
2018-12-20 |  |  | SS-17215 | SFATP | Stand Alone Acceptance Test Procedure for SIEM | DELETION | Not Required
2018-12-20 |  |  | SS-14325 | TCP | Testing & Commissioning Procedure for SMIS (Pre-Commissioning Phase) | DELETION | Not Required
2018-12-20 |  |  | SS-14328 | TCP | Testing & Commissioning Procedure for ACVIS (Pre-Commissioning Phase) | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-20825 | I-SAT | Testing & Commissioning Procedure for ACVIS (I-SAT Phase) | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-20828 | HICD/ITP | HICD Interface Testing Procedure (Reference to existing HICD IVTP's) | DELETION | Not Required
2018-12-20 |  |  |  | STE | Spare parts, Tools & Extra (STE) material - Access Control Vehicle Identification System (ACVIS) | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-22675 | I-SAT | Testing & Commissioning Procedure for SACS (I-SAT Phase) Volume - 2 | DELETION | Not Required
2018-12-20 |  |  | SS-16856 | DS | Government LAN MTB - Labelling Scheme | DELETION | As per PM Instructed /Submitted for Cancellation
2018-12-20 |  |  | SS-12020 | MAR (old) | Material Approval Request for STORAGE | DELETION | Not Required
2018-12-20 |  |  | SS-11998 | SFATP | Standalone Functional Acceptance Test Procedure for LPR | DELETION | Not Required
2018-12-20 |  |  | SS-13330 | TP | Training Plan | DELETION | Submitting by JV with our input . Not to be submitted.
2018-12-20 |  |  | SS-15903 | TM | Traceability Matrix for ACVIS | DELETION | Removed as per BP 66.2
2018-12-20 |  |  | SS-13335 | CMP | Configuration Management Plan for IVA | DELETION | To be REMOVED. Combined submission done with FR
2018-12-20 |  |  | SS-14311 | SIDD | System Interface Detail Document for Security (SMIS-SACS-VSS-FR-IVA-LET-T&T) | DELETION | To be Removed as per received Code 5 Commands of other SIDD
2018-12-20 |  |  | SS-14312 | SIDD | System Interface Detail Document for Curbside (SMIS-LPR-ACVIS-SACS-VSS) | DELETION | To be Removed as per received Code 5 Commands of other SIDD
2018-12-20 |  |  | SS-14317 | I-SAT | System Integration Test Proecedure for Curbside (SMIS-LPR-ACVIS-SACS) | DELETION | To be Removed as there is no more integration with Curbside system with SMIS
2018-12-20 |  |  | SS-12839 | RAM | RAM Calculation for BLTS | DELETION | Has been Combined as SMIS, VSS, SACS & BLTS
2018-12-20 |  |  | SS-12843 | RAM | RAM Calculation for CSE | DELETION | Has been Combined as LAN, , SAN, NAS & CSE
2018-12-20 |  |  | SS-12838 | RAM | RAM Calculation for FR | DELETION | Has been Combined as LPR, FR & IVA
2018-12-20 |  |  | SS-12837 | RAM | RAM Calculation for IVA | DELETION | Has been Combined as LPR, FR & IVA
2018-12-20 |  |  | SS-12836 | RAM | RAM Calculation for SACS | DELETION | Has been Combined as SMIS, VSS, SACS & BLTS
2018-12-20 |  |  | SS-12844 | RAM | RAM Calculation for SAN & NAS | DELETION | Has been Combined as LAN, , SAN, NAS & CSE
2018-12-20 |  |  | SS-12835 | RAM | RAM Calculation for VSS | DELETION | Has been Combined as SMIS, VSS, SACS & BLTS
2018-12-20 |  |  | SS-15492 | TP (T) | Training Plan | DELETION | Submitting by JV with our input . Not to be submitted.
2018-12-20 |  |  | SS-13351 | MS | Installation Method Statement for LPR, Gate Barrier and Intercom. | UPDATED | Changed Title "Installation Method Statement for LPR, Gate Barrier and Intercom"
2018-12-20 |  |  | SS-12853 | ITP | Inspection and Testing Plan for LPR, Gate Barrier and Intercom. | UPDATED | Changed Title "Inspection and Testing Plan for LPR, Gate Barrier and Intercom"
2018-12-20 |  |  | SS-14304 | IVTP | Interface Verification Test Procedure for SMIS/T&T | DELETION | SMIS-IVA-T&T does not require a separate IVTP , and would be having only SIDD.
2019-04-17 |  |  | SS-23791 | MAR | Matreial Approval Request for SMIS Workstation | ADDITION | As per Nidhal and Murali newly added

## Sheet1 (hidden)
Contractual Review Time
Rev. 00 | < 21 Days
Rev. 01 | < 14 Days
Rev. 02 and above | < 7 Days

## Data (hidden)
Data Date | 2025-08-12 |  | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856 | <=45863 | <=45870 | <=45877
Cutoff | 2025-08-08 |  | >45786 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849 | >45856 | >45863 | >45870
|  |  | W -12 | W -11 | W -10 | W -9 | W -8 | W -7 | W -6 | W -5 | W -4 | W -3 | W -2 | W -1 | This Week
|  |  | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08
|  | Submitted | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856 | <=45863 | <=45870 | <=45877
APPROVED | 3237 |  | >0 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849 | >45856 | >45863 | >45870
UNDER REVIEW | 125 |  | Over | 11 Weeks | 10 Weeks | 9 Weeks | 8 Weeks | 7 Weeks | 6 Weeks | 5 Weeks | 4 Weeks | 3 Weeks | 2 Weeks | 1 Weeks | This Week
REJECTED | 20 | Pending Review | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
REV. 0 TO GO | 12 | Cumulative | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!