## ATLAS AD-LOG
| Project Name | Constuction of East Midfiled Cargo Terminal Facility at ZIA
| Contract No | ADAC/025/2023
| Sub Contractor | ATLAS SECURITY
| Clinet | ADA | [25 empty] | Revision 00 | [5 empty] | Revision 01 | [5 empty] | Revision 02 | [5 empty] | Revision 03 | [5 empty] | Revision 04 | [5 empty] | Revision 05 | [5 empty] | Revision 06 | [5 empty] | Revision 07
| Contractor | RAQ Contracting Co LLC | [16 empty] | 2025-08-05 | CURRENT STATUS OF THE DRAWING | [7 empty] | SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | SUBMISSION DETAILS |  |  | STATUS DETAILS |  |  | SUBMISSION DETAILS |  |  | STATUS DETAILS
| BUILDINGS NAME | PROGRAM NAME | LAST 4 DIGITS OF CONTRACT NO. | DISCIPLINE CODE | LEVEL | AREA CODE | PART/SECTOR/SEQUENCE NO. | REVISION | DRAWING TYPE | DRAWING SCALE | SYSTEM | SUB SYSTEM | IFC DRAWING NUMBER | ATLAS DRAWING NUMBER | DESCRIPTION | PLANNED DATE FOR SUBMISSION | FORECAST DATE | REVIEW TIME (DAYS) | REVIEW TIME OVERDUE DAYS | REVISION | SUBMISSION DTAE | TRANSMITTAL NUMBER | LATEST STATUS | ENGINEER COMMENT DATE | ENGINEER TRANSMITTAL NUMBER | CURRENT STATUS | REJECTED BY | CON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | HILL COMMENT | DATE | HILL COMMENT | CON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | AECOM COMMENT | DATE | AECOM COMMENT | CON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | AECOM COMMENT | DATE | AECOM COMMENT | CON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | AECOM COMMENT | DATE | AECOM COMMENT | CON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | AECOM COMMENT | DATE | AECOM COMMENT | CON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | AECOM COMMENT | DATE | AECOM COMMENT | CON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | AECOM COMMENT | DATE | AECOM COMMENT | SUBCON REFERENCE | DATE SUBMITTED | ENGINEER REFERENCE | AECOM COMMENT | DATE | AECOM COMMENT
DAYS_UR | Column1 | PGN | CN | DIC | LR | SSA | SQN | REV | 11 | 12 | Sys | SubSystem | DWGNR | ATLASDWGNR | DESCRIPTION | 20 | 21 | REV_TIME | REV_OD | 25 | S_DATE | 27 | 28 | C_DATE | 292 | C_STATUS | BY2 | AREF_0 | ASUB_0 | JVREF_0 | JVC_0 | JVCD_0 | CMAC_0 | AREF_1 | ASUB_1 | JVREF_1 | JVC_1 | JVCD_1 | CMAC_1 | AREF_2 | ASUB_2 | JVREF_2 | JVC_2 | JVCD_2 | CMAC_2 | AREF_3 | ASUB_3 | JVREF_3 | JVC_3 | JVCD_3 | CMAC_3 | AREF_4 | ASUB_4 | JVREF_4 | JVC_4 | JVCD_4 | CMAC_4 | AREF_5 | ASUB_5 | JVREF_5 | JVC_5 | JVCD_5 | CMAC_5 | AREF_6 | ASUB_6 | JVREF_6 | JVC_6 | JVCD_6 | CMAC_6 | AREF_7 | ASUB_7 | JVREF_7 | JVC_7 | JVCD_7 | CMAC_7
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 00001 | 00 | SD | 1:500 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1200-RB | MTC-23A25-Y100-L000-1399-00001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - OVERALL | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 01001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1201-RB | MTC-23A25-Y100-L000-1399-01001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 01 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 02001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1202-RB | MTC-23A25-Y100-L000-1399-02001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 02 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 03001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1203-RB | MTC-23A25-Y100-L000-1399-03001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 03 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 04001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1204-RB | MTC-23A25-Y100-L000-1399-04001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 04 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 05001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1205-RB | MTC-23A25-Y100-L000-1399-05001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 05 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 06001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1206-RB | MTC-23A25-Y100-L000-1399-06001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 06 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 07001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1207-RB | MTC-23A25-Y100-L000-1399-07001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 07 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 08001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1208-RB | MTC-23A25-Y100-L000-1399-08001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 08 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0011-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0011-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 09001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1209-RB | MTC-23A25-Y100-L000-1399-09001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 09 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 10001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1210-RB | MTC-23A25-Y100-L000-1399-10001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 10 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 11001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1211-RB | MTC-23A25-Y100-L000-1399-11001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 11 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 12001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1212-RB | MTC-23A25-Y100-L000-1399-12001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 12 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 13001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1213-RB | MTC-23A25-Y100-L000-1399-13001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 13 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 14001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1214-RB | MTC-23A25-Y100-L000-1399-14001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 14 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 15001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1215-RB | MTC-23A25-Y100-L000-1399-15001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 15 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 16001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1216-RB | MTC-23A25-Y100-L000-1399-16001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 16 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 17001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1217-RB | MTC-23A25-Y100-L000-1399-17001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 17 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L000 | 1399 | 18001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1218-RB | MTC-23A25-Y100-L000-1399-18001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 18 | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0012-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L001 | 1399 | 00001 | 00 | SD | 1:500 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L1-P-1200-RB | MTC-23A25-Y100-L001-1399-00001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 1 - OVERALL |  |  | 33 | 12 | 00 | 2025-06-11 | SDS-23A25-Y100-0005-00 | Code 2 | 2025-07-14 | SDS-23A25-Y100-0027-00 | Code 2 |  | SDS-23A25-Y100-0005-00 | 2025-06-11 | SDS-23A25-Y100-0027-00 | Code 2 | 2025-07-14 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L001 | 1399 | 05001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L1-P-1201-RB | MTC-23A25-Y100-L001-1399-05001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 1 - PART 05 |  |  | 33 | 12 | 00 | 2025-06-11 | SDS-23A25-Y100-0005-00 | Code 2 | 2025-07-14 | SDS-23A25-Y100-0027-00 | Code 2 |  | SDS-23A25-Y100-0005-00 | 2025-06-11 | SDS-23A25-Y100-0027-00 | Code 2 | 2025-07-14 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L001 | 1399 | 18001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L1-P-1201-RB | MTC-23A25-Y100-L001-1399-18001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 1 - PART 18 |  |  | 33 | 12 | 00 | 2025-06-11 | SDS-23A25-Y100-0005-00 | Code 2 | 2025-07-14 | SDS-23A25-Y100-0027-00 | Code 2 |  | SDS-23A25-Y100-0005-00 | 2025-06-11 | SDS-23A25-Y100-0027-00 | Code 2 | 2025-07-14 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L002 | 1399 | 00001 | 00 | SD | 1:500 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L2-P-1200-RB | MTC-23A25-Y100-L002-1399-00001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 2 - OVERALL |  |  | 55 | 34 | 00 | 2025-06-11 | SDS-23A25-Y100-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0006-00 | 2025-06-11 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L002 | 1399 | 03001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L2-P-1201-RB | MTC-23A25-Y100-L002-1399-03001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 2 - PART 03 |  |  | 55 | 34 | 00 | 2025-06-11 | SDS-23A25-Y100-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0006-00 | 2025-06-11 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L002 | 1399 | 04001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L2-P-1202-RB | MTC-23A25-Y100-L002-1399-04001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 2 - PART 04 |  |  | 55 | 34 | 00 | 2025-06-11 | SDS-23A25-Y100-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0006-00 | 2025-06-11 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L002 | 1399 | 05001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L2-P-1203-RB | MTC-23A25-Y100-L002-1399-05001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 2 - PART 05 |  |  | 55 | 34 | 00 | 2025-06-11 | SDS-23A25-Y100-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0006-00 | 2025-06-11 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L002 | 1399 | 06001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L2-P-1204-RB | MTC-23A25-Y100-L002-1399-06001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 2 - PART 06 |  |  | 55 | 34 | 00 | 2025-06-11 | SDS-23A25-Y100-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0006-00 | 2025-06-11 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | L002 | 1399 | 12001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L2-P-1205-RB | MTC-23A25-Y100-L002-1399-12001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 2 - PART 12 |  |  | 55 | 34 | 00 | 2025-06-11 | SDS-23A25-Y100-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0006-00 | 2025-06-11 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 00001 | 00 | SD | 1:500 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1200-RB | MTC-23A25-Y108-L000-1399-00001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - OVERALL |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0004-01 | Code 3 | 2025-06-18 | SDS-23A25-Y100-0004-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0004-00 | 2025-05-23 | SDS-23A25-Y100-0004-00 | Code 3 | 2025-06-18 | Code 3 | SDS-23A25-Y100-0004-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 01001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1201-RB | MTC-23A25-Y108-L000-1399-01001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 01 |  |  | 4 | --- | 00 | 2025-08-01 | SDS-23A25-Y100-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0014-00 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 02001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1202-RB | MTC-23A25-Y108-L000-1399-02001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 02 |  |  | 4 | --- | 00 | 2025-08-01 | SDS-23A25-Y100-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0014-00 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 03001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1203-RB | MTC-23A25-Y108-L000-1399-03001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 03 |  |  | 4 | --- | 00 | 2025-08-01 | SDS-23A25-Y100-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0014-00 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 04001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1204-RB | MTC-23A25-Y108-L000-1399-04001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 04 |  |  | 4 | --- | 00 | 2025-08-01 | SDS-23A25-Y100-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0014-00 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 05001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1205-RB | MTC-23A25-Y108-L000-1399-05001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 05 |  |  | 4 | --- | 00 | 2025-08-01 | SDS-23A25-Y100-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0014-00 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 06001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1206-RB | MTC-23A25-Y108-L000-1399-06001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 06 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 07001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1207-RB | MTC-23A25-Y108-L000-1399-07001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 07 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 08001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1208-RB | MTC-23A25-Y108-L000-1399-08001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 08 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 09001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1209-RB | MTC-23A25-Y108-L000-1399-09001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 09 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 10001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1210-RB | MTC-23A25-Y108-L000-1399-10001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 10 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 11001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1211-RB | MTC-23A25-Y108-L000-1399-11001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 11 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 12001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1212-RB | MTC-23A25-Y108-L000-1399-12001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 12 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 13001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1213-RB | MTC-23A25-Y108-L000-1399-13001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 13 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 14001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1214-RB | MTC-23A25-Y108-L000-1399-14001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 14 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 15001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1215-RB | MTC-23A25-Y108-L000-1399-15001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 15 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 16001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1216-RB | MTC-23A25-Y108-L000-1399-16001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 16 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 17001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1217-RB | MTC-23A25-Y108-L000-1399-17001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 17 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L000 | 1399 | 18001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1218-RB | MTC-23A25-Y108-L000-1399-18001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 18 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0003-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0003-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0003-00 | 2025-05-23 | SDS-23A25-Y100-0003-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0003-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L001 | 1399 | 00001 | 00 | SD | 1:500 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L1-P-1200-RB | MTC-23A25-Y108-L001-1399-00001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 1 - OVERALL | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0132-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0132-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0009-00 | 2025-07-15 | SDS-23A25-Y100-0132-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0132-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L001 | 1399 | 05001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L1-P-1201-RB | MTC-23A25-Y108-L001-1399-05001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 1 - PART 05 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0132-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0132-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0009-00 | 2025-07-15 | SDS-23A25-Y100-0132-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0132-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L001 | 1399 | 18001 |  | SD | 1:100 | Security System | SACS |  | MTC-23A25-Y108-L001-1399-18001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 1 - PART 18 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0132-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0132-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0009-00 | 2025-07-15 | SDS-23A25-Y100-0132-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0132-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L002 | 1399 | 00001 | 00 | SD | 1:500 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L2-P-1200-RB | MTC-23A25-Y108-L002-1399-00001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 2 - OVERALL | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0133-01 | Code 3 | 2025-07-23 | SDS-23A25-Y100-0133-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0010-00 | 2025-07-15 | SDS-23A25-Y100-0133-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y100-0133-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L002 | 1399 | 03001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L2-P-1201-RB | MTC-23A25-Y108-L002-1399-03001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 2 - PART 03 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0133-01 | Code 3 | 2025-07-23 | SDS-23A25-Y100-0133-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0010-00 | 2025-07-15 | SDS-23A25-Y100-0133-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y100-0133-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L002 | 1399 | 04001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L2-P-1202-RB | MTC-23A25-Y108-L002-1399-04001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 2 - PART 04 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0133-01 | Code 3 | 2025-07-23 | SDS-23A25-Y100-0133-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0010-00 | 2025-07-15 | SDS-23A25-Y100-0133-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y100-0133-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L002 | 1399 | 05001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L2-P-1203-RB | MTC-23A25-Y108-L002-1399-05001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 2 - PART 05 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0133-01 | Code 3 | 2025-07-23 | SDS-23A25-Y100-0133-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0010-00 | 2025-07-15 | SDS-23A25-Y100-0133-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y100-0133-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L002 | 1399 | 06001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L2-P-1204-RB | MTC-23A25-Y108-L002-1399-06001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 2 - PART 06 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0133-01 | Code 3 | 2025-07-23 | SDS-23A25-Y100-0133-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0010-00 | 2025-07-15 | SDS-23A25-Y100-0133-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y100-0133-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | L002 | 1399 | 12001 |  | SD | 1:100 | Security System | SACS |  | MTC-23A25-Y108-L002-1399-12001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 2 - PART 12 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0133-01 | Code 3 | 2025-07-23 | SDS-23A25-Y100-0133-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0010-00 | 2025-07-15 | SDS-23A25-Y100-0133-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y100-0133-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 00001 | 00 | SD | 1:500 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1000-RB | MTC-23A25-Y300-L000-1399-00001 | ICT (SCN) LAYOUTS - LEVEL 0 - OVERALL | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 01001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1001-RB | MTC-23A25-Y300-L000-1399-01001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 01 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 02001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1002-RB | MTC-23A25-Y300-L000-1399-02001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 02 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 03001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1003-RB | MTC-23A25-Y300-L000-1399-03001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 03 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 04001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1004-RB | MTC-23A25-Y300-L000-1399-04001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 04 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 05001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1005-RB | MTC-23A25-Y300-L000-1399-05001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 05 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 06001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1006-RB | MTC-23A25-Y300-L000-1399-06001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 06 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 07001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1007-RB | MTC-23A25-Y300-L000-1399-07001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 07 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 08001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1008-RB | MTC-23A25-Y300-L000-1399-08001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 08 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 09001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1009-RB | MTC-23A25-Y300-L000-1399-09001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 09 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 10001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1010-RB | MTC-23A25-Y300-L000-1399-10001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 10 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 11001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1011-RB | MTC-23A25-Y300-L000-1399-11001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 11 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 12001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1012-RB | MTC-23A25-Y300-L000-1399-12001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 12 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 13001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1013-RB | MTC-23A25-Y300-L000-1399-13001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 13 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 14001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1014-RB | MTC-23A25-Y300-L000-1399-14001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 14 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 15001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1015-RB | MTC-23A25-Y300-L000-1399-15001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 15 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 16001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1016-RB | MTC-23A25-Y300-L000-1399-16001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 16 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 17001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1017-RB | MTC-23A25-Y300-L000-1399-17001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 17 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L000 | 1399 | 18001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L0-P-1018-RB | MTC-23A25-Y300-L000-1399-18001 | ICT (SCN) LAYOUTS - LEVEL 0 - PART 18 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L001 | 1399 | 00001 | 00 | SD | 1:500 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L1-P-1000-RB | MTC-23A25-Y300-L001-1399-00001 | ICT (SCN) LAYOUTS - LEVEL 1 - OVERALL | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L001 | 1399 | 05001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L1-P-1001-RB | MTC-23A25-Y300-L001-1399-05001 | ICT (SCN) LAYOUTS - LEVEL 1 - PART 05 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L002 | 1399 | 00001 | 00 | SD | 1:500 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L2-P-1000-RB | MTC-23A25-Y300-L002-1399-00001 | ICT (SCN) LAYOUTS - LEVEL 2 - OVERALL | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L002 | 1399 | 03001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L2-P-1001-RB | MTC-23A25-Y300-L002-1399-03001 | ICT (SCN) LAYOUTS - LEVEL 2 - PART 03 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L002 | 1399 | 04001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L2-P-1002-RB | MTC-23A25-Y300-L002-1399-04001 | ICT (SCN) LAYOUTS - LEVEL 2 - PART 04 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L002 | 1399 | 05001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L2-P-1003-RB | MTC-23A25-Y300-L002-1399-05001 | ICT (SCN) LAYOUTS - LEVEL 2 - PART 05 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y300 | L002 | 1399 | 06001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1399-T100-DR-L2-P-1004-RB | MTC-23A25-Y300-L002-1399-06001 | ICT (SCN) LAYOUTS - LEVEL 2 - PART 06 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 00001 | 00 | SD | 1:500 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1100-RB | MTC-23A25-Y307-L000-1399-00001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - OVERALL | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 01001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1101-RB | MTC-23A25-Y307-L000-1399-01001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 01 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 02001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1102-RB | MTC-23A25-Y307-L000-1399-02001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 02 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 03001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1103-RB | MTC-23A25-Y307-L000-1399-03001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 03 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 04001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1104-RB | MTC-23A25-Y307-L000-1399-04001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 04 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 05001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1105-RB | MTC-23A25-Y307-L000-1399-05001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 05 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 06001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1106-RB | MTC-23A25-Y307-L000-1399-06001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 06 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 07001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1107-RB | MTC-23A25-Y307-L000-1399-07001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 07 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 08001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1108-RB | MTC-23A25-Y307-L000-1399-08001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 08 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0014-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 09001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1109-RB | MTC-23A25-Y307-L000-1399-09001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 09 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 10001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1110-RB | MTC-23A25-Y307-L000-1399-10001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 10 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 11001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1111-RB | MTC-23A25-Y307-L000-1399-11001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 11 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 12001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1112-RB | MTC-23A25-Y307-L000-1399-12001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 12 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 13001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1113-RB | MTC-23A25-Y307-L000-1399-13001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 13 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 14001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1114-RB | MTC-23A25-Y307-L000-1399-14001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 14 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 15001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1115-RB | MTC-23A25-Y307-L000-1399-15001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 15 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 16001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1116-RB | MTC-23A25-Y307-L000-1399-16001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 16 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 17001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1117-RB | MTC-23A25-Y307-L000-1399-17001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 17 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L000 | 1399 | 18001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L0-P-1118-RB | MTC-23A25-Y307-L000-1399-18001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 - PART 18 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0015-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L001 | 1399 | 00001 | 00 | SD | 1:500 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L1-P-1100-RB | MTC-23A25-Y307-L001-1399-00001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 1 - OVERALL | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0016-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L001 | 1399 | 05001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L1-P-1101-RB | MTC-23A25-Y307-L001-1399-05001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 1 - PART 05 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0016-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L001 | 1399 | 08001 |  | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) |  | MTC-23A25-Y307-L001-1399-08001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 1 - PART 08 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0016-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L001 | 1399 | 13001 |  | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) |  | MTC-23A25-Y307-L001-1399-13001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 1 - PART 13 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0016-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L002 | 1399 | 00001 | 00 | SD | 1:500 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L2-P-1100-RB | MTC-23A25-Y307-L002-1399-00001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 2 - OVERALL | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0017-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L002 | 1399 | 03001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L2-P-1101-RB | MTC-23A25-Y307-L002-1399-03001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 2 - PART 03 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0017-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L002 | 1399 | 04001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L2-P-1102-RB | MTC-23A25-Y307-L002-1399-04001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 2 - PART 04 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0017-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L002 | 1399 | 05001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L2-P-1103-RB | MTC-23A25-Y307-L002-1399-05001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 2 - PART 05 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0017-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L002 | 1399 | 06001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1399-T100-DR-L2-P-1104-RB | MTC-23A25-Y307-L002-1399-06001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 2 - PART 06 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0017-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y307 | L002 | 1399 | 12001 |  | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) |  | MTC-23A25-Y307-L002-1399-12001 | COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 2 - PART 12 | 2025-07-12 |  | 19 | --- | 00 | 2025-07-17 | SDS-23A25-Y300-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0017-00 | 2025-07-17 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 00001 | 00 | SD | 1:500 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1400-RA | MTC-23A25-Y204-L000-1399-00001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - OVERALL |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0105-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0105-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0003-00 | 2025-07-15 | SDS-23A25-Y000-0105-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0105-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 01001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1401-RA | MTC-23A25-Y204-L000-1399-01001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 01 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0105-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0105-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0003-00 | 2025-07-15 | SDS-23A25-Y000-0105-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0105-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 02001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1402-RA | MTC-23A25-Y204-L000-1399-02001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 02 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0105-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0105-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0003-00 | 2025-07-15 | SDS-23A25-Y000-0105-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0105-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 03001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1403-RA | MTC-23A25-Y204-L000-1399-03001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 03 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0105-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0105-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0003-00 | 2025-07-15 | SDS-23A25-Y000-0105-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0105-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 04001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1404-RA | MTC-23A25-Y204-L000-1399-04001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 04 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0105-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0105-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0003-00 | 2025-07-15 | SDS-23A25-Y000-0105-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0105-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 05001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1405-RA | MTC-23A25-Y204-L000-1399-05001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 05 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0105-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0105-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0003-00 | 2025-07-15 | SDS-23A25-Y000-0105-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0105-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 06001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1406-RA | MTC-23A25-Y204-L000-1399-06001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 06 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0111-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0111-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0009-00 | 2025-07-15 | SDS-23A25-Y000-0111-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0111-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 07001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1407-RA | MTC-23A25-Y204-L000-1399-07001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 07 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0111-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0111-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0009-00 | 2025-07-15 | SDS-23A25-Y000-0111-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0111-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 08001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1408-RA | MTC-23A25-Y204-L000-1399-08001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 08 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0111-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0111-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0009-00 | 2025-07-15 | SDS-23A25-Y000-0111-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0111-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 09001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1409-RA | MTC-23A25-Y204-L000-1399-09001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 09 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0111-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0111-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0009-00 | 2025-07-15 | SDS-23A25-Y000-0111-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0111-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 10001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1410-RA | MTC-23A25-Y204-L000-1399-10001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 10 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0111-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0111-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0009-00 | 2025-07-15 | SDS-23A25-Y000-0111-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0111-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 11001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1411-RA | MTC-23A25-Y204-L000-1399-11001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 11 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0111-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0111-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0009-00 | 2025-07-15 | SDS-23A25-Y000-0111-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0111-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 12001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1412-RA | MTC-23A25-Y204-L000-1399-12001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 12 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0112-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0112-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0010-00 | 2025-07-15 | SDS-23A25-Y000-0112-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0112-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 13001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1413-RA | MTC-23A25-Y204-L000-1399-13001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 13 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0112-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0112-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0010-00 | 2025-07-15 | SDS-23A25-Y000-0112-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0112-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 14001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1414-RA | MTC-23A25-Y204-L000-1399-14001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 14 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0112-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0112-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0010-00 | 2025-07-15 | SDS-23A25-Y000-0112-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0112-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 15001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1415-RA | MTC-23A25-Y204-L000-1399-15001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 15 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0112-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0112-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0010-00 | 2025-07-15 | SDS-23A25-Y000-0112-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0112-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 16001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1416-RA | MTC-23A25-Y204-L000-1399-16001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 16 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0112-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0112-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0010-00 | 2025-07-15 | SDS-23A25-Y000-0112-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0112-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 17001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1417-RA | MTC-23A25-Y204-L000-1399-17001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 17 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0112-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0112-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0010-00 | 2025-07-15 | SDS-23A25-Y000-0112-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0112-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L000 | 1399 | 18001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L0-P-1418-RA | MTC-23A25-Y204-L000-1399-18001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 0 - PART 18 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0112-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0112-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0010-00 | 2025-07-15 | SDS-23A25-Y000-0112-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0112-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L001 | 1399 | 00001 | 00 | SD | 1:500 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L1-P-1400-RA | MTC-23A25-Y204-L001-1399-00001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 1 - OVERALL |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0004-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L001 | 1399 | 05001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L1-P-1401-RA | MTC-23A25-Y204-L001-1399-05001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 1 - PART 05 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0004-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L001 | 1399 | 06001 | 00 | SD | 1:100 | Special System | TV |  | MTC-23A25-Y204-L001-1399-06001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 1 - PART 06 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0004-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L002 | 1399 | 00001 | 00 | SD | 1:500 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L2-P-1400-RA | MTC-23A25-Y204-L002-1399-00001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 2 - OVERALL |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0107-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0107-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0005-00 | 2025-07-15 | SDS-23A25-Y000-0107-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0107-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L002 | 1399 | 03001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L2-P-1401-RA | MTC-23A25-Y204-L002-1399-03001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 2 - PART 03 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0107-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0107-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0005-00 | 2025-07-15 | SDS-23A25-Y000-0107-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0107-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L002 | 1399 | 04001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L2-P-1402-RA | MTC-23A25-Y204-L002-1399-04001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 2 - PART 04 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0107-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0107-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0005-00 | 2025-07-15 | SDS-23A25-Y000-0107-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0107-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L002 | 1399 | 05001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L2-P-1403-RA | MTC-23A25-Y204-L002-1399-05001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 2 - PART 05 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0107-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0107-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0005-00 | 2025-07-15 | SDS-23A25-Y000-0107-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0107-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y204 | L002 | 1399 | 06001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1399-T100-DR-L2-P-1404-RA | MTC-23A25-Y204-L002-1399-06001 | MEDIA HARDWARE TV LAYOUTS - LEVEL 2 - PART 06 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0107-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0107-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0005-00 | 2025-07-15 | SDS-23A25-Y000-0107-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0107-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 00001 | 00 | SD | 1:500 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1400-RA | MTC-23A25-Y211-L000-1399-00001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - OVERALL | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0108-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0108-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0006-00 | 2025-07-15 | SDS-23A25-Y000-0108-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0108-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 01001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1401-RA | MTC-23A25-Y211-L000-1399-01001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 01 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0108-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0108-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0006-00 | 2025-07-15 | SDS-23A25-Y000-0108-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0108-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 02001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1402-RA | MTC-23A25-Y211-L000-1399-02001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 02 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0108-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0108-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0006-00 | 2025-07-15 | SDS-23A25-Y000-0108-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0108-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 03001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1403-RA | MTC-23A25-Y211-L000-1399-03001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 03 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0108-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0108-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0006-00 | 2025-07-15 | SDS-23A25-Y000-0108-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0108-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 04001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1404-RA | MTC-23A25-Y211-L000-1399-04001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 04 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0108-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0108-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0006-00 | 2025-07-15 | SDS-23A25-Y000-0108-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0108-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 05001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1405-RA | MTC-23A25-Y211-L000-1399-05001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 05 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0108-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0108-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0006-00 | 2025-07-15 | SDS-23A25-Y000-0108-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0108-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 06001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1406-RA | MTC-23A25-Y211-L000-1399-06001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 06 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0113-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0113-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0011-00 | 2025-07-15 | SDS-23A25-Y000-0113-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0113-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 07001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1407-RA | MTC-23A25-Y211-L000-1399-07001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 07 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0113-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0113-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0011-00 | 2025-07-15 | SDS-23A25-Y000-0113-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0113-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 08001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1408-RA | MTC-23A25-Y211-L000-1399-08001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 08 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0113-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0113-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0011-00 | 2025-07-15 | SDS-23A25-Y000-0113-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0113-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 09001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1409-RA | MTC-23A25-Y211-L000-1399-09001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 09 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0113-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0113-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0011-00 | 2025-07-15 | SDS-23A25-Y000-0113-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0113-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 10001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1410-RA | MTC-23A25-Y211-L000-1399-10001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 10 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0113-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0113-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0011-00 | 2025-07-15 | SDS-23A25-Y000-0113-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0113-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 11001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1411-RA | MTC-23A25-Y211-L000-1399-11001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 11 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0113-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0113-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0011-00 | 2025-07-15 | SDS-23A25-Y000-0113-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0113-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 12001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1412-RA | MTC-23A25-Y211-L000-1399-12001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 12 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0114-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0114-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0012-00 | 2025-07-15 | SDS-23A25-Y000-0114-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0114-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 13001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1413-RA | MTC-23A25-Y211-L000-1399-13001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 13 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0114-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0114-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0012-00 | 2025-07-15 | SDS-23A25-Y000-0114-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0114-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 14001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1414-RA | MTC-23A25-Y211-L000-1399-14001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 14 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0114-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0114-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0012-00 | 2025-07-15 | SDS-23A25-Y000-0114-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0114-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 15001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1415-RA | MTC-23A25-Y211-L000-1399-15001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 15 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0114-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0114-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0012-00 | 2025-07-15 | SDS-23A25-Y000-0114-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0114-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 16001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1416-RA | MTC-23A25-Y211-L000-1399-16001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 16 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0114-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0114-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0012-00 | 2025-07-15 | SDS-23A25-Y000-0114-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0114-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 17001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1417-RA | MTC-23A25-Y211-L000-1399-17001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 17 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0114-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0114-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0012-00 | 2025-07-15 | SDS-23A25-Y000-0114-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0114-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L000 | 1399 | 18001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L0-P-1418-RA | MTC-23A25-Y211-L000-1399-18001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 - PART 18 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0114-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0114-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0012-00 | 2025-07-15 | SDS-23A25-Y000-0114-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0114-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L001 | 1399 | 00001 | 00 | SD | 1:500 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L1-P-1400-RA | MTC-23A25-Y211-L001-1399-00001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 1 - OVERALL |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0109-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0109-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0007-00 | 2025-07-15 | SDS-23A25-Y000-0109-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0109-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L001 | 1399 | 05001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L1-P-1401-RA | MTC-23A25-Y211-L001-1399-05001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 1 - PART 05 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0109-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0109-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0007-00 | 2025-07-15 | SDS-23A25-Y000-0109-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0109-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L001 | 1399 | 06001 | 00 | SD | 1:100 | Special System | CLOCK |  | MTC-23A25-Y211-L001-1399-06001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 1 - PART 06 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0109-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0109-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0007-00 | 2025-07-15 | SDS-23A25-Y000-0109-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0109-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L002 | 1399 | 00001 | 00 | SD | 1:500 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L2-P-1400-RA | MTC-23A25-Y211-L002-1399-00001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 2 - OVERALL |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0110-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0110-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0008-00 | 2025-07-15 | SDS-23A25-Y000-0110-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0110-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L002 | 1399 | 03001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L2-P-1401-RA | MTC-23A25-Y211-L002-1399-03001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 2 - PART 03 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0110-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0110-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0008-00 | 2025-07-15 | SDS-23A25-Y000-0110-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0110-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L002 | 1399 | 04001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L2-P-1402-RA | MTC-23A25-Y211-L002-1399-04001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 2 - PART 04 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0110-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0110-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0008-00 | 2025-07-15 | SDS-23A25-Y000-0110-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0110-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L002 | 1399 | 05001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L2-P-1403-RA | MTC-23A25-Y211-L002-1399-05001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 2 - PART 05 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0110-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0110-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0008-00 | 2025-07-15 | SDS-23A25-Y000-0110-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0110-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y211 | L002 | 1399 | 06001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1399-T100-DR-L2-P-1404-RA | MTC-23A25-Y211-L002-1399-06001 | MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 2 - PART 06 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0110-01 | Code 3 | 2025-07-22 | SDS-23A25-Y000-0110-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0008-00 | 2025-07-15 | SDS-23A25-Y000-0110-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y000-0110-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 09001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-09001 | ICT RACK LAYOUT IN TR-01 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 11001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-11001 | ICT RACK LAYOUT IN TR-02 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 06001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-06001 | ICT RACK LAYOUT IN TR-03 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 16001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-16001 | ICT RACK LAYOUT IN TR-04 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 18001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-18001 | ICT RACK LAYOUT IN TR-05 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 07001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-07001 | ICT RACK LAYOUT IN TR-06 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 14001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-14001 | ICT RACK LAYOUT IN TR-07 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 01001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-01001 | ICT RACK LAYOUT IN SER-01 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 08001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-08001 | ICT RACK LAYOUT IN MHS-01 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 08002 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-08002 | ICT RACK LAYOUT IN BD-01 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 18002 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-18002 | ICT RACK LAYOUT IN MHS-02 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 18003 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1399-18003 | ICT RACK LAYOUT IN BD-02 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 09002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-09002 | SECURITY RACK LAYOUT IN TR-01 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 11002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-11002 | SECURITY RACK LAYOUT IN TR-02 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 06002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-06002 | SECURITY RACK LAYOUT IN TR-03 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 16002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-16002 | SECURITY RACK LAYOUT IN TR-04 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 18004 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-18004 | SECURITY RACK LAYOUT IN TR-05 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 07002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-07002 | SECURITY RACK LAYOUT IN TR-06 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 14002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-14002 | SECURITY RACK LAYOUT IN TR-07 | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 01002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-01002 | SECURITY RACK LAYOUT IN SER-01 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 08003 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-08003 | SECURITY RACK LAYOUT IN MHS-01 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 08004 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-08004 | SECURITY RACK LAYOUT IN BD-01 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 18005 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-18005 | SECURITY RACK LAYOUT IN MHS-02 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y301 | L000 | 1399 | 18006 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1399-18006 | SECURITY RACK LAYOUT IN BD-02 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-EAST 1393 | MTC | 23A25 | Y100 | L000 | 1393 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1393-T100-DR-L0-P-2000-RB | MTC-23A25-Y100-L000-1393-00001 | EMCT-TECHNICAL BLOCK-EAST-SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-EAST 1393 | MTC | 23A25 | Y108 | L000 | 1393 | 00001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1393-T100-DR-L0-P-2000-RB | MTC-23A25-Y108-L000-1393-00001 | EMCT-TECHNICAL BLOCK-EAST-SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-EAST 1393 | MTC | 23A25 | Y300 | L000 | 1393 | 00001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1393-T100-DR-L0-P-2000-RB | MTC-23A25-Y300-L000-1393-00001 | EMCT-TECHNICAL BLOCK-EAST-ICT (SCN) LAYOUTS - LEVEL 0 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0001-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0001-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-EAST 1393 | MTC | 23A25 | Y307 | L000 | 1393 | 00001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1393-T100-DR-L0-P-2000-RB | MTC-23A25-Y307-L000-1393-00001 | EMCT-TECHNICAL BLOCK-EAST-COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0008-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0008-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-EAST 1393 | MTC | 23A25 | Y301 | L000 | 1393 | 00001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1393-00001 | EMCT-TECHNICAL BLOCK-EAST - ICT RACK LAYOUT IN TR-04 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-EAST 1393 | MTC | 23A25 | Y301 | L000 | 1393 | 00002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1393-00002 | EMCT-TECHNICAL BLOCK-EAST - SECURITY RACK LAYOUT IN TR-04 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-NORTH 1394 | MTC | 23A25 | Y100 | L000 | 1394 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1394-T100-DR-L0-P-3000-RB | MTC-23A25-Y100-L000-1394-00001 | EMCT-TECHNICAL BLOCK-NORTH-SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-NORTH 1394 | MTC | 23A25 | Y300 | L000 | 1394 | 00001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1394-T100-DR-L0-P-3000-RB | MTC-23A25-Y300-L000-1394-00001 | EMCT-TECHNICAL BLOCK-NORTH-ICT (SCN) LAYOUTS - LEVEL 0 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0002-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-NORTH 1394 | MTC | 23A25 | Y307 | L000 | 1394 | 00001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1394-T100-DR-L0-P-3000-RB | MTC-23A25-Y307-L000-1394-00001 | EMCT-TECHNICAL BLOCK-NORTH-COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 |  |  | 13 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0009-00 | Code 4 | 2025-07-28 | SDS-23A25-Y000-0123-00 | Code 4 | ENG | SDS-23A25-Y300-0009-00 | 2025-07-15 | SDS-23A25-Y000-0123-00 | Code 4 | 2025-07-28 | Code 4 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-NORTH 1394 | MTC | 23A25 | Y301 | L000 | 1394 | 00001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1394-00001 | EMCT-TECHNICAL BLOCK-NORTH - ICT RACK LAYOUT IN TR-10 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-NORTH 1394 | MTC | 23A25 | Y301 | L000 | 1394 | 00002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1394-00002 | EMCT-TECHNICAL BLOCK-NORTH - SECURITY RACK LAYOUT IN TR-10 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-WEST 1395 | MTC | 23A25 | Y100 | L000 | 1395 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1395-T100-DR-L0-P-4002-RB | MTC-23A25-Y100-L000-1395-00001 | EMCT-TECHNICAL BLOCK-WEST-SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-WEST 1395 | MTC | 23A25 | Y108 | L000 | 1395 | 00001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1395-T100-DR-L0-P-4002-RB | MTC-23A25-Y108-L000-1395-00001 | EMCT-TECHNICAL BLOCK-WEST-SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-WEST 1395 | MTC | 23A25 | Y300 | L000 | 1395 | 00001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1395-T100-DR-L0-P-4000-RB | MTC-23A25-Y300-L000-1395-00001 | EMCT-TECHNICAL BLOCK-WEST-ICT (SCN) LAYOUTS - LEVEL 0 |  |  | 9 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0003-00 | Code 3 | 2025-07-24 | SDS-23A25-Y000-0117-00 | Code 3 | ENG | SDS-23A25-Y300-0003-00 | 2025-07-15 | SDS-23A25-Y000-0117-00 | Code 3 | 2025-07-24 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-WEST 1395 | MTC | 23A25 | Y307 | L000 | 1395 | 00001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1395-T100-DR-L0-P-4001-RB | MTC-23A25-Y307-L000-1395-00001 | EMCT-TECHNICAL BLOCK-WEST-COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 |  |  | 13 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0010-00 | Code 4 | 2025-07-28 | SDS-23A25-Y000-0124-00 | Code 4 | ENG | SDS-23A25-Y300-0010-00 | 2025-07-15 | SDS-23A25-Y000-0124-00 | Code 4 | 2025-07-28 | Code 4 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-WEST 1395 | MTC | 23A25 | Y301 | L000 | 1395 | 00001 | 00 | SD | N.T.S | Special System | LAN-ICT | --- | MTC-23A25-Y301-L000-1395-00001 | EMCT-TECHNICAL BLOCK-WEST - ICT RACK LAYOUT IN TR-09 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-WEST 1395 | MTC | 23A25 | Y301 | L000 | 1395 | 00002 | 00 | SD | N.T.S | Special System | LAN-SECURITY | --- | MTC-23A25-Y301-L000-1395-00002 | EMCT-TECHNICAL BLOCK-WEST - SECURITY RACK LAYOUT IN TR-09 | 2025-08-28 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL GUARD HOUSE 1396 | MTC | 23A25 | Y300 | L000 | 1396 | 00001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1396-T100-DR-L0-P-6000-RB | MTC-23A25-Y300-L000-1396-00001 | EMCT-TYPICAL GUARD HOUSE-ICT (SCN) LAYOUTS - LEVEL 0 |  |  | 14 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0004-00 | Code 3 | 2025-07-29 | SDS-23A25-Y000-0118-00 | Code 3 | ENG | SDS-23A25-Y300-0004-00 | 2025-07-15 | SDS-23A25-Y000-0118-00 | Code 3 | 2025-07-29 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL GUARD HOUSE 1396 | MTC | 23A25 | Y307 | L000 | 1396 | 00001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1396-T100-DR-L0-P-6000-RB | MTC-23A25-Y307-L000-1396-00001 | EMCT-TYPICAL GUARD HOUSE-COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 |  |  | 13 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0011-00 | Code 4 | 2025-07-28 | SDS-23A25-Y000-0125-00 | Code 4 | ENG | SDS-23A25-Y300-0011-00 | 2025-07-15 | SDS-23A25-Y000-0125-00 | Code 4 | 2025-07-28 | Code 4 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL GUARD HOUSE 1396 | MTC | 23A25 | Y211 | L000 | 1396 | 00001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1396-T100-DR-L0-P-6000-RB | MTC-23A25-Y211-L000-1396-00001 | EMCT-TYPICAL GUARD HOUSE-MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0103-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0103-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0001-00 | 2025-07-15 | SDS-23A25-Y000-0103-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0103-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL GUARD HOUSE 1396 | MTC | 23A25 | Y100 | L000 | 1396 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1396-T100-DR-L0-P-6000-RB | MTC-23A25-Y100-L000-1396-00001 | EMCT-TYPICAL GUARD HOUSE-SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL GUARD HOUSE 1396 | MTC | 23A25 | Y108 | L000 | 1396 | 00001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1396-T100-DR-L0-P-6000-RB | MTC-23A25-Y108-L000-1396-00001 | EMCT-TYPICAL GUARD HOUSE-SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-VISITOR MANAGEMENT CENTER 1397 | MTC | 23A25 | Y100 | L000 | 1397 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1397-T100-DR-L0-P-7000-RB | MTC-23A25-Y100-L000-1397-00001 | EMCT-VISITOR MANAGEMENT CENTER-SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-VISITOR MANAGEMENT CENTER 1397 | MTC | 23A25 | Y300 | L000 | 1397 | 00001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1397-T100-DR-L0-P-7000-RB | MTC-23A25-Y300-L000-1397-00001 | EMCT-VISITOR MANAGEMENT CENTER-ICT (SCN) LAYOUTS - LEVEL 0 |  |  | 14 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0005-00 | Code 3 | 2025-07-29 | SDS-23A25-Y000-0119-00 | Code 3 | ENG | SDS-23A25-Y300-0005-00 | 2025-07-15 | SDS-23A25-Y000-0119-00 | Code 3 | 2025-07-29 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-VISITOR MANAGEMENT CENTER 1397 | MTC | 23A25 | Y307 | L000 | 1397 | 00001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1397-T100-DR-L0-P-7000-RB | MTC-23A25-Y307-L000-1397-00001 | EMCT-VISITOR MANAGEMENT CENTER-COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0012-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0012-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-VISITOR MANAGEMENT CENTER 1397 | MTC | 23A25 | Y211 | L000 | 1397 | 00001 | 00 | SD | 1:100 | Special System | CLOCK | ADA-AUH0620022-1397-T100-DR-L0-P-7000-RB | MTC-23A25-Y211-L000-1397-00001 | EMCT-VISITOR MANAGEMENT CENTER-MEDIA HARDWARE CLOCK LAYOUTS - LEVEL 0 | 2025-08-14 |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0104-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0104-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0002-00 | 2025-07-15 | SDS-23A25-Y000-0104-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0104-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-VISITOR MANAGEMENT CENTER 1397 | MTC | 23A25 | Y204 | L000 | 1397 | 00001 | 00 | SD | 1:100 | Special System | TV | ADA-AUH0620022-1397-T100-DR-L0-P-7000-RB | MTC-23A25-Y204-L000-1397-00001 | EMCT-VISITOR MANAGEMENT CENTER-MEDIA HARDWARE TV LAYOUTS - LEVEL 0 |  |  | 6 | --- | 01 | 2025-07-30 | SDS-23A25-Y000-0104-01 | Code 3 | 2025-07-23 | SDS-23A25-Y000-0104-00 | UNDER REVIEW | ENG | SDS-23A25-Y000-0002-00 | 2025-07-15 | SDS-23A25-Y000-0104-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y000-0104-01 | 2025-07-30 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-WASTE MANAGEMENT 1401 | MTC | 23A25 | Y100 | L000 | 1401 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1401-T100-DR-L0-P-8000-RB | MTC-23A25-Y100-L000-1401-00001 | EMCT-WASTE MANAGEMENT-SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-WASTE MANAGEMENT 1401 | MTC | 23A25 | Y300 | L000 | 1401 | 00001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1401-T100-DR-L0-P-8000-RB | MTC-23A25-Y300-L000-1401-00001 | EMCT-WASTE MANAGEMENT-ICT (SCN) LAYOUTS - LEVEL 0 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0006-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-WASTE MANAGEMENT 1401 | MTC | 23A25 | Y108 | L000 | 1401 | 00001 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1401-T100-DR-L0-P-8000-RB | MTC-23A25-Y108-L000-1401-00001 | EMCT-WASTE MANAGEMENT-SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-WASTE MANAGEMENT 1401 | MTC | 23A25 | Y307 | L000 | 1401 | 00001 | 00 | SD | 1:100 | Special System | COMMUNICATION (WDN, DAS) | ADA-AUH0620022-1401-T100-DR-L0-P-8000-RB | MTC-23A25-Y307-L000-1401-00001 | EMCT-WASTE MANAGEMENT-COMMUNICATION (WDN, DAS) LAYOUTS - LEVEL 0 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0013-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL CHARGING STATION 1402 | MTC | 23A25 | Y100 | L000 | 1402 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1402-T100-DR-L0-P-5000-RB | MTC-23A25-Y100-L000-1402-00001 | EMCT-TYPICAL CHARGING STATION-SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL CHARGING STATION 1402 | MTC | 23A25 | Y300 | L000 | 1402 | 00001 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-1402-T100-DR-L0-P-5000-RB | MTC-23A25-Y300-L000-1402-00001 | EMCT-TYPICAL CHARGING STATION-ICT (SCN) LAYOUTS - LEVEL 0 |  |  | 21 | --- | 00 | 2025-07-15 | SDS-23A25-Y300-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y300-0007-00 | 2025-07-15 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y100 | L000 | 0000 | 00001 | 00 | SD | N.T.S | Security System | CCTV | --- | MTC-23A25-Y100-L000-0000-00001 | EMCT-EXTERNAL-SECURITY SYSTEM (CCTV) LAYOUTS - OVERALL | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y100 | L000 | 0000 | 00002 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-L18-T100-DR-P-1200-RB | MTC-23A25-Y100-L000-0000-00002 | EMCT-EXTERNAL-SECURITY SYSTEM (CCTV) LAYOUTS - L18 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y100 | L000 | 0000 | 00003 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-L19-T100-DR-P-1201-RB | MTC-23A25-Y100-L000-0000-00003 | EMCT-EXTERNAL-SECURITY SYSTEM (CCTV) LAYOUTS - L19 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y100 | L000 | 0000 | 00004 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-M17-T100-DR-P-1202-RB | MTC-23A25-Y100-L000-0000-00004 | EMCT-EXTERNAL-SECURITY SYSTEM (CCTV) LAYOUTS - M17 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y100 | L000 | 0000 | 00005 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-M18-T100-DR-P-1203-RB | MTC-23A25-Y100-L000-0000-00005 | EMCT-EXTERNAL-SECURITY SYSTEM (CCTV) LAYOUTS - M18 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y100 | L000 | 0000 | 00006 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-M19-T100-DR-P-1204-RB | MTC-23A25-Y100-L000-0000-00006 | EMCT-EXTERNAL-SECURITY SYSTEM (CCTV) LAYOUTS - M19 | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y300 | L000 | 0000 | 00001 | 00 | SD | N.T.S | Special System | ICT (SCN) | --- | MTC-23A25-Y300-L000-0000-00001 | EMCT-EXTERNAL-ICT (SCN) LAYOUTS - OVERALL | 2025-07-18 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y000-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y300 | L000 | 0000 | 00002 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-L18-T100-DR-P-1000-RB | MTC-23A25-Y300-L000-0000-00002 | EMCT-EXTERNAL-ICT (SCN) LAYOUTS - L18 | 2025-07-18 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y000-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y300 | L000 | 0000 | 00003 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-L19-T100-DR-P-1001-RB | MTC-23A25-Y300-L000-0000-00003 | EMCT-EXTERNAL-ICT (SCN) LAYOUTS - L19 | 2025-07-18 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y000-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y300 | L000 | 0000 | 00004 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-M17-T100-DR-P-1002-RB | MTC-23A25-Y300-L000-0000-00004 | EMCT-EXTERNAL-ICT (SCN) LAYOUTS - M17 | 2025-07-18 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y000-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y300 | L000 | 0000 | 00005 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-M18-T100-DR-P-1003-RB | MTC-23A25-Y300-L000-0000-00005 | EMCT-EXTERNAL-ICT (SCN) LAYOUTS - M18 | 2025-07-18 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y000-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-EXTERNAL 1399 | MTC | 23A25 | Y300 | L000 | 0000 | 00006 | 00 | SD | 1:100 | Special System | ICT (SCN) | ADA-AUH0620022-M19-T100-DR-P-1004-RB | MTC-23A25-Y300-L000-0000-00006 | EMCT-EXTERNAL-ICT (SCN) LAYOUTS - M19 | 2025-07-18 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y000-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00001 | 00 | SD | N.T.S | Security System | GENERAL | --- | MTC-23A25-Y000-L000-0000-00001 | SECURITY SYSTEM (SACS) EQUIPMENT SCHEDULE LAYOUTS LEVEL 0 - SHEET 01 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0004-01 | Code 3 | 2025-06-18 | SDS-23A25-Y100-0004-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0004-00 | 2025-05-23 | SDS-23A25-Y100-0004-00 | Code 3 | 2025-06-18 | Code 3 | SDS-23A25-Y100-0004-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00002 | 00 | SD | N.T.S | Security System | GENERAL | --- | MTC-23A25-Y000-L000-0000-00002 | SECURITY SYSTEM (SACS) EQUIPMENT SCHEDULE LAYOUTS LEVEL 0 - SHEET 02 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0004-01 | Code 3 | 2025-06-18 | SDS-23A25-Y100-0004-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0004-00 | 2025-05-23 | SDS-23A25-Y100-0004-00 | Code 3 | 2025-06-18 | Code 3 | SDS-23A25-Y100-0004-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00003 | 00 | SD | N.T.S | Security System | GENERAL | --- | MTC-23A25-Y000-L000-0000-00003 | SECURITY SYSTEM (SACS) EQUIPMENT SCHEDULE LAYOUTS LEVEL 0 - SHEET 03 |  |  | 4 | --- | 01 | 2025-08-01 | SDS-23A25-Y100-0004-01 | Code 3 | 2025-06-18 | SDS-23A25-Y100-0004-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0004-00 | 2025-05-23 | SDS-23A25-Y100-0004-00 | Code 3 | 2025-06-18 | Code 3 | SDS-23A25-Y100-0004-01 | 2025-08-01 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L001 | 0000 | 00001 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L001-0000-00001 | SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT - LEVEL 1 |  |  | 33 | 12 | 00 | 2025-06-11 | SDS-23A25-Y100-0005-00 | Code 2 | 2025-07-14 | SDS-23A25-Y100-0027-00 | Code 2 |  | SDS-23A25-Y100-0005-00 | 2025-06-11 | SDS-23A25-Y100-0027-00 | Code 2 | 2025-07-14 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L002 | 0000 | 00001 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L002-0000-00001 | SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT - LEVEL 2 |  |  | 55 | 34 | 00 | 2025-06-11 | SDS-23A25-Y100-0006-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0006-00 | 2025-06-11 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00007 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00007 | EMCT-TECHNICAL BLOCK-EAST- SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT- LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00008 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00008 | EMCT-TECHNICAL BLOCK-NORTH- SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT- LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00009 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00009 | EMCT-TECHNICAL BLOCK-WEST- SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT- LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00010 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00010 | EMCT-TYPICAL GUARD HOUSE- SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT- LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00011 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00011 | EMCT-VISITOR MANAGEMENT CENTRE- SECURITY SYSTEM (CCTV) SCHEDULES LAYOUT- LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00012 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00012 | EMCT-WASTE MANAGEMENT- SECURITY SYSTEM (CCTV) SCHEDULES LAYOUT- LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00013 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00013 | EMCT-TYPICAL CHARGING STATION- SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT- LEVEL 0 |  |  | 32 | 11 | 00 | 2025-07-04 | SDS-23A25-Y100-0007-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0007-00 | 2025-07-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00014 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00014 | SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT - LEVEL 0 (SHEET 01) | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00015 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00015 | SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT - LEVEL 0 (SHEET 02) | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00016 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00016 | SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT - LEVEL 0 (SHEET 03) | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00017 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00017 | SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT - LEVEL 0 (SHEET 04) | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00018 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00018 | SECURITY SYSTEM (CCTV) SCHEDULE LAYOUT - LEVEL 0 (SHEET 05) | 2025-07-15 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-Y100-0013-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0013-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00019 | 00 | SD | N.T.S | Security System | CCTV SCHEDULES | --- | MTC-23A25-Y100-L000-0000-00019 | SCHEDULES for cctv EXTERNAL | 2025-08-10 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L001 | 0000 | 00001 | 00 | SD | N.T.S | Security System | SACS SCHEDULES | --- | MTC-23A25-Y108-L001-0000-00001 | SECURITY SYSTEM (SACS) SCHEDULE LAYOUT - LEVEL 1 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0132-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0132-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0009-00 | 2025-07-15 | SDS-23A25-Y100-0132-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0132-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L002 | 0000 | 00002 | 00 | SD | N.T.S | Security System | SACS SCHEDULES | --- | MTC-23A25-Y108-L002-0000-00002 | SECURITY SYSTEM (SACS) SCHEDULE LAYOUT - LEVEL 2 | 2025-07-12 |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0133-01 | Code 3 | 2025-07-23 | SDS-23A25-Y100-0133-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0010-00 | 2025-07-15 | SDS-23A25-Y100-0133-00 | Code 3 | 2025-07-23 | Code 3 | SDS-23A25-Y100-0133-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00003 | 00 | SD | N.T.S | Security System | SACS SCHEDULES | --- | MTC-23A25-Y108-L000-0000-00003 | EMCT-WASTE MANAGEMENT-SECURITY SYSTEM (SACS) EQUIPMENT SCHEDULE LAYOUTS LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00004 | 00 | SD | N.T.S | Security System | SACS SCHEDULES | --- | MTC-23A25-Y108-L000-0000-00004 | EMCT-TECHNICAL BLOCK WEST-SECURITY SYSTEM (SACS) EQUIPMENT SCHEDULE LAYOUTS LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00005 | 00 | SD | N.T.S | Security System | SACS SCHEDULES | --- | MTC-23A25-Y108-L000-0000-00005 | EMCT-TYPICAL GUARD HOUSE-SECURITY SYSTEM (SACS) EQUIPMENT SCHEDULE LAYOUTS LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00006 | 00 | SD | N.T.S | Security System | SACS SCHEDULES | --- | MTC-23A25-Y108-L000-0000-00006 | EMCT-TECHNICAL BLOCK EAST-SECURITY SYSTEM (SACS) EQUIPMENT SCHEDULE LAYOUTS LEVEL 0 |  |  | 5 | --- | 01 | 2025-07-31 | SDS-23A25-Y100-0128-01 | Code 3 | 2025-07-22 | SDS-23A25-Y100-0128-00 | UNDER REVIEW | ENG | SDS-23A25-Y100-0008-00 | 2025-07-15 | SDS-23A25-Y100-0128-00 | Code 3 | 2025-07-22 | Code 3 | SDS-23A25-Y100-0128-01 | 2025-07-31 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00018 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00018 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00019 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00019 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00020 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00020 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00022 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00022 | EMCT - CCTV CEILING PENDANT _ TYPICAL MOUNTING DETAILS & CAMERA BRACKETS INSTALLATION ASB-1 | 2025-08-07 |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y100-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0015-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00023 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00023 | EMCT - CTV - FALSE CEILING-TYPICAL MOUNTING DETAILS & CAMERA BRACKETS INSTALLATION ASB-3 | 2025-08-07 |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y100-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0015-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00024 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00024 | EMCT-CCTV-WALL MOUNT - TYPICAL MOUNTING DETAILS & CAMERA BRACKETS INSTALLATION T91E61 | 2025-08-07 |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y100-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0015-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00025 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00025 | EMCT- CCTV- COLUMN MOUNTED - TYPICAL MOUNTING DETAILS & CAMERA BRACKETS INSTALLATION T91E61 | 2025-08-07 |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y100-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0015-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00026 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00026 | CCTV TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00027 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00027 | CCTV TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00028 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00028 | CCTV TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y100 | L000 | 0000 | 00029 | 00 | SD | N.T.S | Security System | CCTV TYPICAL | --- | MTC-23A25-Y100-L000-0000-00029 | CCTV TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00021 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00021 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00022 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00022 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00023 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00023 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00024 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00024 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00025 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00025 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00026 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00026 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00027 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00027 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y108 | L000 | 0000 | 00028 | 00 | SD | N.T.S | Security System | SACS TYPICAL | --- | MTC-23A25-Y108-L000-0000-00028 | SACS TYPICAL | 2025-08-07 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | T000 | L000 | 0000 | 00001 | 00 | SD | N.T.S | Telecommunications | SCHAMATICS | --- | MTC-23A25-T000-L000-0000-00001 | STRUCTURED CABLING NETWORK SCHEMATIC DIAGRAM (SHEET 01) | 2025-08-14 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-T000-0001-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-T000-0001-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | T000 | L000 | 0000 | 00002 | 00 | SD | N.T.S | Telecommunications | SCHAMATICS | --- | MTC-23A25-T000-L000-0000-00002 | STRUCTURED CABLING NETWORK SCHEMATIC DIAGRAM (SHEET 02) | 2025-08-14 |  | 8 | --- | 00 | 2025-07-28 | SDS-23A25-T000-0001-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-T000-0001-00 | 2025-07-28 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00004 | 00 | SD | N.T.S | Security System | SCHAMATICS | --- | MTC-23A25-Y000-L000-0000-00004 | SCHAMATICS | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00005 | 00 | SD | N.T.S | Security System | SCHAMATICS | --- | MTC-23A25-Y000-L000-0000-00005 | SCHAMATICS | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00006 | 00 | SD | N.T.S | Security System | SCHAMATICS | --- | MTC-23A25-Y000-L000-0000-00006 | SCHAMATICS | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00007 | 00 | SD | N.T.S | Security System | SCHAMATICS | --- | MTC-23A25-Y000-L000-0000-00007 | SCHAMATICS | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00008 | 00 | SD | N.T.S | Security System | SCHAMATICS | --- | MTC-23A25-Y000-L000-0000-00008 | SCHAMATICS | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00009 | 00 | SD | N.T.S | Security System | SCHAMATICS | --- | MTC-23A25-Y000-L000-0000-00009 | SCHAMATICS | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | GENERAL | MTC | 23A25 | Y000 | L000 | 0000 | 00010 | 00 | SD | N.T.S | Security System | SCHAMATICS | --- | MTC-23A25-Y000-L000-0000-00010 | SCHAMATICS | 2025-08-14 |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00001 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00001 | New Relocation of R2 AWFON Duct Layout (Sheet 01 of 02) |  |  | 48 | 27 | 00 | 2025-02-28 | SDS-23A25-C000-0001-00 | Code 4 | 2025-04-17 | SDS-23A25-C000-0001-00 | Code 4 | ENG | SDS-23A25-C000-0001-00 | 2025-02-28 | SDS-23A25-C000-0001-00 | Code 4 | 2025-04-17 | Code 4 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00002 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00002 | New Relocation of R2 AWFON Duct Layout (Sheet 02 of 02) |  |  | 48 | 27 | 00 | 2025-02-28 | SDS-23A25-C000-0001-00 | Code 4 | 2025-04-17 | SDS-23A25-C000-0001-00 | Code 4 | ENG | SDS-23A25-C000-0001-00 | 2025-02-28 | SDS-23A25-C000-0001-00 | Code 4 | 2025-04-17 | Code 4 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Camera Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00003 | 00 | SD | N.T.S | Civil | Camera Layout | --- | MTC-23A25-C000-0000-0000-00003 | EMCT Building Temporary Airside Landside Fence Shifting-Proposed Cameras Layout |  |  | 103 | 82 | 00 | 2025-04-24 | SDS-23A25-C000-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0002-00 | 2025-04-24 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Camera Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00004 | 00 | SD | N.T.S | Civil | Lighting Layout | --- | MTC-23A25-C000-0000-0000-00004 | EMCT Building Temporary Airside Landside Fence Shifting-Proposed Lighting Layout |  |  | 103 | 82 | 00 | 2025-04-24 | SDS-23A25-C000-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0002-00 | 2025-04-24 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00005 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00005 | New Relocation of R2 AWFON Duct Layout (Sheet 01 of 02) |  |  | 47 | 33 | 01 | 2025-06-19 | SDS-23A25-C000-0007-01 | Code 2 | 2025-06-13 | SDS-23A25-C000-0007-00 | UNDER REVIEW | ENG | SDS-23A25-C000-0003-00 | 2025-05-13 | SDS-23A25-C000-0007-00 | Code 2 | 2025-06-13 | Code 2 | SDS-23A25-C000-0007-01 | 2025-06-19 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00006 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00006 | New Relocation of R2 AWFON Duct Layout (Sheet 02 of 02) |  |  | 31 | 10 | 00 | 2025-05-13 | SDS-23A25-C000-0003-00 | Code 2 | 2025-06-13 | SDS-23A25-C000-0007-00 | Code 2 |  | SDS-23A25-C000-0003-00 | 2025-05-13 | SDS-23A25-C000-0007-00 | Code 2 | 2025-06-13 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00007 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00007 | EMCT-EXTERNAL DUCT LAYOUT |  |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00008 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00008 | RE-ROUTE R1 AWFON FIBER OPTIC CABLE LAYOUT OVERALL |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-C000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0004-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00009 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00009 | RE-ROUTE R1 AWFON FIBER OPTIC CABLE LAYOUT - SECTOR C5 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-C000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0004-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00010 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00010 | RE-ROUTE R1 AWFON FIBER OPTIC CABLE LAYOUT - SECTOR C6 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-C000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0004-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00011 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00011 | RE-ROUTE R1 AWFON FIBER OPTIC CABLE LAYOUT - SECTOR D6 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-C000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0004-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00012 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00012 | RE-ROUTE R1 AWFON FIBER OPTIC CABLE LAYOUT - SECTOR E6 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-C000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0004-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00013 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00013 | RE-ROUTE R1 AWFON FIBER OPTIC CABLE LAYOUT - SECTOR E5 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-C000-0004-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0004-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00014 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00014 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT OVERALL |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00015 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00015 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT - SECTOR B2 |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00016 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00016 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT - SECTOR B3 |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00017 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00017 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT - SECTOR B4 |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00018 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00018 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT - SECTOR C2 |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00019 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00019 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT - SECTOR C3 |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00020 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00020 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT - SECTOR C4 |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | Duct Layout | MTC | 23A25 | C000 | 0000 | 0000 | 00021 | 00 | SD | N.T.S | Civil | Duct Layout | --- | MTC-23A25-C000-0000-0000-00021 | CAMPAS BAKBONE CABLE FOR EMCT TO ZIA LAYOUT - SECTOR C5 |  |  | 14 | --- | 00 | 2025-07-22 | SDS-23A25-C000-0005-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-C000-0005-00 | 2025-07-22 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | 00L0 | 1399 | 00001 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1201-RB | MTC-23A25-Y100-00L0-00P1-00001 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 01 |  |  | 77 | 56 | 00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | SDS-23A25-Y100-0001-00 | Code 3 | ENG | SDS-23A25-Y100-0001-00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | 00L0 | 1399 | 00002 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1202-RB | MTC-23A25-Y100-00L0-00P2-00002 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 02 |  |  | 77 | 56 | 00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | SDS-23A25-Y100-0001-00 | Code 3 | ENG | SDS-23A25-Y100-0001-00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | 00L0 | 1399 | 00003 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1203-RB | MTC-23A25-Y100-00L0-00P3-00003 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 03 |  |  | 77 | 56 | 00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | SDS-23A25-Y100-0001-00 | Code 3 | ENG | SDS-23A25-Y100-0001-00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | 00L0 | 1399 | 00004 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1204-RB | MTC-23A25-Y100-00L0-00P4-00004 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 04 |  |  | 77 | 56 | 00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | SDS-23A25-Y100-0001-00 | Code 3 | ENG | SDS-23A25-Y100-0001-00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y100 | 00L0 | 1399 | 00005 | 00 | SD | 1:100 | Security System | CCTV | ADA-AUH0620022-1399-T100-DR-L0-P-1205-RB | MTC-23A25-Y100-00L0-00P5-00005 | SECURITY SYSTEM (CCTV) LAYOUTS - LEVEL 0 - PART 05 |  |  | 77 | 56 | 00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | SDS-23A25-Y100-0001-00 | Code 3 | ENG | SDS-23A25-Y100-0001-00 | 2025-03-13 | SDS-23A25-Y100-0001-00 | Code 3 | 2025-05-29 | Code 3 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | 00L0 | 1399 | 1 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1201-RB | MTC-23A25-Y108-00L0-00P1-00001 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 01 |  |  | 139 | 118 | 00 | 2025-03-19 | SDS-23A25-Y100-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0002-00 | 2025-03-19 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | 00L0 | 1399 | 2 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1202-RB | MTC-23A25-Y108-00L0-00P2-00002 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 02 |  |  | 139 | 118 | 00 | 2025-03-19 | SDS-23A25-Y100-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0002-00 | 2025-03-19 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | 00L0 | 1399 | 3 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1203-RB | MTC-23A25-Y108-00L0-00P3-00003 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 03 |  |  | 139 | 118 | 00 | 2025-03-19 | SDS-23A25-Y100-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0002-00 | 2025-03-19 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | 00L0 | 1399 | 4 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1204-RB | MTC-23A25-Y108-00L0-00P4-00004 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 04 |  |  | 139 | 118 | 00 | 2025-03-19 | SDS-23A25-Y100-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0002-00 | 2025-03-19 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y108 | 00L0 | 1399 | 5 | 00 | SD | 1:100 | Security System | SACS | ADA-AUH0620022-1399-T100-DR-L0-P-1205-RB | MTC-23A25-Y108-00L0-00P5-00005 | SECURITY SYSTEM (SACS) LAYOUTS - LEVEL 0 - PART 05 |  |  | 139 | 118 | 00 | 2025-03-19 | SDS-23A25-Y100-0002-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y100-0002-00 | 2025-03-19 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-EAST 1393 | MTC | 23A25 | Y305 | L000 | 1393 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1393-00001 | EMCT - TECHNICAL BLOCK- EAST- TETRA LAYOUT - LEVEL 0 |  |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-NORTH 1394 | MTC | 23A25 | Y305 | L000 | 1394 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1394-00001 | EMCT - TECHNICAL BLOCK- NORTH - TETRA LAYOUT - LEVEL 0 |  |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TECHNICAL BLOCK-WEST 1395 | MTC | 23A25 | Y305 | L000 | 1395 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1395-00001 | EMCT - TECHNICAL BLOCK- WEST- TETRA LAYOUT - LEVEL 0 |  |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-TYPICAL GUARD HOUSE 1396 | MTC | 23A25 | Y305 | L000 | 1396 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1396-00001 | EMCT - TYPICAL GUARD HOUSE- TETRA LAYOUT - LEVEL 0 |  |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-VISITOR MANAGEMENT CENTER 1397 | MTC | 23A25 | Y305 | L000 | 1397 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1397-00001 | EMCT - VISITOR MANAGEMENT CENTER- TETRA LAYOUT - LEVEL 0 |  |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-WASTE MANAGEMENT 1401 | MTC | 23A25 | Y305 | L000 | 1401 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1401-00001 | EMCT - WASTE MANAGEMENT- TETRA LAYOUT - LEVEL 0 |  |  | --- | --- | -- | --- |  | --- | --- |  | --- |  |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-00001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0-OVERALL |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 01001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-01001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 01 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 02001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-02001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 02 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 03001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-03001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 03 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 04001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-04001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 04 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 05001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-05001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 05 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 06001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-06001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 06 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 07001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-07001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 07 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 08001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-08001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 08 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0014-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0014-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 09001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-09001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 09 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 10001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-10001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 10 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 11001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-11001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 11 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 12001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-12001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 12 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 13001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-13001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 13 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 14001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-14001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 14 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 15001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-15001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 15 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 16001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-16001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 16 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 17001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-17001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 17 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L000 | 1399 | 18001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L000-1399-18001 | EMCT BUILDING TETRA LAYOUT-LEVEL 0- PART 18 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0015-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0015-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L001 | 1399 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L001-1399-00001 | EMCT BUILDING TETRA LAYOUT-LEVEL 1- OVERALL |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0016-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L001 | 1399 | 05001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L001-1399-05001 | EMCT BUILDING TETRA LAYOUT-LEVEL 1- PART 05 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0016-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L001 | 1399 | 14001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L001-1399-14001 | EMCT BUILDING TETRA LAYOUT-LEVEL 1- PART 14 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0016-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L001 | 1399 | 15001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L001-1399-15001 | EMCT BUILDING TETRA LAYOUT-LEVEL 1- PART 15 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0016-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0016-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L002 | 1399 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L002-1399-00001 | EMCT BUILDING TETRA LAYOUT-LEVEL 2- OVERALL |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0017-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L002 | 1399 | 03001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L002-1399-03001 | EMCT BUILDING TETRA LAYOUT-LEVEL 2- PART 03 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0017-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L002 | 1399 | 04001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L002-1399-04001 | EMCT BUILDING TETRA LAYOUT-LEVEL 2- PART 04 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0017-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L002 | 1399 | 05001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L002-1399-05001 | EMCT BUILDING TETRA LAYOUT-LEVEL 2- PART 05 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0017-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L002 | 1399 | 06001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L002-1399-06001 | EMCT BUILDING TETRA LAYOUT-LEVEL 2- PART 06 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0017-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L002 | 1399 | 14001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L002-1399-14001 | EMCT BUILDING TETRA LAYOUT-LEVEL 2- PART 14 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0017-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L002 | 1399 | 15001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L002-1399-15001 | EMCT BUILDING TETRA LAYOUT-LEVEL 2- PART 15 |  |  | 1 | --- | 00 | 2025-08-04 | SDS-23A25-Y000-0017-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0017-00 | 2025-08-04 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L00M | 1399 | 00001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L00M-1399-00001 | EMCT BUILDING TETRA LAYOUT-LEVEL M- OVERALL |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y000-0018-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0018-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L00M | 1399 | 06001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L00M-1399-06001 | EMCT BUILDING TETRA LAYOUT-LEVEL M- PART 06 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y000-0018-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0018-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L00M | 1399 | 12001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L00M-1399-12001 | EMCT BUILDING TETRA LAYOUT-LEVEL M- PART 12 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y000-0018-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0018-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L00M | 1399 | 14001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L00M-1399-14001 | EMCT BUILDING TETRA LAYOUT-LEVEL M- PART 14 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y000-0018-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0018-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L00M | 1399 | 15001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L00M-1399-15001 | EMCT BUILDING TETRA LAYOUT-LEVEL M- PART 15 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y000-0018-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0018-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
--- | EMCT-BUILDING 1399 | MTC | 23A25 | Y305 | L00M | 1399 | 18001 | 00 | SD | N.T.S | Special System | TETRA | --- | MTC-23A25-Y305-L00M-1399-18001 | EMCT BUILDING TETRA LAYOUT-LEVEL M- PART 18 |  |  | 0 | --- | 00 | 2025-08-05 | SDS-23A25-Y000-0018-00 | --- | --- |  | UNDER REVIEW |  | SDS-23A25-Y000-0018-00 | 2025-08-05 |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---

## Dashboard
|  |  | 359 | 267 | 74.37% |  | 92 |  | 0 | 5 | 8 | 5 | 0 | 249 |  |  | 0
| 315 |  | TOTAL QUANTITY | SUBMITTED |  |  | REV 0 TO GO |  | CODE 1 | CODE 2 | CODE 3 | CODE 4 | CODE 5 | UNDER REVIEW
| 294 |  |  | 247 |  |  | 91 |  | 0 | 4 | 8 | 3 | 0 | 232
Security System | Security System/Special System/ICT/Telecom | CCTV | 46 | 40 | 86.96% |  | 6 |  | 0 | 3 | 5 | 0 | 0 | 32
Security System |  | SACS | 37 | 37 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 37
Special System |  | ICT (SCN) | 39 | 13 | 33.33% |  | 26 |  | 0 | 0 | 3 | 0 | 0 | 10
Special System |  | COMMUNICATION (WDN, DAS) | 35 | 35 | 100% |  | 0 |  | 0 | 0 | 0 | 3 | 0 | 32
Special System |  | TV | 28 | 28 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 28
Special System |  | CLOCK | 29 | 29 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 29
Special System |  | LAN-ICT | 15 | 0 | 0% |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0
Special System |  | LAN-SECURITY | 15 | 0 | 0% |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0
Security System |  | SACS TYPICAL | 11 | 0 | 0% |  | 11 |  | 0 | 0 | 0 | 0 | 0 | 0
Security System |  | CCTV TYPICAL | 8 | 4 | 50% |  | 4 |  | 0 | 0 | 0 | 0 | 0 | 4
Security System |  | CCTV SCHEDULES | 15 | 14 | 93.33% |  | 1 |  | 0 | 1 | 0 | 0 | 0 | 13
Security System |  | SACS SCHEDULES | 6 | 6 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 6
Security System |  | SCHAMATICS | 7 | 0 | 0% |  | 7 |  | 0 | 0 | 0 | 0 | 0 | 0
Security System |  | GENERAL | 3 | 3 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 3
Special System |  | TETRA | 42 | 36 | 85.71% |  | 6 |  | 0 | 0 | 0 | 0 | 0 | 36
Telecommunications |  | SCHAMATICS | 2 | 2 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 2
| 21 |  |  | 20 |  |  | 1 |  | 0 | 1 | 0 | 2 | 0 | 17
Civil | Civil | Duct Layout | 19 | 18 | 94.74% |  | 1 |  | 0 | 1 | 0 | 2 | 0 | 15
Civil |  | Camera Layout | 1 | 1 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 1
Civil |  | Lighting Layout | 1 | 1 | 100% |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 1
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL | CIVIL | CIVIL | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Barrier Fence | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | NDRC | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Power and Lighting Trench Layout | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Electric Manhole | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | CCTV and Radar Trench Layout | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Communication Trench Layout | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Manhole | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Survey Control Points | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Chain Link Fence Foundation | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | Foundation Detail | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
CIVIL |  | GENERAL | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
ARCHITECTURE | ARCH | ARCHITECTURAL DRAWINGS | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0
ARCHITECTURE |  | GENERAL | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drawing List | GEN | GENERAL | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0
| 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL | STRUCTURE | General | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Radar and Camera Pole | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Foundation Detail | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Precast Manhole Typical | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Precast Foundation Details | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Pilling Setting | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Pilling Layout | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Footing Detail | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | UPS BASE STAND | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
STRUCTURAL |  | Branch Duct bank connection | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MECHANICAL | MCH | HVAC LAYOUT | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0
MECHANICAL |  | AIR CONDITIONING | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0

## Sheet2
EMCT-TECHNICAL BLOCK-EAST 1393 | 00001
EMCT-TECHNICAL BLOCK-NORTH 1394 | 01001
EMCT-TECHNICAL BLOCK-WEST 1395 | 02001
EMCT-TYPICAL GUARD HOUSE 1396 | 03001
EMCT-VISITOR MANAGEMENT CENTER 1397 | 04001
EMCT-WASTE MANAGEMENT 1401 | 05001
06001
07001
08001
09001
10001
11001
12001
13001
14001
15001
16001
17001
18001

## Sheet1 (hidden)
SUBMISSION WEEK |  | <42566 | <42573 | <42580 | <42587 | <42594 | <42601 | <42608 | <42615 | <42622 | <42629 | <42636 | <42643 | <42650 | <42657 | <42664 | <42671 | <42678 | <42685 | <42692 | <42699 | <42706 | <42713 | <42720 | <42727 | <42734 | <42741 | <42748 | <42755 | <42762 | <42769 | <42776 | <42783 | <42790 | <42797 | <42804 | <42811 | <42818 | <42825 | <42832 | <42839 | <42846 | <42853 | <42860 | <42867 | <42874 | <42881 | <42888 | <42895 | <42972 | < | < | < | < | < | < | < | < | < | <
|  | >=42559 | >=42566 | >=42573 | >=42580 | >=42587 | >=42594 | >=42601 | >=42608 | >=42615 | >=42622 | >=42629 | >=42636 | >=42643 | >=42650 | >=42657 | >=42664 | >=42671 | >=42678 | >=42685 | >=42692 | >=42699 | >=42706 | >=42713 | >=42720 | >=42727 | >=42734 | >=42741 | >=42748 | >=42755 | >=42762 | >=42769 | >=42776 | >=42783 | >=42790 | >=42797 | >=42804 | >=42811 | >=42818 | >=42825 | >=42832 | >=42839 | >=42846 | >=42853 | >=42860 | >=42867 | >=42874 | >=42881 | >=42888 | >=42895 | >=42902 | >=42909 | >=42916 | >=42923 | >=42930 | >=42937 | >=42944 | >=42951 | >=42958 | >=42965
 | time axis 2016-07-08 to 2017-08-25
 | time axis 2016-07-08 to 2017-08-25
 | time axis 2016-07-01 to 2017-08-25
CMA REV 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CMA REV >0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL SUBM |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CUM REV 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Data (hidden)
Data Date | 2025-08-05 |  | <=45786 | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856 | <=45863 | <=45870
Cutoff | 2025-08-01 |  | >45779 | >45786 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849 | >45856 | >45863
|  |  | W -12 | W -11 | W -10 | W -9 | W -8 | W -7 | W -6 | W -5 | W -4 | W -3 | W -2 | W -1 | This Week
|  |  | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01
|  | Submitted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | <=45786 | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856
APPROVED | #REF! |  | >0 | >45786 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849
UNDER REVIEW | #REF! |  | Over | 11 Weeks | 10 Weeks | 9 Weeks | 8 Weeks | 7 Weeks | 6 Weeks | 5 Weeks | 4 Weeks | 3 Weeks | 2 Weeks
REJECTED | #REF! | Pending Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REV. 0 TO GO | #REF! | Cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | <=45702 | <=45709 | <=45716 | <=45723 | <=45730 | <=45737 | <=45744 | <=45751 | <=45758 | <=45765 | <=45772 | <=45779 | <=45786 | <=45793 | <=45800 | <=45807 | <=45814 | <=45821 | <=45828 | <=45835 | <=45842 | <=45849 | <=45856 | <=45863 | <=45870
|  |  | >45695 | >45702 | >45709 | >45716 | >45723 | >45730 | >45737 | >45744 | >45751 | >45758 | >45765 | >45772 | >45779 | >45786 | >45793 | >45800 | >45807 | >45814 | >45821 | >45828 | >45835 | >45842 | >45849 | >45856 | >45863
|  |  | W -24 | W -23 | W -22 | W -21 | W -20 | W -19 | W -18 | W -17 | W -16 | W -15 | W -14 | W -13 | W -12 | W -11 | W -10 | W -9 | W -8 | W -7 | W -6 | W -5 | W -4 | W -3 | W -2 | W -1 | THIS WEEK
|  |  | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Q.ty Reviewed (or UR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rev Time Overdue (Avg) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0